## NetEng MASTER
OSP SID | Property Name | Status | Internal Notes | Pending Status (Internal) | MR Cert - End Date | Unit # | Business Unit | Agreement STATUS | Account/Project Manager | NetEng PM | Network/ GPON Eng | Region | Address | Type | OSP | Router | GPON Shelf | Bulk RF ? | Platform [ALU/ZTE/SE] | PON [8Port/NO GIG] | In-Unit ONT/CPE | In-Unit RTR? | SOW Submitted | SubID Requested? | MDF gear ready for pick-up? | MDF Gear Installed? | MDF Gear X-Connected? | MR Cert to EXE | NOC/T2 Handover | Coffee Talk Notes
| Avalon Phase 1 [Avalon Homes ] | Certified |  |  | 2014-01-01 | 101 | Fision Home | Received | Miguel Castillo |  | Edward/Jose |  | 2800 Old Milton Pkwy Alpharetta, GA 30009 | New Construction | Avalon - ASR9006 - 10.110.255.26 |  | Avalon | Yes | ALU |  | I-241G-B
| Aqualina | Certified |  |  | 2014-05-15 | 1 | Demo | Not Applicable | Leticia Suarez |  | Edward |  |  | New Construction | Trump Hollywood -7606S |  | Demo |  | SE |  | NA
| Blue Condominiums | Certified |  |  | 2014-05-29 | 330 | Fision Home | Received |  |  |  |  | 601 NE 36th Street Miami, FL 33137 | Conversion/OverBuild | Midtown 2 - 7606 |  | Blue Condo |  | ZTE |  | F668
| Blue Condominiums | Certified |  |  | 2014-05-29 | 1 | Demo | Not Applicable |  |  |  |  | 601 NE 36th Street Miami, FL 33137 | Conversion/OverBuild | Midtown 2 - 7606 |  | Blue Condo |  | SE |  | F668
| Oceana Bal Harbour Trailer | Certified |  |  | 2014-06-06 | 1 | Demo | Not Applicable |  |  |  |  | 10201 Collins Avenue, Bal Harbour, FL 33154 |  | St Regis - ASR9006 - 10.63.255.57 |  | NA |  | SE |  | NA
| Paraiso Bay | Certified |  |  | 2014-06-10 | 1 | Demo | Not Applicable | Roger Bartlett |  | Lik |  | 600 NE 31st St, Miami, FL 33137 | New Construction | Onyx -7606S |  | NA | No | SE |  | NA
| Marina Palms | Certified |  |  | 2014-06-12 | 1 | Demo | Not Applicable | Roger Bartlett |  | Edward |  | 7111, 17211, 17301 Biscayne Blvd., North Miami Beach, FL 33160 | New Construction | Pen2 -7606s |  | NA |  | SE |  | NA
| Journeys End | Certified |  |  | 2014-06-26 | 471 | Fision Home | Received |  |  | Edward/Jose |  | 6400 Journeys End Blvd. Lake Worth, FL 33467 |  | Journeys End - ASR9K |  | Journeys End |  | ALU
| St Regis Bal Harbour | Certified |  |  | 2014-06-26 | 1 | Demo | Not Applicable | Bob Smith |  |  |  | 9703 Collins Avenue Miami, FL 33154 |  | Canyon Ranch |  | Boca Woods |  | SE |  | NA
| Boca Woods | Certified |  |  | 2014-09-22 | 645 | Fision Home | Received |  |  |  |  | 10471 Boca Woods Lane Boca Raton, FL 33428 |  | Boca Woods - ASR9006 |  | Boca Woods |  | ALU
| Boca Marina | Certified |  |  | 2014-10-31 | 86 | Fision Home | Received |  |  |  |  | 5150 N Federal Hwy Boca Raton, FL 33487 |  | BY&YC - ASR9006 |  | BY&RC |  | ZTE |  | F668
| BARU | Certified |  |  | 2014-11-17 | 1 | Demo | Not Applicable | Maria/David R |  | Edward/Felix |  |  | Conversion/OverBuild | Midtown 2 7606 |  | NA | No | SE |  | NA
| 200 East | Certified |  |  | 2014-11-19 | 1 | Demo | Not Applicable | Victor Martinez |  | Edward |  | 200 East Palmetto Park Boca Raton, FL 33432 | Upgrade | 200 East - ASR9006 |  | Demo | No | SE |  | NA
| Sun Valley | Certified |  |  | 2014-12-20 | 1 | Demo | Not Applicable | Heather S |  |  |  | 9781 El Clair Ranch Road BOYNTON BEACH, FL 33437 |  | Valencia Lakes |  | Sun Valley |  | SE |  | NA
| Lauderdale One | Certified | GPON Bulk and Retail Swithces |  | 2015-01-15 | 1 | Demo | Not Applicable | Bob Smith |  |  |  | 2401 E 65th Street Fort Lauderdale, FL 33308 |  | Laudedale One |  |  |  | SE |  | NA
| Millecento, 1100 | Certified |  |  | 2015-01-29 | 382 | Fision Home | Received | [6 empty] | 951-Media R- 7606-S - 10.63.255.33 |  | Millecento, |  | ZTE |  | F668
| Epic West Residences | Certified |  |  | 2015-02-15 | 342 | Fision Home | Received | Wayde Webber |  | Edward/Jose |  | 270 Biscayne Boulevard Way, Miami, FL 33131 | Upgrade | MET1 |  | Epic West |  | ZTE |  | F668
| 1 Hotel (aka Perry) | Certified |  |  | 2015-02-20 | 165 | Fision Home | Received | Diamond William |  | Edward/Jose |  | 2399 Collins Ave, Miami Beach, FL 33139 | New Construction | One Hotel - ASR9006 |  | One Hotel | No | ALU
| Beach Club | Certified |  |  | 2015-03-01 | 386 | Fision Home | Received |  |  |  |  | 111 Surf Road Hallandale, FL |  | Trump Hollywood -7606S - 10.63.255.47 |  | Beach Club |  | ZTE |  | F668
| Beach Walk | Certified |  |  | 2015-03-01 | 432 | Fision Stay | Received | Christian Galante |  |  |  | 2600 E. Hallandale Beach Blvd. Hallandale Beach, FL 33009 |  | BeachWalk - ASR9006 - 10.63.255.52 |  | Beach Walk |  | ALU
| Icon Brickell 1& 2 | Certified |  |  | 2015-03-08 | 1273 | Fision Home | Received |  |  |  |  | 465, 475, 485 Brickell Ave Miami, FL 33131 |  |  |  | Icon Tower |  | ALU |  | I-241G-B
| Beach Walk | Certified |  |  | 2015-03-15 | 84 | Fision Home | Received |  |  |  |  | 2600 E. Hallandale Beach Blvd. Hallandale Beach, FL 33009 |  | BeachWalk - ASR9006 - 10.63.255.52 |  | Beach Walk |  | ALU
| Fountains At Champions Gate | Certified |  |  | 2015-03-31 | 80 | Fision Home | Received |  |  |  |  | 8101 Roseville Boulevard Davenport, Davenport, FL 33896 |  | Fountains At Champions Gate - ASR9006 - 10.86.255.1 |  | Fountains At Champions Gate |  | ALU
| Martinique Club in Naples | Certified |  |  | 2015-05-01 | 36 | Fision Home | Received | Pete Ferreira |  |  |  | 3003 Gulf Shore Blvd. N., Naples, FL 34 I 03 | [5 empty] | ALU
| Trump Towers 1 | Certified |  |  | 2015-05-06 | 271 | Fision Home | Received | Diamond William |  |  |  | 16001 Collins Avenue Miami, FL 33160 | Upgrade |  |  |  |  | SE
| Baltus House | Certified |  |  | 2015-05-13 | 167 | Fision Home | Received | Michael Stegman |  | Carl/Jose |  | 3925 N Miami Ave Miami, FL 33127 | New Construction | Onyx -7606S - 10.63.255.15 |  | Baltus House | No | ZTE |  | F668
| Gibraltar | Certified | GPON housed in Gibraltar |  | 2015-05-13 | 121 | Fision Home | Received | Bob Smith |  |  |  | 3711 SW 27th Street Miami, FL 33134 |  | PDP - 7606S - 10.63.255.23 |  | Gibraltar |  | ZTE |  | F668
| Mint, The | Certified |  |  | 2015-06-03 | 536 | Fision Home | Received |  |  |  |  | 92 W 3rd Street Miami, FL 33131 | [5 empty] | ZTE |  | 0-221-H-P (Outdoor)
| Boca Delray | Certified |  |  | 2015-06-06 | 437 | Fision Home | Received |  |  |  |  | 5483 Boca Delray Blvd. Delray Beach, FL 33484 |  | Boca Delray -7606S - 10.57.89.129 |  | Boca Delray |  | ZTE |  | F668
| Ibis Cove | Certified |  |  | 2015-06-11 | 416 | Fision Home | Received | Pete Ferreira |  |  |  | 8120 Logan Way Naples, Florida 34119 |  | Olde Cypress - ASR9006 - 10.84.255.4 |  | ALU |  | ALU
| Icon Bay | Certified |  |  | 2015-06-15 | 299 | Fision Home | Received |  |  |  |  | 460 NE 28th St, Miami, Fl. 33137 |  | Onyx -7606S - 10.63.255.15 |  |  |  | ZTE |  | F668
| La Perla | Certified |  |  | 2015-06-19 | 326 | Fision Home | Received | Diamond William |  | Edward/Jose |  | 16699 Collins Avenue Sunny Isles Beach, FL 33160 | Upgrade |  |  |  |  | ZTE
| Regalia | Certified |  |  | 2015-06-26 | 39 | Fision Home | Received | Wayde Webber | [5 empty] | WS-2960 |  |  |  | SE |  | NA
| Broken Sound | Certified |  |  | 2015-06-27 | 1618 | Fision Home | Received |  |  |  |  | 2701 NW 64 Blvd Boca Raton, FL 33496 |  | St Andrews |  | Broken Sound |  | ALU
| Apogee South Beach | Certified |  |  | 2015-06-30 | 67 | Fision Home | Received | Bob Smith |  | Edward/Jose |  | 800 S Pointe Drive Miami Beach, FL 33139 | Upgrade | Apogee - ASR9006 - 10.63.255.78 |  | Apogee South Beach | No | ZTE |  | F668
| Mirage Bay | Certified |  |  | 2015-07-06 | 137 | Fision Home | Received |  |  |  |  | 14401 Metro Parkway Fort Myers, FL 33912 | [5 empty] | ALU
| Boca Green | Certified |  |  | 2015-07-14 | 586 | Fision Home | Received |  |  |  |  | 10400 Kimberly Blvd. Boca Raton, FL 33498 |  | Boca Woods |  | Boca Green |  | ZTE |  | F668
| Marina Grande Riviera Beach | Certified |  |  | 2015-07-16 | 349 | Fision Home | Received | Victor Martinez |  | Edward/Jose | WPB | 245 E. Blue Hero Blvd. West Palm Beach, FL 33404 | Conversion/OverBuild | Marina Grande |  | Marina Grande | No | ZTE | 4 | F668 | No
| Berkley South | Certified |  |  | 2015-07-16 | 200 | Fision Home | Received |  |  |  |  | 3015 N. Ocean Blvd. Fort Lauderdale, FL |  | Berkley South - ASR9006 - 10.63.255. |  | Berkley South |  | ZTE |  | F668
| Puerta de Palmas | Certified |  |  | 2015-07-21 | 198 | Fision Home | Received |  |  |  |  | 888 S Douglas Road Miami, FL 33134 | [5 empty] | SE
| Newport Bay Club | Certified |  |  | 2015-07-30 | 225 | Fision Home | Received |  |  |  |  | 17251 Newport Club Drive Boca Raton, FL 33496 |  | Trump 1 |  |  |  | ZTE
| MET1 | Certified |  |  | 2015-08-01 | 447 | Fision Home | Received |  |  |  |  | 300 S. Biscayne Blvd. Miami, FL 33131 | Upgrade |  |  |  |  | SE
| Two City Plaza | Certified |  |  | 2015-08-03 | 460 | Fision Home | Received |  |  |  |  | 701 S. Olive Avenue West Palm Beach, FL 33401 | [5 empty] | ZTE
| Lakes of Sherbrooke | Certified |  |  | 2015-08-07 | 898 | Fision Home | Received |  |  |  |  | 8130 Havasu Court Lake Worth, FL 33467 | Upgrade |  |  |  |  | ALU
| Marquis | Certified |  |  | 2015-08-11 | 1 | Demo | Not Applicable | David Ramos |  |  |  | 1100 Biscayne Blvd. Miami, FL 33131 | [5 empty] | SE |  | NA
| Ocean 4 | Certified |  |  | 2015-08-27 | 281 | Fision Home | Received | Joia Bjorklund |  |  |  | 17201 Collins Avenue Sunny Isles Beach, FL 33160 | [5 empty] | ZTE
| Faena House | Certified |  |  | 2015-09-01 | 49 | Fision Home | Received | Mike Stegman |  | Edward/Jose |  | 3201 Collins Ave, Miami Beach, FL 33140 | New Construction | Faena Residence |  | Faena |  | ALU |  | I-241G-B
| Uptown Marina Loft | Certified |  |  | 2015-09-01 | 216 | Fision Home | Received | Bob Smith |  |  |  | 3029 NE 188TH Street Aventura, FL 33180 | Upgrade |  |  |  |  | ZTE
| Plaza on Brickell | Certified |  |  | 2015-09-09 |  | Fision Home | Received |  |  |  |  | 901 Brickell Avenue Miami, FL 33131 | [5 empty] | ZTE
| Harbour House | Certified |  |  | 2015-09-16 | 476 | Fision Home | Received |  |  |  |  | 10275 Collins Avenue Bal Harbour, FL 33154 | Upgrade | St Regis - ASR9006 - 10.63.255.57 |  | Harbour House |  | ZTE |  | F668
| Beach House 8 | Certified | Shared with Feana ALU Chassis |  | 2015-09-23 | 8 | Fision Home | Received |  |  |  |  | 3651 Collins Ave. Miami Beach, FL 33140 |  | Faena Residence |  | Faena |  | ALU
| St Regis Bal Harbour | Certified |  |  | 2015-10-01 | 282 | Fision Home | Received | Bob Smith |  |  |  | 9703 Collins Avenue Miami, FL 33154 | [5 empty] | ZTE
| Grovenor House | Certified | Temporarily located in Gibraltar MDF |  | 2015-10-02 | 166 | Fision Home | Received |  |  |  |  | 2627 S Bayshore Drive Miami, FL 33133 |  | Gables Marquis - 7606S- 10.63.255.30 |  | Grovenor House |  | ZTE |  | F668
| Carillon Hotel and Spa | Certified |  |  | 2015-10-06 | 150 | Fision Stay | Received | Christian Galante |  |  |  | 6801 Collins Avenue, Miami Beach, FL 33141 |  | Carillon Hotel - ASR9006 - 10.63.255.35 |  | NA |  | SE |  | NA
| Carillon Miami Beach - Central | Certified |  |  | 2015-10-06 | 231 | Fision Home | Received |  |  |  |  | 6801 Collins Avenue, Miami Beach, FL 33141 |  | Carillon Res - ASR9006 - 10.63.255.79 |  | NA |  | SE |  | NA
| Carillon Miami Beach - North | Certified |  |  | 2015-10-06 | 207 | Fision Home | Received |  |  |  |  | 6801 Collins Avenue, Miami Beach, FL 33141 |  | Carillon Res - ASR9006 - 10.63.255.79 |  | NA |  | SE |  | NA
| Carillon Miami Beach - South | Certified |  |  | 2015-10-06 | 143 | Fision Home | Received |  |  |  |  | 6801 Collins Avenue, Miami Beach, FL 33141 |  | Carillon Res - ASR9006 - 10.63.255.79 |  | NA |  | SE |  | NA
| Brentwood Estates | Certified |  |  | 2015-10-08 | 201 | Fision Home | Received |  |  |  |  | 8750 Mori Blvd, 33434 |  | Boca Woods |  | Brentwood Estates |  | ZTE |  | F668
| Quantum on the Bay [North+South Towers] | Certified |  |  | 2015-10-19 | 698 | Fision Home | Received | Bob Smith |  | Edward |  | 1900 North Bayshore Drive Miami, FL 33132 | Upgrade | Quantum ASR |  | NA | No | SE |  | NA
| Town at Pembroke Pines | Certified |  |  | 2015-10-20 | 364 | Fision Home | Received | Mike Perdomo |  |  |  | 10700 City Center Blvd, Pembroke Pines, Florida 33025 | [5 empty] | ZTE
| Bella Vista Phase 1 | Certified |  |  | 2015-10-22 | 224 | Fision Home | Received | Donald Rahmer |  |  |  | 3559 NW 29th Court Fort Lauderdale, FL 33311 | New Construction | Bella Vista |  | Bella Vista | Yes | ZTE |  | F668
| Pines of Oakland Forest West | Certified |  |  | 2015-10-22 | 206 | Fision Home | Received |  |  |  |  | 3082 S Oakland Forest Dr, Oakland Park, FL 33309 |  | Bella Vista |  |  |  | ZTE |  | F668
| Punta Rassa | Certified |  |  | 2015-11-08 | 194 | Fision Home | Received | Pete Ferreira |  |  |  | 15008 Punta Rassa Road, Fort Myers, Florida 33908 | [5 empty] | ALU
| Artech | Certified | Shared with Uptown Marina Loft ZTE Chassis |  | 2015-11-09 | 232 | Fision Home | Received | Bob Smith |  | Edward/Dario |  | 2950 E 188th Street Miami, FL 33180 | Conversion/OverBuild | Uptown - ASR9006 |  | Uptown Marina Loft | No | ZTE |  | F668
| Glass | Certified |  |  | 2015-11-09 |  | Fision Home | Received |  |  |  |  | 120 Ocean Drive Miami Beach, FL |  | Apogee - ASR9006 - 10.63.255.78 |  | Apogee South Beach |  | ZTE |  | F668
| Marea | Certified |  |  | 2015-11-09 | 30 | Fision Home | Received |  |  |  |  | 801 South Pointe Dr. Miami Beach, FL 33139 | [5 empty] | ZTE
| Mile, The | Certified | GPON housed in Gibraltar |  | 2015-11-09 | 119 | Fision Home | Received |  |  |  |  | 3622 SW 22nd St Miami, FL 33145 |  | PDP - 7606S - 10.63.255.23 |  | Gibraltar |  | ZTE |  | F668
| One Ocean | Certified |  |  | 2015-11-09 | 50 | Fision Home | Received |  |  |  |  | 1 Collins Ave. Miami Beach, FL 33139 | New Construction |  |  |  |  | ZTE
| Turnberry Ocean Colony | Certified |  |  | 2015-11-09 | 260 | Fision Home | Received | Joia Bjorklund |  |  |  | 16051 Collins Avenue Miami, FL 33160 | [5 empty] | ZTE
| 200 East | Certified |  |  | 2015-11-12 | 115 | Fision Home | Received | Victor Martinez |  | Edward |  | 200 East Palmetto Park Boca Raton, FL 33432 | Upgrade | 200 East - ASR9006 |  | 200 East | No | SE |  | NA
| Trump Towers 2 | Certified |  |  | 2015-11-20 | 271 | Fision Home | Received | Joia Bjorklund |  |  |  | 15901 Collins Avenue Miami, FL 33160 | Upgrade |  |  |  |  | ZTE
| Trump Towers 3 | Certified |  |  | 2015-11-20 | 271 | Fision Home | Received | Joia Bjorklund |  |  |  | 15811 Collins Avenue Miami, FL 33160 | Upgrade |  |  |  |  | ZTE
| Vanderbilt Community | Certified |  |  | 2015-11-23 | 800 | Fision Home | Received | Pete Ferreira |  |  |  | 8250 Danbury Blvd., Naples, Florida 34120 | [5 empty] | ALU
| Modern Doral | Certified |  |  | 2015-12-15 | 319 | Fision Home | Received | Mike Perdomo |  |  |  | 14751 Hammocks Blvd, Miami, FL 33166 | [5 empty] | ZTE
| Marina Palms [North& South Tower] | Certified |  |  | 2015-12-16 | 468 | Fision Home | Received | Roger Bartlett |  | Edward/Jose |  | 7111, 17211, 17301 Biscayne Blvd., North Miami Beach, FL 33160 | [5 empty] | ZTE
| City Palms | Certified |  |  | 2015-12-22 | 288 | Fision Home | Received |  |  |  |  | 480 Hibiscus Street West Palm Beach, FL 33401 |  | Whitney - ASR9K - 10.63.0.198 |  | City Palms |  | ZTE |  | F668
| Grove Station Tower | Certified | GPON housed in Gibraltar |  | 2016-01-06 | 184 | Fision Home | Received |  |  |  |  | 2700 SW 27th Avenue, Miami, FL | Conversion/OverBuild | PDP - 7606S - 10.63.255.23 | ME-3412 | Gibraltar |  | ZTE |  | F668 | No
| Downtown Doral - 5252 Paseo - (Phase I/South Tower) | Certified |  |  | 2016-01-07 | 203 | Fision Home | Received | John Cleary |  |  | MIAMI | 5252 NW 85 Ave, Doral, FL 33166 | New Construction | Downtown Doral Residence |  | Downtown Doral | Yes | ZTE |  | F668
| Downtown Doral - 5300 Paseo - (Phase II) | Certified |  |  | 2016-01-07 | 219 | Fision Home | Received | John Cleary |  |  | MIAMI | 5300 NW 85 Ave, Doral, FL 33166 | New Construction | Downtown Doral Residence |  | Downtown Doral | No | ZTE |  | F668
| Commodore Club 1 | Certified |  |  | 2016-01-08 | 47 | Fision Home | Received | Pete Ferreira |  |  |  | 2675 South Horseshoe Drive, Naples, FL 34104 | New Construction |  |  |  |  | ALU
| Quail Creek Estates | Certified |  |  | 2016-01-08 | 291 | Fision Home | Received | Pete Ferreira |  |  |  | 4866 Pond Apple Drive Naples, FL 34119 |  | Olde Cypress - ASR9006 - 10.84.255.4 |  |  |  | ALU |  |  | Yes
| Tiara Condominium | Certified |  |  | 2016-01-12 | 320 | Fision Home | Received | Dave Benitez |  |  |  | 3000 N. Ocean Drive Singer Island, FL |  | Marina Grande |  |  |  | ALU
| VUE [GPON] | Not Approved | Shared with Berkely South ZTE Chassis |  | 2016-01-15 | 157 | Fision Home | Received | Bob Smith |  |  |  | 2001 N Ocean Blvd. Fort Lauderdale, FL 33305 |  | Berkely South |  |  |  | ZTE |  | F668
| Modern Miami | Certified |  |  | 2016-01-15 | 166 | Fision Home | Not Applicable | Mike Perdomo |  |  |  | 1444 NW 14th Avenue Miami, FL 33126 | [5 empty] | SE
| Sinai Residences | Certified |  |  | 2016-01-18 | 369 | Fision Home | Received |  |  |  |  | 21090 Saint Andrews Blvd. Boca Raton, FL 33433 | New Construction | Sinai Residences |  |  |  | ALU
| Rose Garden at Fort Myers | Certified |  |  | 2016-01-26 | 114 | Fision Home | Received | Pete Ferreira |  |  |  | 2117 Earl Road Fort Myers, FL 33901 |  | Synergy nd Oasis |  | NA |  | SE |  | NA
| Crimson, The | Certified |  |  | 2016-02-04 | 90 | Fision Home | Received | Roger Bartlett |  | Edward/Jose |  | 601 NE 27th Street Miami, FL 33137 | New Construction | Onyx -7606S - 10.63.255.15 |  | Crimson |  | ALU
| Valencia Pointe | Certified |  |  | 2016-02-09 | 690 | Fision Home | Received | Victor Martinez |  |  |  | 6395 Castle Gate Blvd. Boynton Beach |  | Valencia Lakes |  | Valencia Pointe |  | ALU
| Commodore Club 2 | Certified |  |  | 2016-02-15 | 36 | Fision Home | Received | Pete Ferreira |  |  |  | 222 Harbour Drive Naples, FL 34103 | Conversion/OverBuild |  |  |  |  | ALU
| Mission Bay | Certified |  |  | 2016-02-18 | 1239 | Fision Home | Received |  |  |  |  | 10555 Diego Drive South Boca Raton, FL 33428 |  | Boca Woods |  | Mission Bay |  | ZTE |  | F668
| Ocean Reserve | Certified |  |  | 2016-02-18 | 405 | Fision Home | Received | Bob Smith |  |  |  | 19370 Collins Avenue Sunny Isles Beach, FL 33160 |  | Acqualina ASR9006 - 10.63.255.65 |  | Ocean Reserve |  | ZTE |  | F668
| Sabal Shores | Certified |  |  | 2016-02-18 | 125 | Fision Home | Received | Kenton Daley |  |  |  | 600 South Ocean Boulevard |  | BY&RC / BY&RC |  |  |  | ZTE |  | F668
| Valletta at Boca Raton | Certified |  |  | 2016-02-19 | 76 | Fision Home | Received | Donald Rahmer |  |  |  | Yamato Rd & NW 2nd Ave |  | BY&RC / BY&RC |  |  |  | ZTE |  | F668
| Neo Vertika | Certified | Chassis Housed at Neo Vertika |  | 2016-02-22 | 443 | Fision Home | Received |  |  |  |  | 690 SW 1 Court Miami, FL 33130 |  | Neo Vertika - 10.63.255.66 |  | Neo Vertika |  | ALU
| 1 Hotel (aka Perry) | Certified |  |  | 2016-02-26 | 1 | Fision Stay | Received | Christian Galante |  | Edward |  | 2399 Collins Ave, Miami Beach, FL 33139 | New Construction | One Hotel - ASR9006 |  | One Hotel | No | ALU
| Villages of Emerald Bay, The | Certified |  |  | 2016-02-29 | 216 | Fision Home | Received | Pete Ferreira |  |  |  | 422 Emerald Bay Circle Naples, FL 34110 |  | Naples - ASR9006 - 10.84.255.8 |  | Villages of Emerald Bay |  | ALU
| 360 Condos | Certified |  |  | 2016-03-07 | 36 | Fision Home | Not Applicable | Joey Gonzalez |  | Edward |  | 360 Harbor Island Drive Miami Beach, FL 33141 | Upgrade | AT&T: 10G from miami.fl.rtr |  | NA | No | SE |  | NA
| Cassa Brickell | Certified | Chassis Housed at Neo Vertika |  | 2016-03-08 | 80 | Fision Home | Received |  |  |  |  | 201 SW 17th Road Miami, FL 33129 |  | Neo Vertika - 10.63.255.66 |  | Neo Vertika |  | ALU
| Ivy [GPON] | Not Approved | Changed to Switched Ethernet: Per Marty |  | 2016-03-10 | 504 | Fision Home | Received | Diamond William |  | Saji |  | 90 SW 3rd St. Miami, FL 33130 | Upgrade | The Wind - ASR9006 - 10.63.255.53 |  | Ivy |  | ZTE |  | F668
| Downtown Dadeland | Certified |  |  | 2016-03-14 | 416 | Fision Home | Received | Jorge Pelaez |  |  | MIAMI | 7270 SW 88 Street Miami, FL 33156 | Upgrade | D Dadeland - ASR9006 - 10.63.255.83 |  | Downtown Dadeland |  | ZTE |  | F668
| Marquis | Certified |  |  | 2016-03-16 | 320 | Fision Home | Received | Joia Bjorklund |  |  |  | 1100 Biscayne Blvd. Miami, FL 33131 |  | 900 Bisc |  | Marquis |  | ALU
| Metropolitan at Wilton Manors | Certified | Shared with Berkely South ZTE Chassis |  | 2016-03-16 | 179 | Fision Home | Received | Roger Bartlett |  |  |  | 1330 NE 24th Street, Wilton Manors |  | Berkley South ASR9006 - 10.63.255.55 |  | Berkley South |  | ZTE |  | F668
| Ocean Sounds | Not Approved |  |  | 2016-03-24 | 50 | Fision Home | Received | Victor Martinez |  |  |  | 1770 South Ocean Blvd Lauderdale by the Sea, FL |  | Berkley South ASR9006 - 10.63.255.55 |  | Berkley South |  | ZTE |  | F668
| Veranda at Plantation | Certified | Shared with Manor Plantation ZTE Chassis |  | 2016-03-24 | 201 | Fision Home | Received |  |  |  |  | 540 NW 84th Ave, Plantation |  | The Manor – 10.63.255.22 |  | Manor Plantation |  | ZTE |  | F668
| Vizcayne | Not Approved | Design changed to SE |  | 2016-03-29 | 849 | Fision Home | Received | Jorge Pelaez |  | Edward/Jose |  | 244 E Biscayne Blvd. Miami, FL 33132 |  | Vizcayne ASR9006 |  |  |  | ZTE |  | F668
| Tarpon Bay | Certified | Shared with Quail Creek ALU Chassis |  | 2016-03-31 | 352 | Fision Home | Received | Pete Ferreira |  |  |  | 2050 Castaways Court Naples, FL 34119 | Conversion/OverBuild | Quail Creek – ASR9006 – 10.84.255.13 |  | Quail Creek |  | ALU
| Brentwood Lakes | Certified | (10.11 - rm) HLD and Launch Summary sent in MR Cert email |  | 2016-04-01 | 198 | Fision Home | Not Applicable | Eddie Miranda |  | Keith Brown | NFL | 2425 N. Courtenay Pkwy, Suite 9, Merritt Island, Florida 32953 | Upgrade |  |  |  |  | ALU
| BCC - Reach, The | Certified |  |  | 2016-04-07 | 390 | Fision Home | Received |  |  |  |  | 68 SE 6th Street Miami, Florida 33131 |  | BCC East ASR9006 - 10.63.255.87 |  | Reach |  | ZTE |  | F668
| BCC -Rise, The | Certified |  |  | 2016-04-07 | 390 | Fision Home | Received |  |  |  |  | 88 S.W. 7th Street, Miami, Florida 33131 |  | BCC East ASR9006 - 10.63.255.87 |  | Reach |  | ZTE |  | F668 |  |  | MFBREAK-1457 (30007279001)
| Saturnia Lakes | Certified |  |  | 2016-04-20 | 580 | Fision Home | Received | Pete Ferreira |  |  |  | 1310 Saturnia Grande Drive, Naples, Florida 34119 |  | Quail Creek – ASR9006 – 10.84.255.13 |  | Quail Creek |  | ALU
| Regent, The | Certified |  |  | 2016-05-12 | 37 | Fision Home | Received | Pete Ferreira |  |  |  | 4101 Gulf Shores Blvd North Naples, Florida 34103 |  | Lausanne |  | Lausanne |  | ALU
| Bond, The | Certified |  |  | 2016-05-18 | 328 | Fision Home | Received |  |  |  |  | 1080 Brickell Ave Miami, FL |  | BCC East Tower |  | The Bond |  | ZTE |  | F668
| Casa Costa | Certified |  |  | 2016-05-20 | 406 | Fision Home | Received |  |  |  |  | 416 Federal Highway Boynton Beach, FL 33435 |  | Casa Costa - ASR9006 - 10.63.1.234 |  | Casa Costa |  | ZTE |  | F668
| Grove at Grand Bay | Certified |  |  | 2016-05-25 | 98 | Fision Home | Received |  |  |  |  | 2675 South Bayshore Drive, Miami, FL 33133 |  | Grove at Grand Bay - ASR9006 - 10.63.255. |  | Grove at Grand Bay |  | ZTE |  | F668
| Centro | Certified |  |  | 2016-06-10 | 352 | Fision Home | Received |  |  |  |  | 96 NE 2nd Avenue Miami, FL 33132 |  | MET 1 - 10.63.255.70 |  | Centro |  | ZTE |  | F668
| VUE [SE] | Certified |  |  | 2016-06-15 | 157 | Fision Home | Received | Bob Smith |  |  |  | 2001 N Ocean Blvd. Fort Lauderdale, FL 33305 |  | Berkley South |  | NA |  | SE |  | NA
| Harbour Lights | Certified | Shared with Lausanne ALU Chassis |  | 2016-06-16 | 27 | Fision Home | Received | Pete Ferreira |  |  |  | 390 Harbour Drive, Naples, Florida 34103 | Conversion/OverBuild | Lausanne - ASR9006 - 10.84.255.5 |  | Lausanne |  | ALU
| Moorings Bay Apartments | Certified | Shared with Lausanne ALU Chassis |  | 2016-06-16 | 25 | Fision Home | Received | Pete Ferreira |  |  |  | 322 Harbour Drive. Naples, Florida 34103 |  | Lausanne - ASR9006 - 10.84.255.5 |  | Lausanne |  | ALU
| SLS Brickell Hotel | Certified |  |  | 2016-06-24 | 1 | Fision Stay | Received | Christian Galante |  |  |  | 1300 South Miami Ave Miami, FL 33130 | New Construction | 951 |  | NA |  | SE |  | NA
| Crystal Riviyera Apartments | Certified |  |  | 2016-06-27 | 117 | Fision Home | Received | Donald Rahmer |  | Saji/Dario |  | 3801 Crystal Lake Drive Deerfield Beach, FL 33064 | New Construction | NI: Host.net & StoneBridge |  | Crystal Riviyera | No | ZTE |  | F668 | No
| Lat On the River | Certified | Chassis Housed at Neo Vertika |  | 2016-06-30 | 454 | Fision Home | Received | Jorge Pelaez |  |  |  | 185 SW 7 Street Miami, FL 33130 |  | Neo Vertika - 10.63.255.66 |  | Lat On the River | Yes | ZTE |  | F668
| Vizcaya Lakes | Certified |  |  | 2016-06-30 | 330 | Fision Home | Received | Ben Kester |  |  |  | 280 Park Terrace Boynton Beach, FL 33426 | Upgrade | Vizcaya Lakes - ASR9006 - 10.63.255.91 |  | Vizcaya Lakes |  | ZTE |  | F668
| Ivy [SE] | Certified |  |  | 2016-07-01 | 504 | Fision Home | Received | Diamond William |  | Saji |  | 90 SW 3rd St. Miami, FL 33130 | Upgrade | Wind |  | NA |  | SE |  | NA
| Sanibel Harbour Tower North | Certified | Shared with Punta Rassa ALU Chassis |  | 2016-07-15 | 81 | Fision Home | Received | Pete Ferreira |  |  |  | 17080 Harbour Pointe Drive, Fort Meyers, FL 339089 |  | Punta Rassa ASR 10.84.255.10 |  |  |  | ALU
| Spindrift Club | Certified | Shared with Lausanne ALU Chassis |  | 2016-07-15 | 1400 | Fision Home | In Sales Phase |  |  |  |  | Biscayne Blvd. & NE 14th Street |  | Lausanne |  | Lausanne |  | ALU
| St James Golf Club | Certified |  |  | 2016-07-15 | 693 | Fision Home | Received | Dominick Foti |  |  |  | 5601 NW St. James Blvd. Port Saint Lucie, FL 34983 |  | St James - ASR9006 - |  | St James |  | ZTE |  | F668
| Windemere [Naples] | Certified | Shared with Lausanne ALU Chassis |  | 2016-07-15 | 29 | Fision Home | Received | Pete Ferreira |  |  |  | 2650 Gulf Shores Bh·d .. North, Naples, Florida 34103 |  | Lausanne - ASR9006 - 10.84.255.5 |  | Lausanne |  | ALU
| Deauville of Naples | Certified | Shared with Amelia Lakes ALU Chassis |  | 2016-07-22 | 240 | Fision Home | Received | Pete Ferreira |  | Carl/Jose |  | 5700 Deauville Circle Naples FL 34112 | Conversion/OverBuild | Deauville - ASR9006 - 10.84.255.14 |  | Deauville |  | ZTE |  | F668
| Shores at Berkshire Lakes, The | Certified |  |  | 2016-07-22 | 517 | Fision Home | Received | Pete Ferreira |  |  |  | 7845 Berkshire Pines Drive Naples, FL 34104 |  | Deauville - ASR9006 - 10.84.255.14 |  | Deauville |  | ALU
| Spindrift Club of Naples | Certified |  |  | 2016-08-01 | 33 | Fision Home | Received | Pete Ferreira |  |  |  | 2600 Gulf Shore Blvd. Naples, FL 34103 |  | Lausanne |  |  |  | ALU
| Vizcayne | Certified | Changed to Switched Ethernet: Per Marty |  | 2016-08-01 | 849 | Fision Home | Received | Jorge Pelaez |  | Edward |  | 244 E Biscayne Blvd. Miami, FL 33132 |  | Vizcayne - ASR9010 |  |  |  | SE |  | NA
| Amelia Lake | Certified |  |  | 2016-08-10 | 104 | Fision Home | Received | Pete Ferreira |  | Carl/Jose |  | 2300 Bayou Lane, Naples, FL 34112 | Conversion/OverBuild | Deauville - ASR9006 |  | Magnolia Cove ZTE | Yes | ZTE |  | F668
| Magnolia Cove | Certified |  |  | 2016-08-10 | 26 | Fision Home | Received | Pete Ferreira |  |  |  | 9150 Galleria Court, Ste. 201, Naples, FL 34109 |  | Deauville - ASR9006 - 10.84.255.14 |  |  |  | ZTE |  | F668
| Neo Vita Doral | Certified |  |  | 2016-08-10 | 80 | Fision Home | Received |  |  |  |  | NW 68th St & NW 71st St(on nw 104 Ave. ) |  | Modern Doral - 10.63.255.60 |  | Modern Doral |  | ZTE |  | F668
| Neo Vita South | Certified |  |  | 2016-08-10 | 142 | Fision Home | Received |  |  |  |  | NW 68th Street & NW 71st St (on NW 104 Ave.) Doral, FL |  | Modern Doral - 10.63.255.60 |  | Modern Doral |  | ZTE |  | F668
| 500 Brickell [2 Towers] 316/320 EW | Certified |  |  | 2016-08-12 | 636 | Fision Home | Received | Bob Smith |  | Edward/Jose |  | West Tower:55 SE 6th Street Miami, FL 33131 AND East Tower 500 Brickell Ave, Miami, 33131 | Upgrade | Icon Brickell - ASR9006 - 10.63.255.39 |  | 500 Brickell | Yes | ZTE |  | F668
| Loft Downtown II | Certified |  |  | 2016-08-15 | 501 | Fision Home | Received | Jorge Pelaez |  |  | MIAMI | 133 NE 2nd Avenue Miami, FL 33132 |  | Vizcayne |  | Loft Downtown II |  | ZTE |  | F668
| 1215 West Ave | Certified | Housed in Apogee South Beach MDF ¦ Back-Up : Air Fiber [P2P] |  | 2016-08-15 | 45 | Fision Stay | Received | Juan Miranda |  | Edward/Jose |  | 1215 West Avenue Miami Beach, FL 33139 | New Construction | Apogee - ASR9006 |  | 1215 West Ave | No | ALU
| Excelsior Condominium | Certified |  |  | 2016-08-16 | 28 | Fision Home | Received | Kenton Daley |  |  |  | 400 S. Ocean Blvd. Boca Raton, FL 33432 |  | BY&RC / BY&RC |  | BY&RC / BY&RC |  | ZTE |  | F668
| Le Parc at Brickell | Certified | Chassis Housed at Neo Vertika |  | 2016-08-22 | 128 | Fision Home | Received | Mike Perdomo |  |  |  | 1600 SW 1 Avenue Miami, FL 33129 | New Construction | Neo Vertika - 10.63.255.66 |  | Lat On the River |  | ZTE |  | F668
| Four Seasons Surf Club | Certified |  |  | 2016-08-26 | 1 | Fision Stay | Received | Christian Galante | [5 empty] | Four Seasons Surf Club |  | NA |  | SE
| SLS Brickell Residence | Certified |  |  | 2016-08-29 | 453 | Fision Home | Received |  |  |  |  | 1300 South Miami Ave Miami, FL 33130 | New Construction | SLS Brickell Hotel |  | SLS Brickell |  | ZTE |  | F668
| Midtown Miami 4 | Certified |  |  | 2016-08-30 | 372 | Fision Home | Received | Joia Bjorklund |  |  |  | 3301 E 1st Avenue Miami, FL 33137 |  | One Hotel & Midtown2 7606-S |  |  |  | SE |  | NA
| Newport Beachside Hotel | Certified |  |  | 2016-08-31 | 1 | Demo | Not Applicable | [6 empty] | Trump Hollywood |  |  |  | SE |  | NA
| Enclave of Naples | Certified | Shared with Park Shore Tower ALU Chassis |  | 2016-09-01 | 28 | Fision Home | Received | Pete Ferreira |  | Carl/Jose |  | 4601 Gulf Shore Blvd Naples, FL 34103 | Conversion/OverBuild | Lausanne - ASR9006 - 10.84.255.5 |  | Park Shore | Yes | ALU |  | I-241G-B
| Lucerne | Certified | Shared with Park Shore Tower ALU Chassis |  | 2016-09-01 | 24 | Fision Home | Received | Pete Ferreira |  |  |  | 3100 Gulf Shore Blvd. N. Naples, FL 34103 |  | Lausanne - ASR9006 - 10.84.255.5 |  | Park Shore |  | ALU
| Park Shore Towers | Certified |  |  | 2016-09-01 | 75 | Fision Home | Received | Pete Ferreira |  |  |  | 4251 Gulf Shore Blvd. Naples, FL 34103 |  | Lausanne - ASR9006 - 10.84.255.5 |  | Park Shore |  | ZTE |  | F668
| Via Mizner, Phase I | Certified |  |  | 2016-09-05 | 366 | Fision Home | Received |  |  |  |  | 101 East Camino Real Boca Raton, Florida 33432 |  | 200 East - ASR9006 - 10.63.255.51 |  | Via Mizner |  | ZTE |  | F668
| Collier’s Reserve | Certified | Housed in Naples Office |  | 2016-09-10 | 224 | Fision Home | Received | Pete Ferreira |  |  |  | 11711 Collier's Reserve Drive | Conversion/OverBuild | Naples - ASR9006 - 10.84.255.8 |  | Villages of Emerald Bay |  | ALU
| Boca Falls | Certified |  |  | 2016-09-14 | 722 | Fision Home | Received |  |  |  |  | 21700 Boca Falls Drive Boca Raton, FL 33428 |  | Boca Woods - ASR9006 - 10.63.255.37 |  | Boca Falls |  | ALU |  | I-241G-B
| Sonoma Bay | Certified | Pending Fiber. ETC next Tuesday |  | 2016-09-17 | 303 | Fision Home | Received | Kenton Daley |  | Saji/Dario |  | 3600 Sonoma Drive West Palm Beach, FL 33404 |  | Sonoma Bay - ASR9006 - |  | Sonoma Bay |  | ZTE |  | F668
| Porshe Tower Design | Certified |  |  | 2016-09-19 | 132 | Fision Home | Received |  |  |  |  | 18555 Collins Avenue, Sunny Isles Beach |  | Porshe Tower Design |  | Porshe Tower Design |  | ALU
| Bay House | Certified |  |  | 2016-09-23 | 165 | Fision Home | Received |  |  |  |  | 600 NE 27th Street, Miami, FL 33137 |  | Onyx -7606S - 10.63.255.15 |  | Crimson |  | ALU
| St Andrews School | Certified |  |  | 2016-09-24 | 1 | Fision Home | Received | Nerupa Imam |  | Edward |  | 17557 Claridge Oval West Boca Raton, FL 33496 |  | St Andrews School - ASR9006 - 10.63.255.106 |  | NA |  | SE |  | NA
| Midtown Miami 2 | Certified |  |  | 2016-09-30 | 337 | Fision Home | Received | Jorge Pelaez |  |  |  | 3470 E Coast Avenue Miami, FL 33137 |  | Trump1 & Onyx |  | NA |  | SE |  | NA
| Kai at Bay Harbor | Certified |  |  | 2016-10-01 | 58 | Fision Home | Received | Roger Bartlett |  |  |  | 9940 W. Bay Harbor Drive Bay Harbor Island, FL 33154 | New Construction | St Regis - ASR9006 - 10.63.255.57 |  | Kai at Bay Harbor | No | ZTE |  | F668 | No
| Brickell Ten | Certified | Chassis Housed at Neo Vertika |  | 2016-10-07 | 155 | Fision Home | Received |  |  |  |  | 1010 SW 2nd Avenue Miami, FL |  | Neo Vertika - 10.63.255.66 |  | Lat on the River |  | ZTE |  | F668
| Onyx on the Bay | Certified |  |  | 2016-10-07 | 121 | Fision Home | Received |  |  |  |  | 665 NE 25th Street Miami, FL 33137 |  | Onyx -7606S - 10.63.255.15 |  | Onyx on the Bay |  | ZTE |  | F668
| Opera Tower | Certified |  |  | 2016-10-07 | 641 | Fision Home | Received |  |  |  |  | 1750 N Bayshore Drive Miami, FL 33132 |  | Quantum on the Bay |  | Opera Tower |  | ZTE |  | F668
| Diplomat Residences | Certified |  |  | 2016-10-10 | 135 | Fision Home | Received | [6 empty] | Trump Hollywood |  | NA |  | SE |  | NA
| Mondrian Hotel | Certified |  |  | 2016-10-12 | 1 | Fision Stay | Received | Christian Galante | [5 empty] | Apogee - ASR9006 - 10.63.255.78 |  | NA
| Latitude Delray | Certified |  |  | 2016-10-13 | 42 | Fision Home | Received | Donald Rahmer |  |  |  | 213 South Latitude Circle |  | BY&RC |  | BY&RC / BY&RC |  | ZTE |  | F668
| Bay Breeze | Certified |  |  | 2016-10-15 | 17 | Fision Home | Received |  |  |  |  | 1120 98 Street Bay Harbor Islands, Florida 33154 |  | St Regis - ASR9006 - 10.63.255.57 |  | Kai at Bay Harbor |  | ZTE |  | F668
| Midblock East | Certified |  |  | 2016-10-15 | 158 | Fision Home | Received | Joia Bjorklund |  |  |  | 3110 E 2nd Avenue Miami, FL 33137 |  | Midtown2 |  | NA |  | SE |  | NA
| Emerald Isle at Laguna Lakes | Certified |  |  | 2016-10-17 | 355 | Fision Home | Received | Ben Kester |  | Saji/Dario |  | 4300 San Marino Blvd. West Palm Beach, FL 33409 | Upgrade | NI: Sonoma Bay & B.Wood |  | Emerald Isle at Laguna Lakes | No | ZTE | 3 | F668 | No
| Residences at Grove Station | Certified | GPON housed in Gibraltar |  | 2016-10-17 | 54 | Fision Home | Received |  |  |  |  | 2560 SW 27th Avenue Miami, FL 33133 | Conversion/OverBuild | Grove at Grand Bay | ME-3412 | Grove at Grand Bay |  | ZTE |  | F668
| Atton Hotel Miami | Certified | Minerva |  | 2016-10-21 | 275 | Fision Stay | Received | Juan Miranda |  | Edward/Jose |  | 1500 SW 1st Ave Miami, FL 33129 | New Construction | Icon Minerva 6509 RTR |  | NA | No | SE |  | NA
| Marsh Harbour | Certified |  |  | 2016-10-26 | 411 | Fision Home | Received | Kenton Daley |  |  |  | 1451 Congress Avenue Riviera Beach, FL 33404 |  | Sonoma Bay |  | Sonoma Bay |  | ZTE |  | F668
| Lauderdale by the Sea | Certified |  |  | 2016-10-30 | 50 | Fision Home | Received | [6 empty] | Ocean Sound |  | Ocean Sound |  | ZTE |  | F668
| Club at Brickell Bay | Certified |  |  | 2016-10-31 | 645 | Fision Home | Received |  |  |  |  | 1200 Brickell Bay Drive Miami, FL 33131 | Upgrade | CABB - ASR9010 - 10.63. |  | NA |  | SE |  | NA
| Ocean Sounds | Certified |  |  | 2016-10-31 | 50 | Fision Home | Received | Victor Martinez |  |  |  | 1770 South Ocean Blvd Lauderdale by the Sea, FL |  | 3rd Party [AT&T] - NAP - 10/20/2016 |  | Ocean Sound |  | ZTE |  | F668
| Harbour Ridge | Certified | 42705 |  | 2016-11-02 | 695 | Fision Home | Received |  |  |  |  | 12600 NW Harbour Ridge Blvd., Palm City, FL 34990 | Conversion/OverBuild | 10GB AT&T [10/27/2016] |  | Harbour Ridge |  | ZTE |  | F668
| Avalon Phase 2 [Veranda] | Certified | Addressed as an Add-On |  | 2016-11-06 | 276 | Fision Work | Received | Miguel Castillo |  | Lynn/Jose |  | 2820 OLD MILTON PKWY, Building 7000, Alpharetta, GA 30009 | New Construction | Avalon - ASR9006 - 10.110.255.26 |  | Avalon | Yes | ALU |  | I-241G-B
| Four Seasons at Parkland | Certified | 11/2/2016: Homes are still beign condtructed: 3-5 year poject. |  | 2016-11-15 | 538 | Fision Home | Received | Donald Rahmer |  | Edward/Jose |  | 15040 Loxahatchee Road, Parkland, Florida 33076 | New Construction | Boca Woods - ASR9006 - 10.63.255.37 |  | Four Seasons at Parkland | No | ZTE |  | F668
| Latitude One | Certified | Chassis Housed at Neo Vertika |  | 2016-11-15 | 220 | Fision Work | Received | Bob Smith |  |  |  |  | Upgrade | Neo Vertika - 10.63.255.66 |  | Neo Vertika |  | ALU
| City Place Doral [The Flats Luxury Apartments] | Certified |  |  | 2016-11-20 | 303 | Fision Home | Received | Mike Perdomo |  | Saji/Dario |  | 3555 - 3550 NW 83rd Avenue Doral, Florida 33122 | New Construction | Manor CityPlace Doral - 10.63.255.44 |  | Manor CityPlace Doral | No | ZTE |  | F668 | No
| Oceana Bal Harbour | Certified |  |  | 2016-11-21 | 240 | Fision Home | Received | Roger Bartlett |  |  |  | 10201 Collins Avenue, Bal Harbour, FL 33154 |  | St Regis - ASR9006 - 10.63.255.57 |  | Oceana Bal Harbour |  | ZTE |  | F668
| Yoo on the Park | Certified |  |  | 2016-11-21 | 245 | Fision Home | Received | Miguel Castillo |  |  |  | 207 13th Street, N.E. Atlanta, GA |  | Plaza Midtown |  | Yoo on the Park |  | ALU
| Europa By The Sea | Certified |  |  | 2016-11-28 | 50 | Fision Home | Received | Victor Martinez |  | Saji/Dario |  | 1460 S. Ocean Blvd, Lauderdale by the Sea, FL | Conversion/OverBuild | Ocean Sound |  | Ocean Sound | No | ZTE |  | F668
| Ivory Residences and Marina | Certified |  |  | 2016-12-01 | 41 | Fision Home | Received | Roger Bartlett |  | Edward/Jose |  | 9421-9461 East Bay Harbor Drive Bay Harbor Islands | New Construction | St Regis - ASR9006 - 10.63.255.57 |  | Kai at Bay Harbor | No | ZTE |  | F668
| Tao - Data Upgrade | Certified | 12 2Port PON Cards installed and Activated by JP |  | 2016-12-15 | 395 | Fision Home | Not Applicable | Wayne Leonard |  | Jose | BROW | 2681 N. Flamingo Road Sunrise, FL 33323 | Upgrade | Metropica |  | Tao | No | ALU
| Avalon of Naples - Phase One | Certified | Shared with Amelia Lakes ALU Chassis |  | 2016-12-20 | 24 | Fision Home | Received | Pete Ferreira |  | Carl/Jose |  | 6820 Davis Blvd, Naples, FL 34104 | Conversion/OverBuild | Deauville - ASR9006 - 10.84.255.14 |  | Amelia Cove | Yes | ZTE |  | F668
| Midtown Miami 5 | Certified |  |  | 2016-12-31 | 399 | Fision Home | Received | Roger Bartlett |  |  |  | 3201 NE 1st Ave, Miami, FL |  | Midtown 4 |  | Midtown 5 |  | ZTE |  | F668
| Tributary Phase 2 | Certified |  |  | 2017-01-01 | 50 | Fision Home | In Sales Phase | Miguel Castillo |  | Lynn |  | 3270 Darby Dr, Douglasville, GA 30135 |  |  |  | New Construction | Yes | ALU |  | I-221E-A
| Mystic Pointe Tower 1 | Certified |  |  | 2017-01-09 | 289 | Fision Home | Received |  |  |  |  | 19195 Mystic Pointe Dr., Aventura, FL 33180 |  | UML |  |  |  | ALU |  | F668
| 9900 Townhomes | Certified |  |  | 2017-01-20 | 6 | Fision Home | Received | Roger Bartlett |  | Edward/Dario |  | 9900 East Bay Harbor Drive | New Construction | St Regis - ASR9006 - 10.63.255.57 |  | St Regis | No | ZTE |  | F668
| Ritz Carlton; Removing Hotwire Middleware | Certified | Chassis Housed at Neo Vertika |  | 2017-01-23 | 1 | Fision Stay | Received | Juan Miranda |  |  |  |  | Hand-Off | Trump Hollywood |  | NA |  | SE |  | NA
| Isles at Wellington | Certified | Splits - to be upgraded by 50M every year - 2 Chassis |  | 2017-01-24 | 759 | Fision Home | Received | Ben Kester |  | Saji/Dario |  | 4325 Isles Vista Blvd., Wellington, FL 33449 | Conversion/OverBuild | Valencia Shores |  | Isles at Wellington | No | ALU |  | I-241G-B
| Brickell House | Certified |  |  | 2017-02-01 | 374 | Fision Home | Received |  |  |  |  | 1330 Brickell Bay Drive Miami FL, 33131 |  | 951 |  | Brickell House |  | ALU
| Country Greens at Westchester | Certified | House Valencia Pointe |  | 2017-02-01 | 150 | Fision Home | Received | Kenton Daley |  | Claudio/Dario |  | 12467 Country Greens Blvd. Boynton Beach, FL 33437 | Conversion/OverBuild | Valencia Lakes |  | Country Greens at Westchester |  | ALU |  | I-241G-B
| Sereno at Bay Harbor | Certified |  |  | 2017-02-01 | 40 | Fision Home | Received | Roger Bartlett |  |  |  | 10201 E Bay Harbor Drive, Bay Harbor, Florida 33154 | New Construction | St Regis - ASR9006 - 10.63.255.57 |  | St Regis | No | ZTE |  | F668
| Boca West | Certified | 6 ZTE Chassis |  | 2017-02-03 | 3431 | Fision Home | Received | Victor Martinez |  |  |  | 20540 Country Club Blvd. Boca Raton, FL 33434 |  | NI: St Andrews School and Woodfield |  | Boca West [5] |  | ZTE |  | F668
| Biscayne Beach Club Residences | Certified |  |  | 2017-02-06 | 399 | Fision Home | Received | John Cleary |  | Claudio/Dario |  | 701 NE 29th Street Miami, FL 33137 | New Construction | Quantum |  | Biscayne Beach Club | No | ZTE |  | F680
| Brickell Heights [East and West] | Certified | Pause until Contract deliverables submitted |  | 2017-02-06 | 690 | Fision Home | Received | John Cleary |  | Edward/Jose |  | 850 SOUTH MIAMI AVENUE Miami FL 33131 | New Construction | SLS Brickell |  | Brickell Heights | No | ZTE |  | F680
| Towers at Key Bizcayne | Certified |  |  | 2017-02-06 | 542 | Fision Home | Received | Luis Martell |  |  |  | 1121 Crandon Blvd, Key Biscayne, FL 33149 |  | Oceana Key Biscayne - ASR9006 – 10.63.255.45 |  | Towers at Key Bizcayne | No | ZTE |  | F680
| Reef, The | Certified |  |  | 2017-02-07 | 76 | Fision Home | Received | Kenton Daley |  |  |  | 2275 South Ocean Blvd. Palm Beach, FL 33480 |  | 2100 Condo |  | 2100 Condo |  | ALU
| Casa Del Mar | Certified | OSP being worked on. |  | 2017-02-10 | 72 | Fision Home | Received | Donald Rahmer |  | LF |  | 2632 N Federal Highway Boynton Beach, FL |  | Casa Costa - ASR9006 - 10.63.1.234 |  | Casa Costa |  | ZTE |  | F668
| Hyde Resort & Residences Hollywood / Hallandale | Certified |  |  | 2017-02-10 | 407 | Fision Stay | Received | Christian Galante |  | Edward/Saji |  | 4111 South Ocean Drive. Hollywood Beach, FL 33019 | New Construction | Trump Hollywood & Porsche |  | NA |  | SE |  | NA
| Hampton Beach Condo | Certified |  |  | 2017-02-15 | 176 | Fision Home | Received | Eric Swain |  | Saji/Dario |  | 1800 S Ocean Blvd Lauderdale By The Sea, FL 33062 | Conversion/OverBuild | Ocean Sound |  | Ocean Sound | No | ZTE |  | F668
| Metropica ASR Installation @ TAO | Certified |  |  | 2017-03-01 | 0 | Fision Work | Not Applicable | Juan Garcia |  | Saj/Dario | BROW | 1800 NW 136 Avenue Sunrise, FL 33323 | Upgrade |  |  |  |  | NA
| Turnberry Village North | Certified |  |  | 2017-03-06 | 191 | Fision Home | Received | Bob Smith |  |  |  | 20000 E Country Club Drive Miami, FL 33180 |  | Uptown - ASR9006 - |  |  |  | SE |  | NA
| Pelican Landing | Certified | Certifed ahead of schedule :) |  | 2017-03-07 | 3319 | Fision Home | Received | Pete Ferreira |  | Carl/Jose | SWFL | 24501 Walden Center Drive, Bonita Springs, Florida 34134 | Conversion/OverBuild | NI: Miraje Bay and Naples | ASR9010 | Pelican Landing | Yes | ALU | 28 | I-241G-B | Yes
| 2100 Condos | Certified |  |  | 2017-03-24 | 141 | Fision Home | Received | Kenton Daley |  | Claudio/Dario |  | 2100 S. Ocean Blvd. Palm Beach, FL 33480 | Conversion/OverBuild | FL-2100-CONDO-FLR01-MDF-RTR1 – 10.63.255.113 [10 to NOTA] |  | 2100 Condo | No | ALU |  | I-241G-B
| Hawk Landing | Certified |  |  | 2017-04-01 | 170 | Fision U | Received | Tony Robbins |  |  |  | 5262 Brown Rd. Oxford OH, 45056 |  | 10G Wavelenght to? |  |  |  | SE
| TAO [Migrate Existing Chassis to MR ONLY] | Certified |  |  | 2017-04-20 | 395 | Fision Home | Received | Wayne Leonard |  | Lik/Saji/Jose | BROW | 2681 N. Flamingo Road Sunrise, FL 33323 | Upgrade | Metropica ASR - Housed at TAO MDF |  | Tao | No | ALU |  | I-221E-A | NA
| Buttonwood West | Certified |  |  | 2017-04-28 | 223 | Fision Home | Received | Ben Kester |  | Saji/Dario |  | 3201 Silver Buttonwood Drive Greenacres City, FL 33463 | Upgrade | FL-BUTTONWOOD-FLR01-MDF-RTR01 – 10.63.255.116 |  | Buttonwood | Yes | ZTE |  | F668 | No
| Huntcrest | LOST | Pending Pre Budget |  | 2017-05-01 | 299 | Fision Home | Not Applicable | Miguel Castillo |  | Lynn |  |  |  | NA |  | NA |  |  |  | NA
| Coral Lago | Certified |  |  | 2017-05-01 | 186 | Fision Home | Received | Donald Rahmer |  | Lik/Jose |  | 3801 N University Drive | New Construction | Cypress MR East RTR |  | Coral Lago | No | ZTE |  | F680 | No
| Old Marsh Golf Club | Certified |  |  | 2017-05-12 | 166 | Fision Home | Received | Ben Kester |  | Lik/Jose |  | 7500 Old Marsh Rd, Palm Beach Gardens, FL 33418 | Conversion/OverBuild | Harbor Ridge : Off net |  | Old Marsh Golf Club | Yes | ZTE |  | F668
| Pelican Harbor | Certified | 4/17/2017: ASR and GPON Chassis is housed at BY&RC MDF. 4/14/2017 GPON Gear requested. 4/17/2017: ASR Requested. |  | 2017-05-12 | 195 | Fision Home | Received | Kenton Daley |  | LF/Dario |  | 475 Pelican Way, Delray Beach, FL 33483 | Conversion/OverBuild | BY&RC |  | Pelican Harbor [Housed in BY&RC] | Yes | ZTE |  | F668
| Ponce De Leon | Certified | OLT Ready for pick |  | 2017-05-15 | 50 | Fision Home | Received | Jorge Pelaez |  | Claudio/Dario |  | 1607 Ponce de Leon Blvd, Coral Gables, FL 33134 | Conversion/OverBuild | PDP - 7606S - 10.63.255.23 |  | Ponce De Leon | No | ZTE |  | F680
| Jackson Tower | Certified |  |  | 2017-05-19 | 125 | Fision Home | Received | Bob Smith |  | Saji/Dario |  | 100 South Birch Rd, Fort Lauderdale, FL 33316 | Conversion/OverBuild | Berkley South ASR9006 - 10.63.255.55 |  | Berkley South | No | ZTE |  | F668
| 26 Edgewater | Certified |  |  | 2017-06-01 | 86 | Fision Home | Received | Eric Hart |  | Pending |  | 321 NE 26th st, Miami, FL 33137 | New Construction | Onyx |  | Crimson | No | ALU |  | I-241G-B
| Stratford Arms Condominium | Certified | 4/24/2017: AT&T Circuit delivery date is 5/31/2017. MR Cert Window TBD. |  | 2017-06-01 | 120 | Fision Home | Received | Eric Swain |  | Saji/Dario |  | 2600 South Ocean Blvd Boca Raton, FL 33432 | Upgrade | Cypress MR East RTR - Off Net [5/31/2017] |  | Stratford Arms Condominium | No | ZTE |  | F680
| Versailles at Wellington | Certified |  |  | 2017-06-01 | 450 | Fision Home | Received | Ben Kester |  | Claudio/Jose |  | 10400 Versailles Blvd | Conversion/OverBuild | Isles of Wellington |  | Versailles at Wellington | Yes | ALU |  | I-241G-B | Yes
| Towne Club Windemere | Certified |  |  | 2017-06-13 | 142 | Fision Home | Received | Miguel Castillo |  |  |  | 3950 Towne Club Parkway Cumming, GA 30041 | [5 empty] | ALU
| Broward Office | Certified | Waiting on approval from the property to install the ASR |  | 2017-06-15 | 0 | Fision Work | Received | David Ramos |  |  |  |  | Hand-Off | NI: Bella Visat & Church |  |  |  | SE
| Eagle Creek | Certified |  |  | 2017-06-16 | 458 | Fision Home | Received | Pete Ferreira |  | Edward/Jose |  | 11 Cypress View Dr. Naples, Florida 34113 | Conversion/OverBuild | NI: Bellasera & Deauville of Naples | ASR920 | Eagle Creek | Yes | ALU |  | I-241G-B | Yes
| Midtown Apartments [Naples] | Certified | Router or Nexus and Chassis/ F680 - IN-UNIT ROUTER? HEATHER TO ADVISE. |  | 2017-06-20 | 90 | Fision Home | Received | Pete Ferreira |  | Carl/Jose |  | 2316 SW 17th Place Cape Coral, FL, 33991 | New Construction | 3rd Party Circuit - Cypress Office |  | Midtown Apartments [Naples] | No | ZTE |  | F680 | No
| Paraiso Bay | Certified |  |  | 2017-06-21 | 368 | Fision Home | Received | Roger Bartlett |  | Lik/Jose |  | 600 NE 31st St, Miami, FL 33137 | New Construction | Onyx -7606S - 10.63.255.15 |  | Paraiso Bay | No | ZTE |  | F680
| 2500 Biscayne | Certified | OSP: 2/1/2017 |  | 2017-06-22 | 156 | Fision Home | In Sales Phase | Roger Bartlett |  | LF/Jose |  | 2500 Biscayne Blvd, Miami, FL | New Construction | 2500 Biscayne |  | 2500 Biscayne | No | ZTE |  | F680
| Doral Landings West | LOST |  |  | 2017-07-01 | 242 | Fision Home | LOST |  |  |  |  | NW 51st Terr and NW 114th Ave | Conversion/OverBuild | ? |  | Doral Landings West |  | ALU |  | I-241G-B
| Everglades Club | Certified |  |  | 2017-07-01 | 44 | Fision Home | In Sales Phase | Bob Smith |  |  |  | 2300 NE 33rd Ave Fort Lauderdale, Florida 33305 | Conversion/OverBuild | Berkley? |  | ZTE | No | ZTE |  | F668 | No
| Park Central at Cypress Key | Certified |  |  | 2017-07-01 | 147 | Fision Home | Received | Donald Rahmer |  | Saji/Jose |  | Southern Blvd & Cypress Head Ave | New Construction | FL-PARK-CENTRAL-MDF-RTR01 [Via AT&T] 10.63.128.34 |  | Cypress Key at Park Central | No | ALU |  | I-241G-B | No
| Mosaic at the Forum | Certified |  |  | 2017-07-10 | 252 | Fision Home | Received | Pete Ferreira |  | Edward/Jose |  | 3100 Champion Ring Rd Ft. Myers, FL 33905, Florida 33905 | New Construction | Mosaic |  | Mosaic at the Forum | No | ZTE |  | F680 | No
| 3 ISLAND (Belle Isle) | Certified |  |  | 2017-07-11 | 144 | Fision Home | Received | Jorge Pelaez |  | Pending | MIAMI | 3 Island Ave, Miami Beach, FL 33139 | Conversion/OverBuild | One Hotel |  | Belle Isle | No | ZTE |  | F680
| Emilia Edgewater Condos | Certified | Pending OSP |  | 2017-07-21 | 30 | Fision Home | In Sales Phase | John Cleary |  | Lik/Jose | Mimai | 481 NE 29th ST Miami, Florida 33137 | New Construction | Icon |  | Emilia Edgewater Condos | Yes | ZTE |  | F668 | No
| Cascade Lakes | Certified | Pending permits for power, the NI needs to be cordinate. |  | 2017-07-27 | 600 | Fision Home | Received | Eric Swain |  | Pending |  | 5075 Cascade Lakes Blvd | New Construction | NI: Vizcaya Lakes and Valencia Lakes |  | Cascade Lakes | Yes | ZTE |  | F668 | Yes
| Icon Las Olas | Certified | Pendin Agreement |  | 2017-08-01 | 272 | Fision Home | Received | John Cleary |  | Saj | BROW | 500 East Las Olas Blvd, Ft. Lauderdale. | New Construction | The Church |  | Icon Las Olas | No | ZTE |  | F680 | No
| 1155-1165 101ST STREET | LOST |  |  | 2017-08-01 | 12 | Fision Home | LOST | Roger Bartlett |  | Pending |  | 1155-1165 101st Street Bay Harbor, Florida 33154 | New Construction | Pending |  | Kai at Bay Harbor |  | ZTE |  | F668
| Arive Housing 850 | Certified |  |  | 2017-08-01 | 35 | Fision U | Received | Eddie Miranda |  | Keith Brown |  | 1857 W Pensacola Street Tallahassee, FL 32304 |  | Stadium Center |  | Stadium Center | Yes |  |  |  | No
| Cloister Beach Towers | Certified |  |  | 2017-08-01 | 125 | Fision Home | Received | Bob Smith |  | Saji/Dario |  | 1200 S. Ocean Blvd Boca Raton, Florida 33432 | Conversion/OverBuild | FL-STRATFORD-FLR01-MDF-RTR01 – 10.63.255.118 |  | Stratford Arms | No | ZTE |  | F680 | No
| Prive at Island Estates | Certified |  |  | 2017-08-07 | 174 | Fision Home | In Sales Phase | John Cleary |  | Pending |  | 5000 Island Estates Dr, Aventura, FL 33160 | New Construction | PEN2 and Marina Palms - New Fiber |  | Prive at Island Estates | No | ZTE |  | F680
| Lake Washington | Certified |  |  | 2017-08-14 | 288 | Fision Home | Received | Eddie Miranda |  | Keith Brown |  | 2727 Revolution Street Melbourne, FL 32935 | Upgrade | 3rd Party Circuit [Cypress] |  | Lake Washington | Yes | ALU |  | I-241G-B | Yes
| Marina Palms Boat Slips | Certified |  |  | 2017-08-15 | 112 | Fision Work | Received | Roger Bartlett |  | Lik/John/Dale |  | 7111, 17211, 17301 Biscayne Blvd., North Miami Beach, FL 33160 |  | Marian Palms |  | Marina Palms |  | SE |  | NA
| Bella Vista Phase 2 | Certified | Construction On Hold until homes are SOLD |  | 2017-08-31 | 124 | Fision Home | Not Applicable | Donald Rahmer |  |  |  | 3559 NW 29th Court Fort Lauderdale, FL 33311 | New Construction | Bella Vista |  | Bella Vista | Yes | ZTE |  | F668
| Boca Lakes Estate | Certified |  |  | 2017-09-09 | 93 | Fision Home | Not Applicable |  |  | Lik/Rolando | WPB | 7070 N.W. 2nd Avenue, Boca Raton, Florida 33487 | Conversion/OverBuild | BY&RC |  | Pelican Harbor [Housed in BY&RC] | Yes | ZTE |  | F668
| Park Grove (Tower 1, 2 & 3) | Certified |  |  | 2017-09-26 | 298 | Fision Home | In Sales Phase | John Cleary |  |  | MIAMI | 2701 S Bayshore Dr, Miami, FL 33133 | New Construction | Grove at Grand Bay - ASR9006 - 10.63.255. | ASR920 | Park Grove - check G@GB CHASSIS | No | ZTE | 3 | F668 | No | Y
| Ocean Walk | LOST |  |  | 2017-10-01 | 538 | Fision Home | LOST |  |  |  |  | Sea Hourse Lane
| Villas of Park Shore | Certified |  |  | 2017-10-06 | 43 | Fision Home | Received | Pete Ferreira |  | Edward/Jose | SWFL | 4056 Crayton Road Naples, FL 34103 | Conversion/OverBuild | Park Shore |  | Park Shore | Yes | ZTE |  | F668 | Yes
| All Seasons of Naples | Certified | Keith to finilize the Wifi design. He Build Out Delayed |  | 2017-10-07 | 187 | Fision Encore | Received | Pete Ferreira |  | Edward/Jose | SWFL | 15450 Tamiami Trail, Naples FL 34110 | New Construction | Naples MDF [Office] |  | All Seasons in Naples | Yes | ALU |  | I-241G-B | No
| Magnolia Falls | Certified |  |  | 2017-10-12 | 144 | Fision Home | Received | Pete Ferreira |  | Edward/Rolando | SWFL | 2370 HIDDEN LAKE COURT #9 Naples, Florida 34112 | Conversion/OverBuild | Deauville - ASR9006 - 10.84.255.14 | ASR920 | Deauville | Yes | ZTE |  | F668 | Yes
| Hampton Inn & Suites Airport Hotel | Certified |  |  | 2017-10-12 | 127 | Fision Stay | Pending | Juan Miranda |  | Lik Wong |  | 3449 NW 42nd Avenue Miami, Fl. 33142 | Conversion/OverBuild | FPL Off-Net 10G [Rate Limited to 2G]to Cypress COLO#4 |  | NA | No | SE
| 2000 Condo | Certified |  |  | 2017-10-20 | 96 | Fision Home | Received | Kenton Daley |  | Lik/Jose | WPB | 2000 S. Ocean Drive, Hallandale Beach, FL 33009 | New Construction | FL-2100-CONDO-FLR01-MDF-RTR1 – 10.63.255.113 |  | 2100 Condo | No | ALU | 1 | I-241G-B | Yes
| Marlwood Estate [@ PGA] | Certified | mr3.0 schedule to launch nov-15th |  | 2017-10-20 | 280 | Fision Home | Received | Kenton Daley |  | Saj/Dario | WPB | Dunbar Road, Palm Beach Gardens, FL 33418 | Conversion/OverBuild | Landmark at the Gardens |  | Marlwood Estate | Yes | ALU |  | I-241G-B | Yes
| Midtown Miami 3 [Hyde Midtown] | Certified |  |  | 2017-10-30 | 410 | Fision Home | Received | Roger Bartlett |  | LF/Rolando | MIAMI | 3401 NE 1st Ave, Miami, Fl 33137 | New Construction | Midtown 2 |  | Hyde Midtown | No | ZTE |  | F680 | Yes
| High Point Condo - Section 1 | Certified | Certification is expidited |  | 2017-11-01 | 264 | Fision Home | Received | Kenton Daley |  | Saj/Dario | WPB | 204 Manatee Lane Fort Pierce, FL 34982 | Conversion/OverBuild | 3rd Party Circuit: 10/13/2017 |  | High Point Condo | Yes | ZTE |  | F668 | No
| Richmond Park Phase 1 | Certified | Chassis Housed at Vanderbuilt |  | 2017-11-01 | 24 | Fision Home | Received | Pete Ferreira |  | Edward/Rolando | SWFL | SE corner of Woodcrest Drive and Immokalee Rd. | New Construction | Vanderbilt |  | Richmond Park Phase 1 | Yes | ZTE |  | F668 | Yes
| Martinique at Abacoa | Certified |  |  | 2017-11-06 | 456 | Fision Home | Received | Jorge Pelaez |  | Saj/Dario | WPB | 1812 Dakota Dr, Jupiter, FL 33458 | Conversion/OverBuild | New fiber from Old Marsh [LATER]- Frenchmans Creek [NOW]- ASR9010 |  | Martinique at Abacoa | Yes | ALU |  | I-241G-B | Yes
| Bonita Bay | Certified |  |  | 2017-11-06 | 3507 | Fision Home | Received | Pete Ferreira |  | Edward/Jose | SWFL | 3451 Bonita Bay Blvd., Suite 100 Bonita Springs, Florida 34134 | Upgrade | NI: Pelican Landing and Naples Office - ASR9010 | ASR9010 | Bonita | Yes | ALU |  | I-241G-B | Yes
| Enclave at Boca Dunes (aka Whispering Lakes ) | Certified |  |  | 2017-11-15 | 211 | Fision Home | Received | Donald Rahmer |  | Lik/Jose | WPB | 1400 SW 65th Avenue Boca Raton, FL 33428 | New Construction | Sinai Res - ASR9006 - |  | Sinai Res | No | ALU |  | I-241G-B | Yes
| Santorini at Renaissance Commons | Certified |  |  | 2017-11-15 | 226 | Fision Home | Received | Donald Rahmer |  | Lik/Jose | WPB | 1645 Renaissance Commons Blvd, 33433 | New Construction | Vizcaya Lakes - ASR9006 - |  | Vizcaya Lakes | Yes | ZTE |  | F668 | Yes
| Tuscany at Abacoa | Certified |  |  | 2017-11-15 | 446 | Fision Home | Received | Jorge Pelaez |  | Saj/Dario | WPB | 3524 Greenway Dr Jupiter, Florida 33458 | Conversion/OverBuild | Martinique at Abacoa |  | Tuscany at Abacoa | Yes | ALU |  | I-241G-B | Yes
| Kellswater Bridge | Certified |  |  | 2017-11-15 | 600 | Fision Home | Received | David Turek |  | Bob/Rolando | NC | 3033 Keady Mill Loop, Kannapolis, NC 28081 | Conversion/OverBuild | Kellswater 6500 - Dish to home retail. |  | Kellwater Bridge | NO/Dish | ALU |  | Outdoor ONT Needed! | Yes
| Park Shore Landing | Certified |  |  | 2017-12-01 | 75 | Fision Home | In Sales Phase | Pete Ferreira |  | Edward/Rolando |  |  | Conversion/OverBuild |  |  |  |  | ZTE |  |  | Yes
| 3200 Inc | Certified | Expidite |  | 2017-12-05 | 80 | Fision Home | Received | Bob Smith |  | Saji/Dario | WPB | 3200 S Ocean Blvd, Palm Beach, FL 33480 | Conversion/OverBuild | Circuit 11/15/2017 |  | 3200 Inc | No | ZTE | 1 | F680 | Yes
| 3 Bala Office | Certified |  |  | 2017-12-08 | 150 | Fision Work | Not Applicable | Nerupa Imam |  | LF | PA | 3 Bala Plaza East, Suite 700, Bala Cynwyd, PA 19004 | Upgrade | 1Gig Off Net Circuit FROM 401 |  | NA | NA | NA | NA | NA | NA
| Jupiter Country Club | Certified |  |  | 2017-12-15 | 400 | Fision Home | Received |  |  |  | WPB | 3970 W. Indiantown Road, Jupiter, FL 33478 | Upgrade | NI: Martinique & Frenchman's |  | Jupiter Country Club | Yes | ALU |  | I-241G-B | Yes
| Calabria at Westside | Certified |  |  | 2017-12-15 | 76 | Fision Home | Received | Eddie Miranda |  | Keith Brown | NFL | 2929 Westside Blvd., Kissimme, Florida 34747 | Conversion/OverBuild | Circuit |  | Westside DRI | yes | ALU |  | I | Yes
| Caribe Cove | Certified |  |  | 2017-12-15 | 187 | Fision Home | Received | Eddie Miranda |  | Keith Brown | NFL | 9000 Treasure Trove Ln., Kissimme, Florida 34747 | Conversion/OverBuild | Westside |  | NA | Yes | SE | NA | NA | Yes
| Tuscany at Caribe Cove | Certified |  |  | 2017-12-15 | 69 | Fision Home | Received | Eddie Miranda |  | Keith Brown | NFL | 2920 Westside Blvd., Kissimmee, FL 34747 | Conversion/OverBuild | Westside |  | Westside DRI | No | ALU | 1 | I-241G-B | Yes
| St Andrews Villa Homes | Certified |  |  | 2017-12-15 | 108 | Fision Home | In Sales Phase | Luis Martell |  | Lik/Jose |  |  | New Construction | St James ASR9K |  | St James | Yes | ZTE |  | F668
| Le Jardin | Certified |  |  | 2017-12-16 | 30 | Fision Home | In Sales Phase | Roger Bartlett |  | Lik/Jose | MIAMI | 1160 102nd st Bay Harbor, Florida 33154 | New Construction | St Regis - ASR9006 - 10.63.255.57 |  | Kai at Bay Harbor | No | ZTE |  | F668 | Yes
| Jade Signature | Certified |  |  | 2017-12-20 | 192 | Fision Home | In Sales Phase | Roger Bartlett |  | Saji/Dario | MIAMI | 17070 Collins Avenue Sunny Isles Beach, FL 33160 | New Construction | Acq : asr9006 |  | Jade Signature | No | ALU |  | I-241G-B | Yes
| Park Grove Tower 1 | Certified |  |  | 2017-12-29 | 72 | Fision Home | Pending | John Cleary |  |  | Miami |  | New Construction | Grove at Grand Bay - ASR9006 - 10.63.255. | ASR920 | Certified Under Park Grove (Tower 1, 2 & 3) | No | ZTE | 0 | F668 | No
| Villa Borghese | LOST | Lost to AT&T 6/7/2017 |  | 2017-12-31 | 582 | Fision Home | LOST |  |  |  |  | 6770 Via Villa Borghese Delray Beach, Florida 33446 |  | Valencia Lakes |  | Villa Borghese | Yes | ALU
| Point East Condominium | Certified |  |  | 2017-12-31 | 312 | Fision Home | Received |  |  |  |  | 2895 Point East Drive, Aventura, Fl 33180 |  | Marina Palms - ASR9006 - 10.63.255.62 |  | Point East |  | ALU
| SLS Lux | Certified |  |  | 2018-01-01 | 534 | Fision Home | Received | John Cleary/ Christian G |  | Lik | MIAMI | 801 S Miami Avenue Miami FL | New Construction | SLS LUX Hotel | ASR9006 | NA | No | SE |  | NA | Yes
| Twin Creeks | LOST |  |  | 2018-01-01 | tBD | Fision Home | In Sales Phase | Eddie Miranda |  |  |  | 755 County Rd 210 St Johns, Florida 32259
| TAO MR Upgrade | Certified |  |  | 2018-01-05 | 395 | Fision Home | NOT Approved to Upgrade | Wayne Leonard |  | Saj/Dario | BROW | 2681 N. Flamingo Road Sunrise, FL 33323 | Upgrade | Metropica ASR - Housed at TAO MDF |  | Tao | Yes | ALU | 4 | I-221E-A | No
| VistaBlue Singer Island | Certified |  |  | 2018-01-15 | 58 | Fision Home | Pending | Donald Rahmer |  | Lik/Jose | WPB | 3730 N Ocean Dr, Riviera Beach, FL 33404 | New Construction | Marina Grande |  | Marina Grande | No | ZTE | 1 | F668 | Yes
| Hallandale Art Square | Certified |  |  | 2018-01-17 | 358 | Fision Home | Pending | John Cleary |  | Saj | BROW | 301 N Federal Highway Hallandale, Florida 33009 | New Construction | BeachWalk - ASR9006 - 10.63.255.52 | ASR920 | ALU | No | ALU | 3 | I-241G-B | Yes | Y |  |  |  |  | Y | Y
| Aria on the Bay | Certified | Retail Property |  | 2018-01-26 | 648 | Fision Home | Received | John Cleary |  | Pending | MAIMI | 1770 North Bayshore Drive Miami, FL 33137 | Upgrade | Quantum |  | Aria on the Bay | No | ZTE |  | F680 | Yes
| Shadow Wood Community Association | Certified |  |  | 2018-01-31 | 1481 | Fision Home | Received | Pete Ferreira |  | Edward/Rolando | SWFL | 23101 Oakwilde Blvd, Estero, FL 34135 | Conversion/OverBuild | Pelican Landing and Bonita [Independent paths] ASR9006 |  | Shadow Wood | Yes | ALU | 14 | I-241G-B | Yes
| Teaseley Place | Certified |  |  | 2018-02-01 | 24 | Fision Home | Received | Miguel Castillo |  | Lynn/Rolando | GA | 50 Canton Street Alpharetta, GA 30009 | New Construction | NI: Avalon |  | Teaseley Place |  | ZTE
| Sea Monarch | Certified |  |  | 2018-02-06 | 239 | Fision Home | Received | Bob Smith |  | Lik/Rolando | BROW | 111 N. Pompano Beach Blvd Pompano, Florida 33062 | Conversion/OverBuild | Ocean Sound |  | Ocean Sound | Yes | ZTE | 3 | F668 | No
| Gale Residences, The | Certified |  |  | 2018-02-08 | 129 | Fision Home | Received | Donald Rahmer |  | Lik/Jose | BROW | 401 Bayshore Drive, Fort Lauderdale FL 33304 | New Construction | VUE ASR9006 |  | Gale | No | ZTE | 2 | F680 | Yes
| Hotel Morrison | Certified |  |  | 2018-02-09 | 143 | Fision Stay | Received |  |  | Saji |  | 28 South Federal Highway, Dania Beach, FL 33004 | Conversion/OverBuild | NI: UML & Church [minerva] |  | NA | Pro:idiom iStay Basic | NA |  | NA | NA
| The Reserve at Lake Keowee | Certified | mdf not ready |  | 2018-02-15 | 854 | Fision Home | Received | Miguel Castillo |  | Lynn/Jose | GA | 435 Pine Grove Church Road, 29685 | Conversion/OverBuild | 10G Off-Net Circuit: 55M ETC: Feb-14 2017 |  | The Reserve at Lake Keowee | No | ALU | 8 | I-241G-B | Yes
| Strata at Plantation | Certified |  |  | 2018-02-15 | 147 | Fision Home | Received | Donald Rahmer |  |  | BROW | 4350 NW 8th Court Plantation, Florida 33317 | New Construction | Bella Vista | ASR920 | Strata at Plantation | Yes | ALU | 2 | I-241G-B | Yes | Y |  |  |  |  | Y | Y
| Brighton Lakes | Certified |  |  | 2018-02-16 | 124 | Fision Home | Received | Jorge Pelaez |  | Lik/Jose | WPB | 4775 Brighton Lakes Blvd., Boynton Beach, Florida 33436 | Conversion/OverBuild | Cascade Lakes[housed at V.Pointe] |  | Cascade Lakes | Yes | ZTE | 1 | F668 | Yes
| Old Palm Golf Club | Certified |  |  | 2018-02-16 | 380 | Fision Home | Received | Kenton Daley |  |  | WPB | 11089 Old Palm Drive, Palm Beach Gardens, FL 33418 | Conversion/OverBuild | Landmark at the Gardens |  | Old Palm Gold Club | Yes | ALU | 3 | I-241G-B | Yes
| Spoke | Certified | Router and GPON gear installed. Pending fiber and MDF power |  | 2018-02-20 | 224 | Fision Home | Received | Miguel Castillo |  | Lynn/Rolando | GA | 1450 La France Street Atlanta, Georgia 30307 | New Construction | NI: 55 Mar and BOHO |  | Spoke | No | ZTE |  | F680 | Yes
| Mallory Creek | Certified |  |  | 2018-03-09 | 595 | Fision Home | Received | Dominick Foti |  |  | WPB | 1221 Jeaqga Dr, Jupiter, FL 33458 | Conversion/OverBuild | Martinique at Abacoa |  | Mallory Creek | Yes | ZTE | 5 | F668 | Yes
| Aqua at Pelican Isle Condominium | Certified |  |  | 2018-03-09 | 80 | Fision Encore | Received | Pete Ferreira |  | Edward/Rolando | SWFL | 13665 & 13675 Vanderbilt Dr. Naples, Florida 34110 | Conversion/OverBuild | Naples MDF [Office] |  | Villages of Emerald Bay | Yes | ALU | 1 | I-241G-B | Yes
| Botaniko - Weston Estates Sales Center | Certified | on customer hold |  | 2018-03-15 | 125 | Fision Home | In Sales Phase | Donald Rahmer |  | Saj/Dario | BROW | 2893 Executive Park Dr. Ste. 304 | New Construction | 3rd Party Circuit - 2 crcuits - 1G for temp service and 10G to Residential ETC: AT&T - 1/1/2018 |  | Botaniko | Yes | ZTE |  | F668 | Yes
| Hollywood Circle | Certified | Installs |  | 2018-03-15 | 400 | Fision Home | Received | John Cleary |  | Saj/Dario | BROW | 1858 Hollywood Blvd Hollywood, Florida 33020 | New Construction | NI: New River & Beachwalk . Minerva Feed TBD |  |  |  | ZTE |  | ZTE | Yes
| Summit Garden | Certified |  |  | 2018-03-23 | 102 | Fision Home | Received |  |  |  |  | 701 Summit Ave. Philadelphia, Pennsylvania 19128 | Upgrade | Summit Garden |  | Summit Garden |  | ZTE | 1
| Woodmere | Certified |  |  | 2018-03-23 | 246 | Fision Home | Received | [6 empty] | Summit Garden |  | Summit Garden |  | ZTE
| Promenade Shores at Doral | Certified |  |  | 2018-03-26 | 240 | Fision Home | Received | Jorge Peleaz |  |  | Miami- Dade | 13800 SW 144th Avenue Miami, FL 33196 | Conversion/OverBuild | Modern Doral - 10.63.255.60 |  | Promenade Shores at Doral | No | ZTE | 2 | F680 | Yes
| Meadows at Martin Downs | Certified |  |  | 2018-03-30 | 832 | Fision Home | In Sales Phase | Kenton Daley |  | Saj/Dario | WPB | 2520 SW Waterfall Blvd | Upgrade | Harbour Ridge [ER] and 3rd Party to 2100 | ASR9006 | Meadows at Martins Downs | No | ZTE | 7 | F668 | Yes | [8 empty] | 6
| Biscayne Cove | LOST | CANCELLED |  | 2018-04-01 | 592 | Fision Home | In Sales Phase | Bob Smith |  |  |  | 18151 NE 31st Ct Aventura, Florida 33160 | Conversion/OverBuild | UML |  | Biscayne Cove |  | ZTE |  | F668
| Prima Luce on the Waterfront | LOST |  |  | 2018-04-01 | 220 | Fision Home | LOST | Pete Ferreira |  | Edward/Jose |  | 2631 FIRST STREET Ft. Myers, Florida 33916 |  | Synergy |  | Prima Luce on the Waterfront
| Heritage Bay Golf and Country Club | Certified |  |  | 2018-04-04 | 1250 | Fision Home | Received | Pete Ferreira |  | Edward/Jose | SWFL | 10154 Heritage Bay Blvd. Naples, FL 34120 | Conversion/OverBuild | Vanderbuilt and Old Cypress |  | Heritage Bay Golf and Country Club | Yes | ZTE | 11 | F668 | Yes
| 115 Sunrise Condominium | Certified |  |  | 2018-04-04 | 14 | Fision Home | In Sales Phase |  |  |  | MIAMI | 115 Sunrise Drive Key Biscayne, Florida 33149 | Conversion/OverBuild | Oceana Key Biscayne - ASR9006 – 10.63.255.45 | ASR920 | Towers at Key Bizcayne | Yes | ZTE | 1 | F668
| Portofino Tower | Certified | chassis temp house in apogee |  | 2018-04-20 | 228 | Fision Plus | Received | Luis Martell |  | Abi | MIAMI | 300 South Pointe Dr Miami Beach, Florida 33139 | Conversion/OverBuild | Apogee - ASR9006 - 10.63.255.78 | ASR920 | Portofino Tower | No | ALU | 2 | G-240G-A | Yes
| Golfview Golf & Racquet Club | Certified |  |  | 2018-04-23 | 400 | Fision Home | Received | Pete Ferreira |  | Edward/Jose | SWFL | 14849 Hole in One Circle, Fort Myers, FL 33919 | Conversion/OverBuild | Venetain Pointe | ASR920 | Golfview Golf & Racquet Club | Yes | ZTE | 4 | F668 | Yes
| Venetian Pointe | Certified |  |  | 2018-04-23 | 180 | Fision Home | Received | Pete Ferreira |  | Edward/Jose | SWFL | Summerlin Rd & Gladiolus Dr Ft Myers, Florida 33907 | New Construction | Mirage Bay [Synergy the Future] | ASR9006 | Venetian Pointe | No | ZTE |  | F668 | Yes
| Hollywood Circle -HANDOFF | Certified |  |  | 2018-04-23 | 104 | Fision Stay | Received | John Cleary |  | Saj/Dario | BROW | 1858 Hollywood Blvd Hollywood, Florida 33020 | New Construction | NI: New River & Beachwalk¦ Minerva NI: |  |  |  | SE | 0 | NA | NA
| Silverleaf | Certified | One model home need to be activated |  | 2018-05-01 | 141 | Fision Encore | Received | Donald Rahmer |  |  | WPB | 7825 Lantana Rd Lake Worth, FL 33480 | New Construction | Journey End | ASR920 | Lakes of Sherebrook | No | ALU | 2 | I-241G-B | Yes
| Aventura Park Square [Aloft Hotel] | Certified |  |  | 2018-05-01 | 207 | Fision Stay | Pending | Eric Hart |  | Saj | MIAMI | 2940 NE 207 Street, Aventura, FL 33180 | New Construction | Minerva: UML/ biscayne _r8 & Hollywood circle | ASR9006 | NA | No | SE
| Vice Miami | Certified |  |  | 2018-05-01 | 464 | Fision Home | Received | Eric Hart |  |  | MIAMI | 243 NE 3rd Street Miami, FL 33131 | New Construction | Vizcayne |  | Vice | No | ZTE | 4 | F680 | No
| Oceantree | Certified |  |  | 2018-05-04 | 146 | Fision Home | Received | Kenton Daley |  |  | WPB | 3400 N Ocean Dr, Singer Island, FL 33404 | Conversion/OverBuild | Marina Grande | WS-2960 | Maina Grande: Chassis Filled after this | Yes | ZTE | 2 | F668 | Yes | Y |  |  |  |  | Y | Y
| Genova Coconut Point | Certified |  |  | 2018-05-04 | 201 | Fision Home | Received | Pete Ferreira |  | Edward/Rolando | SWFL | 9510 Cork Screw Palm Circle, Ste. #1, Estero, FL 33928 | New Construction | NI: Pelican Landing and Mirage Bay | ASR9006 | Genova | No | ZTE | 2 | F668 | Yes
| Muse, The | Certified |  |  | 2018-05-08 | 68 | Fision Home | Received | Roger Bartlett |  | Lik/Jose | MIAMI | 17141 Collins Ave, Sunny Isles Beach, FL 33160 | New Construction | Acqualina & Jade Signature | ASR9006 | Muse | No | ALU | 1 | I-040G-R | Ruckus AP | Y |  |  |  |  | Y | Y
| Somerset Tower (Jenny Tower) | Certified |  |  | 2018-05-09 | 115 | Fision Home | Received | Jorge Palaez |  |  | MIAMI | 1545 W 15 Street Road Miami, FL 33125 | Upgrade | Mordern Miami/Urban Club |  | Somerset Tower | No | ALU | 1 | G-240G-A
| Square Station | Certified |  |  | 2018-05-11 | 710 | Fision Home | In Sales Phase | John Cleary |  | Saj/Dario | MIAMI | 1410 NE Miami Court Miami, Florida 33132 | Conversion/OverBuild | Canvas Condo [Quantum & 900B [ASR9010] | ASR9006 | Square Station | No | ALU | 8 | G-240G-A | Yes | Y |  |  |  |  | Y | Y
| SLS LUX Hotel | Certified |  |  | 2018-05-15 | 85 | Fision Stay | Received | John Cleary/ Christian G |  | Lik | MIAMI | 801 S Miami Avenue Miami FL | New Construction | New Fiber - BCC & ICON |  | NA | No | SE | 0 | NA | Aps
| Aventura Park Square | Certified | temp mdf needed; we will feed lifelines from porsche |  | 2018-05-17 | 131 | Fision Home | Received | Eric Hart |  | Saj | MIAMI | 2950 NE 207th St, Aventura, FL 33180 | New Construction | NI: Trump Holly and Beachwalk | ASR9006 | Aventura Park Sq | Yes | ALU | 2 | I-241G-B | Yes
| Bonjour TV 819 10th Ave | Certified |  |  | 2018-05-23 | 1 | Fision Work | Received | Mary Beth |  | Saj | Miami | 819 10th Ave | Hand-Off | Icon Brickell and PDP | ASR9006 | NA | NA | NA | NA | NA | NA
| Hunters Run | Certified |  |  | 2018-05-31 | 1649 | Fision Home | Received | Kenton Daley |  | Saj/Jose | WPB | 3700 Clubhouse Lane, Boynton Beach, Florida 33436 | Conversion/OverBuild | NI: St Andrews and Valencia Lakes | ASR9010 | Hunters Run [3] | Yes | ALU | 17 | G-241G-A | Yes | [5 empty] | Y | Y
| Pelican Point West | Certified |  |  | 2018-06-01 | 24 | Fision Home | Received | Pete Ferreira |  | Edward/Jose | SWFL | 250 PARK SHORE DR Naples, Florida 34103 | Conversion/OverBuild | Lausanne | WS-2960 | Park Shore Tower | Yes | ZTE | 1 | F668 | No | [5 empty] | Y | Y
| Uptown at Liberty Park | Certified |  |  | 2018-06-18 | 320 | Fision Encore | In Sales Phase | Pete Ferreira |  | Edward/Jose | SWFL | NE 24th Ave & NE Pine Island Rd Cape Coral, Florida 33909 | New Construction | North Star Yacht Club | ASR9006 [Shipped] | Uptown at Liberty Park | Yes | ALU | 4 | G-241G-A | Yes | 2018-06-14 | Yes | Yes | Yes | Yes | 2018-07-02 | 2018-07-02
| Aventura Park Square Assisted Living | Certified |  |  | 2018-06-20 | 141 | Fision Encore | Received | Roger Bartlett |  | Saj | MIAMI | 2940 NE 207 Street, Aventura, FL 33180 | New Construction | Aventura | ASR920 | NA | Yes | SE | 0 |  | Yes | Y |  |  |  |  | 2018-06-27 | 2018-06-27
| Murano at Westside | On-Hold |  |  | 2018-07-01 | 350 | Fision Home | Pending |  |  |  | NFL | Florence Villa Grove Rd &amp; Westside Blvd Kissimmee, Florida, United States | New Construction |  |  |  |  | ZTE | 3 | F668 | Yes
| Wellington Shores | LOST |  |  | 2018-07-01 | 181 | Fision Home | LOST |  |  |  |  | 4090 Wellington Shores Drive
| Regency of Palm Beach | Certified |  |  | 2018-07-13 | 85 | Fision Home | Pending | Kenton Daley |  |  | WPB | 2760 South Ocean BLVD, Palm Beach, FL 33480 | Conversion/OverBuild | 3200 [OLT housed at 3200] | ASR920 | Regency of Palm Beach | No | ALU | 1 | G-241G-A | Yes | 2018-06-25 | Yes | Yes | Yes | Yes | 2018-07-11 | 2018-07-11
| Paraiso Bay Views | Certified |  |  | 2018-07-15 | 384 | Fision Home | Received | Roger Bartlett |  | Edward/Rolando | MIAMI | 600 NE 31st St, Miami, FL 33137 | New Construction | Paraiso Bay ASR9006 | WS-2960 | Paraiso Bay View | No | ZTE |  | F680 | No | [5 empty] | 2018-07-16 | 2018-07-16
| Paraiso, Gran | Certified |  |  | 2018-07-15 | 315 | Fision Home | Received | Roger Bartlett |  | Lik/Jose | MIAMI | 660 NE 31st St, Miami, FL 33137 | New Construction | Paraiso Bay ASR9006 | WS-2960 | Paraiso Bay | No | ZTE |  | F680 | No | [5 empty] | 2018-07-16 | 2018-07-16
| Paraiso, One | Certified |  |  | 2018-07-15 | 273 | Fision Home | Received | Roger Bartlett |  | Edward/Rolando | MIAMI | 700 NE 31st St, Miami, FL 33137 | New Construction | Paraiso Bay ASR9006 | WS-2960 | Paraiso Bay View | No | ZTE |  | F680 | No | [5 empty] | 2018-07-16 | 2018-07-16
| Diamondhead Beach Resort | Certified |  |  | 2018-07-15 | 124 | Fision Stay | Received | Pete Ferreira |  | Keith | CFL | 2000 Estero Blvd Fort Myers, FL 33931 | Conversion/OverBuild | 5G: 3rd party circuit [Pending] ETC 6/7/2018 | Nexus9k | NA | No | SE | 0 | SG200-10P | NA
| Canvas Condo | Certified |  |  | 2018-07-15 | 513 | Fision Home | Pending | Eric Hart |  |  |  | 1630 NE 1st Ave Miami, FL 33132 | New Construction | Square Station | ASR9006 | Canvas Condo | Yes | ALU | 5 | G-241G-A | Yes | [5 empty] | 2018-07-25 | 2018-07-25
| Westgate Condos | Certified |  |  | 2018-07-20 | 48 | Fision Home | Received | Pete Ferreira |  | Edward | SWFL | 2901 Gulf Shore Blvd. N. Naples, Florida, 34103 United States | Conversion/OverBuild | Lausanne | WS-2960 | Lausanne | Yes | ALU | 1 | I-241G-B | Yes | 2018-07-16 | MFBREAK-1178 | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-20 | 2018-07-20
| TRYP Hotel | Ongoing | Juan M |  | 2018-07-25 | 150 | Fision Stay | Received | Juan Miranda |  | Lik | BROW | 2720 S.W. 22nd Terrace, Fort Lauderdale, Florida 33312 | New Construction | 3rd Party FPL Circuit. ETC: 10G | ASR9006 | NA | No | SE | 0 | NA | NA | 2018-01-24 | ProIdium | 2018-05-14 | 2018-05-14 | 2018-05-14 | Pending
| Ocean Bay Club | Certified |  |  | 2018-07-26 | 88 | Fision Home | Received | Kenton Daley |  |  | BROW | 5555 North Ocean Blvd. Lauderdale By The Sea, FL 33308 | Conversion/OverBuild | Ocean Sound | ASR920 | Oceab Bay Club | No | ALU | 1 | G-241G-A | Yes | 2018-07-03 | MFBREAK-1160 | 2018-07-16 | 2018-07-16 | 2018-07-25 | 2018-07-27 | 2018-07-27
| Edge/The Lumberyard | Certified |  |  | 2018-07-29 | 112/413 Beds | Fision U | Received | Tony Robbins |  |  |  | 704 West Gaines Street, Tallahassee, FL 32304 | Conversion/OverBuild | Stadium Center & 10G Offnet from 55M | ASR9006 | The Lumberyard (Fision U) | NA | ALU | 0 | G-241G-A | No | 2018-07-03 | MFBREAK-1168 - certified with test account - Cable Service account#: 4498140 | 2018-07-13 | 2018-07-13 | pending second circuit | 2018-08-29 | 2018-08-29
| Giralda Place | Certified | Pending Contract |  | 2018-07-30 | 33 | Fision Home | Received | Donald Rahmer |  | Abi | MIAMI | 2222 Ponce De Leon Coral Gables, Florida 33134 | New Construction | PDP | ME-3412 | Ponce de Leon | 0 | ZTE | F680 | F680 | No | 2018-03-27 | MFBREAK-919 | 2018-04-10 | Passive site to Ponce de Leon | Passive site to Ponce de Leon | 2018-08-21 | 2018-08-21
| University Residence at FSU | Certified |  |  | 2018-08-01 | 1 | Fision U | In Sales Phase | Eddie Miranda |  |  | NFL | 446 Conradi Street, Tallahassee, FL 32301 | Conversion/OverBuild |  |  |  |  | SE | [8 empty] | Pending
| Manchester Square | Certified |  |  | 2018-08-10 | 117 | Fision Home | Received | Pete Ferreira |  | Edward | SWFL | 13355 Kent Street Naples, FL 34109 | Conversion/OverBuild | Olde Cypress - ASR9006 - 10.84.255.4 | WS-2960 | Manchester Square [Housed in Village Walk] | Yes | ALU | 1 | I-241G-B | Yes | 2018-07-24 | MFBREAK-1256 | 2018-08-03 | 2018-08-09 | 8/9/2018 - Pete would like to certify 8/10/2018 | 2018-08-20 | 2018-08-20
| Lakeridge Green | Certified |  |  | 2018-08-15 | 352 | Fision Home | Pending | Matt Kick |  |  | WPB | 6824 Sun River Rd, Boynton Beach | Conversion/OverBuild | Valencia Lakes | ASR920 | Starlight Cove | Yes | ALU |  | G-241G-A | Yes |  | MFBREAK-1226
| Starlight Cove | Certified |  |  | 2018-08-15 | 187 | Fision Home | In Sales Phase | Victor Martinez |  |  | WPB | 12241 Fairway Pines Drive, Boynton Beach, FL 33437 | Conversion/OverBuild | Valencia Point [Cascade Lake] | ASR920 | Starlight Cove | No | ALU | 2 | G-241G-A | Yes | 2018-07-20 | MFBREAK-1225 | 2018-07-31 | Issues with Power, no fiber yet.
| City of Salisbury 10G | Certified |  |  | 2018-08-15 | 3200 | Fision Home | Pending | Nerupa Imam |  | Bob | NC | 1415 Martin Luther King Jr Ave S, Salisbury, NC 28144 | Conversion/OverBuild | 2 x 10G Links to 55M | ASR9006 [2] | City of Salisbury [4] | No | ALU | 12 | 250 X-A | No [retail] | 2018-06-27 | MFBREAK-1159 - Used Kellswater until Salisbury is built out | 12 PON cards | 2018-08-10 | 2018-08-10 | 2018-09-17 | 2018-09-17
| Parque Towers | Certified |  |  | 2018-08-15 | 360 | Fision Home | Received | Eric Hart |  |  | MIAMI | 330 Sunny Isles Blvd Sunny Isles, Florida 33160 | New Construction | Jade Signature |  | Ritz Carlton Residences |  | ZTE | 3 | F680 | No |  | MFBREAK-914
| 1200 West Marshall | Certified |  |  | 2018-08-15 | 136units/406 beds | Fision Stay | Received | [6 empty] | 401 - 10G Circuit
| Quail Creek Village | Certified |  |  | 2018-08-17 | 325 | Fision Home | Received | Pete Ferreira |  | Edward | SWFL | 11655 Quail Village Way, Naples, FL 34119 | Conversion/OverBuild | Quail Creek | WS-2960 | Quail Creek Village | Yes | ALU | 3 | G-241G-A | Yes | 2018-07-24 | MFBREAK-1259 | 2018-08-06 | Pete to advise | 2018-08-16 | 2018-09-04 | 2018-09-04
| Four Season Palm Beach | Upcoming |  |  | 2018-08-22 | 210 | Fision Stay | Received | Juan Miranda |  | Saj | WPB | 2800 S Ocean Blvd, Palm Beach Florida | Conversion/OverBuild | 3200 | Nexus9k | NA | No | SE | 0 | NA | NA | 2018-08-16 | NA - proidium lineup submitted | 8/22/2018 - Dale and John to install and validate services. | 8/22/2018 - Dale and John to install and validate services. | 2018-08-22 | Pending
| Hyde Midtown Hotel / Midtown Miami 3 | Ongoing |  |  | 2018-08-22 | 60 | Fision Stay | In Sales Phase | Christian Galante |  | Saj | MIAMI | 3401 NE 1st Ave, Miami, Fl 33137 | New Construction | Midtown 2 | WS-2960 | Hyde Midtown Hotel | NA | ALU | 1 | I-040G-R | NA | 2017-11-29 | NA | Yes | Yes | Yes | Pending
| Commodore Club South | Certified |  |  | 2018-08-24 | 186 | Fision Home | Received | Luis Martell |  |  | MIAMI | 199 Ocean Lane Drive Key Biscayne, FL 33149 | Conversion/OverBuild | Oceana Key Biscayne - ASR9006 – 10.63.255.45 | ASR920 | Commodore Club South | No | ALU | 2 | G-240G-A | Yes | 2018-06-21 | MFBREAK-1126 | 2018-07-10 | 2018-07-12 | OSP yet to receive permit, current ETA is 8/20
| Atrium Association - First 10g ONT Launch | Certified |  |  | 2018-08-30 | 60 | Fision Home | Received |  |  |  |  | 800 East El Camino Road, Boca Raton, FL 33432 | Conversion/OverBuild | Stratford Arms | ASR920 | Atrium Association [OLT Housed at Stratford Arms] | No | ALU | 2 | G-241G-A | Yes | 2018-08-06 | MFBREAK-1306 | 2018-08-14 | 2018-08-15
| Turnberry Isle Resort JW Marriot 5G Handoff | Upcoming |  |  | 2018-08-31 | 1 | Fision Stay | Received | Juan Miranda |  | Saj | MIAMI | 19999 West Country Club Drive, Aventura, FL | Hand-Off | Aventura Park Sq | Pending Discussion with Jeff | NA | NA | SE | NA | NA | NA | 2018-06-21 | NA- Handoff Only | 2018-08-09 | 2018-08-20 | 2018-08-20 | Pending
| Eagle Bay Phase 1 | Ongoing | Per Keith (10.11) site down due to Hurricane --- 10/11 - Need MAC address info from STB - sent email to Keith/ Richard/ Eddie. 10/12 - Per Angela Smith, new test account will be generated as soon as rates are built in Amdocs. | SubID | 2018-08-31 | 177 | Fision Home | Pending | Eddie Miranda |  | Keith Brown/Rolando | CFL | 2675 Eagle Bay Boulevard, Kissimmee, FL 34744 | Conversion/OverBuild | 3rd Party Circuit from 55M | ASR9006 | Eagle Bay Phase 1 |  | ALU | 6 | O-221H-P | No | 2018-05-14 | MFBREAK-1045 (New test account to be generated in Amdocs) | 2018-05-25 | 2018-05-30 | 2018-05-30 | Pending
| Eagle Bay Phase 2, 3 & 4 | Ongoing | 10/11 - Need MAC address info from STB - sent email to Keith/ Richard/ Eddie. 10/12 - Per Angela Smith, new test account will be generated as soon as rates are built in Amdocs. | SubID | 2018-08-31 | 191 | Fision Home | Pending | Eddie Miranda |  | Keith Brown/Rolando | CFL | 2675 Eagle Bay Boulevard, Kissimmee, FL 34744 | Conversion/OverBuild | Eagle Bay Phase 1 | WS-2960 | Eagle Bay Phase 1 |  | ALU | 6 | O-221H-P | No | 2018-05-14 | MFBREAK-1045 (New test account to be generated in Amdocs) | 2018-05-25 | 2018-05-30 | 2018-05-30 | Pending
| Eagle Bay Townhomes | Ongoing |  |  | 2018-08-31 | 129 | Fision Home | Pending | Eddie Miranda |  | Keith Brown/Rolando | CFL | 2675 Eagle Bay Boulevard, Kissimmee, FL 34744 | Conversion/OverBuild | Eagle Bay Phase 1 | WS-2960 | Eagle Bay Phase 1 |  | ALU | 6 | O-221H-P | No | 2018-05-14 | MFBREAK-1045 | 2018-05-25 | 2018-05-30 | 2018-05-30 | Pending
| Magnolia at Westside | Certified |  |  | 2018-09-07 | 245 | Fision Home | Received | Eddie Miranda |  | Keith Brown/Jose | CFL | Florence Villa Grove Rd and Westside Blvd Kissimmee, FL 33474 | New Construction | Westside | WS-2960 | Westside DRI - LAST 3 slots | No | ALU | 3 | I-240G-B | NA | 2018-08-21 | MFBREAK-1366 | GPON gear requested on 8/21/2018. scheduled to be shipped out this week. |  | Existing OLT | Pending
| Atrium, The | Not Approved |  |  | 2018-09-10 | 107 | Fision Home | NOT Approved to Upgrade | Pending |  | Pending |  | 150 S. E. 3rd Ave Miami, FL 33131 | New Construction | MET 1 - 10.63.255.70 |  | TBD
| New Haven at Abacoa | Certified |  |  | 2018-09-11 | 505 | Fision Home | Received | Dominick Foti |  |  | WPB | 1200 University Blvd #102, Jupiter, FL 33458 | Conversion/OverBuild | Martinique at Abacoa - update rtr hostname to frnchman creek | ASR920 | New Haven at Abacoa | Yes | ALU | 5 | G-241G-A | Yes | 2018-07-17 | MFBREAK-1182 | 2018-08-06 | 8/8/2018: Installed but no power from FPL . No ETC was given. 1 more PON card needed. Currently installed with 1. | 2018-09-04 | 2018-09-11 | 2018-09-11
| Auberge- Fort Lauderdale | Certified |  |  | 2018-09-11 | 171 162 | Fision Home | In Sales Phase | Donald Rahmer |  | Abi |  | 2200 N Ocean Blvd. Fort Lauderdale, FL 33305 | New Construction | Berkley South | ASR920 | Auberge- Fort Lauderdale | No | ALU | 2 | G-240G-A | Yes | 2018-02-22 | MFBREAK-1384 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-09-11 | 2018-09-11
| Ardissone Condominium | Certified |  |  | 2018-09-14 | 33 | Fision Home | Received | Pete Ferreira |  | Edward | SWFL | 4400 Gulf Shore Blvd. N. Naples, Florida, 34103 United States | Conversion/OverBuild | Lausanne | WS-2960 | Swan Lake Club | Yes | ALU | 1 | G-241G-A | Yes | 2018-08-29 | MFBREAK-1397 | 2018-09-10 | 2018-09-12 | 2018-09-12 | 2018-10-02 | 2018-10-02
| Club Brittany at Park Shore | Certified |  |  | 2018-09-14 | 127 | Fision Encore | Received | Pete Ferreira |  | Edward | SWFL | 4021 Gulf Shore Blvd. N.Naples, Florida, 34103 United States | Conversion/OverBuild | Lausanne | WS-2960 | Swan Lake Club | Yes | ALU | 2 | G-241G-A | Yes | 2018-08-29 | MFBREAK-1395 | 2018-09-10 | 2018-09-12 | 2018-09-12 | 2018-10-02 | 2018-10-02
| Swan Lake Club | Certified |  |  | 2018-09-14 | 40 | Fision Home | Received | Pete Ferreira |  | Edward | SWFL | 4140 Crayton Rd. Naples, Florida, 34103 United States | Conversion/OverBuild | Lausanne [Swap the following 2x10G with 4x10G] | WS-2960 | Swan Lake Club | Yes | ALU | 1 | G-241G-A | Yes | 2018-08-29 | MFBREAK-1394 | 2018-09-10 | 2018-09-12 | 2018-09-12 | 2018-09-14 | 2018-09-14
| Vistas at Park Shore | Upcoming | On 10.03, per Cathy, the bulk plug & play services includes Expanded Basic Television |  | 2018-09-14 | 131 | Fision Home | In Sales Phase | Pete Ferreira |  | Edward | SWFL | 4651 Gulf Shore Blvd N Naples, Florida, 34103 United States | Conversion/OverBuild | Lausanne | WS-2960 | Swan Lake Club | Yes | ALU | 2 | G-241G-A | Yes | 2018-08-29 | MFBREAK-1396 | 2018-09-10 | 2018-09-12 | 2018-09-12 | 2018-10-02
| 327 Royal Palm Condo | Certified |  |  | 2018-09-15 | 25 | Fision Home | Received | Donald Rahmer |  | Pending | WPB | 327 E Royal Palm Rd Boca Raton, FL 33432 | New Construction | 200 East | ASR920 | 327 Royal Palm Condo | No | ALU | 1 | G-240G-A | Yes | 2018-08-03 | MFBREAK-1297 | 2018-08-08 | Carl to confirm. | Fiber is ready, however we're still pending rectifiers. About 3 building away.. Label at 200 east... Should be first 12 at Palm.... | 2018-09-05 | 2018-09-05
| Moody River Estates | On-Hold |  |  | 2018-09-15 | 731 | Fision Home | Received | Pete Ferreira |  | Edward | SWFL | 3050 Moody River Blvd. North Fort Myers, FL 33903 | Conversion/OverBuild | North Star Y Club | WS-2960 | Moody River Estates | Yes | ALU | 8 | G-241G-A | Yes
| Urbano Hilton Garden Inn Brickell | Upcoming |  |  | 2018-09-15 | 1 | Fision Stay | Received | Juan Miranda |  | Saj | MIAMI | 2500 Brickell Avenue, Miami FL 33129 | Upgrade | MR: SLS, Minerva: Icon Brickell - No Redundancy | Nexus9k | NA | No | SE | 0 | NA | NA | ASAP |  |  |  |  | Pending
| Riverview Tower | Certified |  |  | 2018-09-19 | 100 | Fision Encore | Pending | John Cleary |  | Saji | MIAMI | 645 NW 1st Street Miami, Florida 33128 | New Construction | Bonjour ASR - 10.63.255.151 | ASR920 | Riverview Tower | No | ALU | 1 | G-240G-A | Yes | 2018-08-03 | MFBREAK-1295 | 2018-08-10 | 8/15/2018 - per mary, Riverview olt is installed but no rectifier or batteries yet. After labor day | 2018-09-18 | 2018-09-19 | 2018-09-19
| OceanView | Certified |  |  | 2018-09-21 | 405 | Fision Home | Received | Chris Smily |  |  | MIAMI | 19390 Collins Ave, Sunny Isles, FL 33160 | Conversion/OverBuild | Porshe Tower Design [LR] | ASR920 | OceanView | Yes | ALU | 4 | G-241G-A | Yes | 2018-08-22 | MFBREAK-1378 | 2018-08-22 | 2018-09-06 | 2018-09-10 | 2018-09-21 | 2018-09-21
| Woodfield Vero [HOA/POA] | Certified |  |  | 2018-09-26 | 434 | Fision Home | Received | Jim Campbell |  |  | WPB | 2755 Woodfield Blvd Vero Beach, Florida 32966 | Conversion/OverBuild | 10G Circuit back to 2100Cypress - check with Matt ETC: 9/1/2018. Build back to Frenchman? WDM - 104km | ASR9006 | Woodfield POA | No | ALU | 4 | G-240G-A | Yes | 2018-06-06 | MFBREAK-1118, NETENG-3426 | 2018-07-06 | 2018-07-06 | 2018-09-26 | 2018-09-26 | 2018-09-26
| Eagle Point | Upcoming |  |  | 2018-09-28 | 66 | Fision Home | Pending | Victor Martinez |  | Abi | WPB | 7619 Eagle Point Drive, Delray Beach, FL 33446 | Conversion/OverBuild | HighPoint of Delray | ASR920 | High Point of Delray | No | ALU | 1 | G-241G-A | Yes | 2018-08-02 | MFBREAK-1290 | 2018-09-11 | 2018-09-11 | 2018-09-24 | 2018-09-28 | 2018-09-28
| International Club at Villages of Oriole | Certified |  |  | 2018-09-28 | 104 | Fision Home | Pending | Victor Martinez |  | Abi | WPB | 14896 Bal Moral Lane, Delray Beach, FL 33446 | Conversion/OverBuild | HighPoint of Delray | ASR920 | High Point of Delray | No | ALU | 1 | G-241G-A | Yes | 2018-08-02 | MFBREAK-1291 | 2018-09-11 | 2018-09-25 | 2018-09-24 | 2018-09-28 | 2018-09-28
| Akoya [Launched as part of Boca West] | Certified | Same as Boca West??? |  | 2018-10-01 | 139 | Fision Home | Received | Donald Rahmer |  | Pending | WPB | 20583 Boca West Dr. Boca Raton, Florida | New Construction | Boca West?? | Boca West | Boca West | Yes | ZTE | 2 | F668 | Yes
| Preserve at Hobe Sound | Upcoming |  |  | 2018-10-01 | 315 | Fision Home | Pending |  |  |  | WPB | 5303 SE Preserve Trce Hobe Sound, Florida, 33455 United States | Conversion/OverBuild | Not in OSP - Erin to update | ASR920 | Preserve at Hobe Sound |  | ALU | 4 | G-241G-A | Yes
| Costa Brava | Upcoming |  |  | 2018-10-01 | 216 | Fision Home | In Sales Phase |  |  |  | MIAMI | 5601 Collins Ave, Miami Beach, Florida, 33140 | Conversion/OverBuild | Not in OSP - Need new timeline | Pending OSP | Costa Brava | No | ALU | 2 | G-240G-A | Yes
| High Point of Delray West | Certified | On 10.03, Rob R. provided a COA. Certified 10/3. |  | 2018-10-02 | 368 | Fision Home | Pending | Victor Martinez | Guillermo | Abi | WPB | 5230 Lakefront Blvd, Delray Beach, Florida 33484 | Conversion/OverBuild | Broken Sound & St Andrews | ASR9006 | High Point of Delray | Yes | ALU | 4 | G-241G-A | Yes | 2018-08-02 | MFBREAK-1289 - PENDING (99995230) | 2018-09-11 | 2018-09-11 | 2018-09-24
| Avida Senior Living | Certified | MR Cert Scheduled for 10.04.18; Per Joia on 10.02, Splicing waiting. HLD is pending to be sent out; Provobles with SUB-ID only video on demand shows. Next MR Cert 10/5/2018. (10.11 - rm) HLD and Launch summary sent in MR Cert email. |  | 2018-10-09 | 460 | Fision Home | Received | Pete Ferreira | Ramon | Edward/Jose | SWFL | 7650 Gladiolus Drive Ft Myers, Florida 33908 | New Construction | NI: Pelican Landing and Mirage Bay | ASR9006 | Avida Senior Living | Yes | ALU | 5 | G-241G-A | Yes | 2018-05-03 | MFBREAK-1027 (30003122001) | 2018-05-11 | 2018-06-29 | Pending Pete Feedback |  |  | MR cert pushed to after Amdocs
| Brentwood Lakes | Certified | All MDF gear installed 7/17/18; SOW submitted to Eng 7/25/18; Plant guilt and OLT/ASR activated on 8/1/2018; Circuit handed off to HWC on 10/01/18; MR Cert pending: 10/10/18 contingent on AT&T circuit stability. (10.11 - rm) HLD and Launch Summary sent in MR Cert email |  | 2018-10-09 | 458 | Fision Home | Received | Eddie Miranda | Ramon | Keith Brown | NFL | 290 Bending Branch | Upgrade | 3rd Party Circuit 10 2100 [etc 9/25/2018] | ASR9006 | Brentwood Lakes [reuse existing] | No | ALU | 3 |  |  | 2018-07-25 | MFBREAK-1474 (30002746001), NETENG-3334 | [5 empty] | All MDF gear shipped and installed 7/17/2018 SOW submitted to Eng 7/25/2018. Plant built out and OLT/ASR ready for activation – 8/1/2018 Circuit handed off to HWC and became stable on 10/4/2018. MR Certification sched – 10/8
| 1000 Museum [1000 Biscayne Tower] | Ongoing | Per Joia, on 10.02, MR Certification a priority. 10/10 - OSPF successfully enabled. 10/11 - SUB ID 30005099001 provided by Marketing. | MR Cert | 2018-10-12 | 83 | Fision Home | Received | Eric Hart | Guillermo | Pending | Miami | 1000 Biscayne Blvd Miami, Florida 33132 | New Construction | 900 [Router] Marquis [Chassis] | ASR9006 | 1000 Museum | No | ALU | 1 | G-240G-A | Yes - Ruckus Aps | 2018-07-09 | MFBREAK-1257 (30005099001) | 2018-07-24 | 2018-08-28 | 2018-08-28
| Admirals Walk Condo | Ongoing | waiting for the PM to verify if we have fiber to the MDF to do the cross-connect; @Admiral Walk... 288ct panel PT1-12.. Green, 3 meter jumpers.. NOTE:H.E. Is located on roof.. elevator to top floor, stars to roof. Door to left.. Scheduled to be cross-connected 10/9. 10/11 - SUB ID 30005225001 provided by Marketing. | MR Cert | 2018-10-15 | 68 | Fision Home | Received | Victor Martinez | Guillermo |  | WPB | 4545 N Ocean Blvd, Boca Raton, Florida 33431 | Conversion/OverBuild | BY&RC_02 - FL-BOCA-Y+R-CLUB-FLR01-MDF-RTR02 [10.63.255.120] | ASR920 | Admiral Walk Condo | No | ALU | 1 | G-241G-A | Yes | 2018-09-17 | MFBREAK-1455 (30005225001) | 2018-10-02 | 2018-10-03 | 2018-10-09
| Kewoee Key | Upcoming |  |  | 2018-10-15 | 1613 | Fision Home | In Sales Phase | Miguel Castillo |  |  | GA | 1392 Stamp Creek Rd Salem, South Carolina, 29676 United States | Conversion/OverBuild |  |  |  |  | ALU |  | G-241G-A
| One by Tross | Ongoing | Per Joia on 10/8 , MR Cert date moved to 10/22. 10/8 - Cross-connect complete. 10/12 - SUB ID 30005463001 provided by Marketing. MR cert scheduled for 10/18. | MR Cert | 2018-10-22 | 17 | Fision Home | Received | John Cleary | Abi | Lik/Josh | MIAMI | 1150 101st Street Bay Harbor Islands, Florida, 33154 United States | New Construction | St Regis ASR [OLT] and Sereno [COA Services] | WS-2960 | Bay Harbor Island [Housed at Sereno MDF] | No | ALU | 1 | G-240G-A | No | 2018-09-05 | MFBREAK-1432 (30005463001) | 2018-09-18 | 2018-09-20 | 2018-10-08 |  |  | Scheduled to be x-connected 10/8/2018. Pending SubID from Marketing.
| Pearl House | Ongoing | Per Joia on 10/8 , MR Cert date moved to 10/22. 10/8 - Cross-connect complete. 10/17 - SUB ID 30006514001 provided by Marketing. | MR Cert | 2018-10-22 | 15 | Fision Home | Received | Roger Bartlett | Abi | Lik/Josh | MIAMI | 1170 101th St, Bay Harbor, FL 33154 | New Construction | St Regis ASR [OLT] and Sereno [COA Services] | WS-2960 | Bay Harbor Island [Housed at Sereno MDF] | No | ALU | 1 | G-240G-A | No | 2018-09-05 | MFBREAK-1434 (30006514001) | 2018-09-18 | 2018-09-20 | 2018-10-08 |  |  | Scheduled to be x-connected 10/8/2018. Pending SubID from Marketing.
| Palm Villas | Ongoing | Per Joia on 10/8 , MR Cert date moved to 10/22. 10/8 - Cross-connect complete. 10/9 - Per Ryan, Legal is working on contract. Needed before Marketing can release SubID. | SubID | 2018-10-22 | 14 | Fision Home | In Sales Phase | Roger Bartlett | Abi | Lik/Josh | MIAMI | 9870-9880 East Bay Harbor Drive, Bay Harbour Isl, FL 33154 | New Construction | St Regis ASR [OLT] and Sereno [COA Services] | WS-2960 | Bay Harbor Island [Housed at Sereno MDF] | No | ALU | 1 | G-240G-A | No | 2018-09-05 | MFBREAK-1435 | 2018-09-18 | 2018-09-20 | 2018-10-08 |  |  | Scheduled to be x-connected 10/8/2018. Pending SubID from Marketing.
| Bay Harbor One | Ongoing | Per Joia on 10/8 , MR Cert date moved to 10/22. 10/8 - Cross-connect complete. 10/9 - Per Ryan, Legal is working on contract. Needed before Marketing can release SubID. | SubID | 2018-10-22 | 36 | Fision Home | In Sales Phase | Roger Bartlett | Abi | Lik/Josh | MIAMI | 1133 Kane Concourse Bay Harbor Islands, Florida 33154 | New Construction | St Regis ASR [OLT] and Sereno [COA Services] | WS-2960 | Bay Harbor Island [Housed at Sereno MDF] | No | ALU | 1 | G-240G-A | No | 2018-09-05 | MFBREAK-1433 | 2018-09-18 | 2018-09-20 | 2018-10-08 |  |  | Scheduled to be x-connected 10/8/2018. Pending SubID from Marketing.
| Marquesa Isles | Upcoming | A Sub ID pending. Reached out to Pete Ferreira. | HLD | 2018-10-23 | 156 | Fision Home | Received | Pete Ferreira | Ramon | Edward | SWFL | 2101 County Barn Road, Naples, Florida | New Construction | Deauville - ASR9006 - 10.84.255.14 | WS-2960 | Marquesa Isles [Housed in Deauville] | Yes | ALU | 2 | G-241G-B | Yes | 2018-07-24 | MFBREAK-1258 (30007111001) | 2018-08-22 | 2018-09-18 |  |  |  | MR cert pushed to after Amdocs; SubId pending.
| Palace at Bay Harbour [Gig BULK] | Ongoing | 10/16 - Per Chris Wilson, Fiber will be ready end of 10/17 - can install MDF Switch (not needed for MR cert). SUB ID 30004964001 provided by Marketing. MR cert scheduled for 10/18. MDF Switch installed but needs power | MR Cert | 2018-10-23 | 148 | Fision Home | Received | Luis Martell | Abi | Lik/Josh | MIAMI | 10101 Collins Avenue Bal Harbor, Florida 33154 | Conversion/OverBuild | St Regis ASR | ASR920 | Oceana Bal Harbor | No | ZTE | 3 | F668 | No | 2018-09-05 | MFBREAK-1436 - (30004964001) | N/A | N/A | N/A - Passive |  |  | Pending SubID from Marketing
| Parkside Villas (Palm City) | Upcoming | No COA. Fed from? SOW Submited; |  | 2018-11-05 | 68 | Fision Home | In Sales Phase | Matt Kick |  |  | WPB | 1593 SW Pineland Way, Palm City, Florida, 33490 | Conversion/OverBuild | Medows at Martin Down | ASR920 | Meadows |  |  |  | G-241G-A |  | MFBREAK-1547 | FBREAK-1547 (30007553001)
| AC Doral | Upcoming | Fiber is pending. Ask Juan Miranda if fiber is ready and is MRoom needed? - Per Saji power and AC needed. Sched for Wed 10/10/18 | Cross Connect | 2018-10-26 | 118 | Fision Stay | Received | Juan Miranda | Ramon | Saj | Miami | 2500 Brickell Avenue Miami Florida, 33129 | Conversion/OverBuild | Shoma - 10.50.255.35 - 2km ¦ MR Manor | ASR920 | NA | No | SE | 0 | NA | No | 2018-09-19 | [6 empty] | SOW Submitted. MDF gear currently prepped. Scheduled to be installed next week. Pending Fiber delivery.
| Sunset Harbour North Condominium | Upcoming | waiting for OLT, should by ready for delivery on friday. On 10.03 Robert O. reported he picked up the equipment. 10/9 - Per Luis Martell, Power and Cooling ready. Start installs on 10/25. | Cross Connect | 2018-10-26 | 217 | Fision Home | Received | Luis Martell | Guillermo | Saji | MIAMI | 1900 Purdy Ave, Miami Beach, FL 33139 | Conversion/OverBuild | One Hotel [need MOD200 with 4x10G] | ASR920 | Sunset Harbor | No | ALU | 2 | G-240G-A | Yes | 2018-09-27 | MFBREAK-1457 (30007279001) | 2018-10-05 | 10/5/2018 - OLT Turned off no AC
| Fairfield Inn Hotel | Ongoing | cross-connect for 10/3/18; test TV and Data 10/4/18 -- On 10.04 John and Dale are installing today. Need to send Hand-off email | MR Cert | 2018-10-26 | 133 | Fision Stay | Pending | Juan Miranda | Ramon | Saj | MIAMI | 8051 NW 36th Street, Doral, FL 33166 | Conversion/OverBuild | SHOMA_r36 – 10.50.255.36 [2x1G] | ASR920 | NA | No | SE | 0 | NA | NA | 2018-09-19 |  |  |  | 2018-10-03 |  |  | SOW Submitted. MDF gear currently prepped. Scheduled to be installed next week. Pending Fiber delivery. Power and AC still pending.
| 6080 Collins Hotel | Ongoing | (10.02 - Lou issued PO for AG5900 gateway and SW); (10.02 - Eleven OS Portal PO issued). PMS webrac, this is based on 1215 west ave. 10/15 - Dale said need 5 Tripp Lite 1000 BBUs for the 5 IDFs. Sent email to Sonia to request transfer from Warehouse. Cross-connect scheduled for Wed. 10/16 - Fiber info provided by Chris. | MR Cert | 2018-10-26 | 70 | Fision Stay | Received | Juan Miranda | Ramon | Saji | MIAMI | 6080 Collins Ave, Miami Beach, FL33140 | New Construction | MR: Carillon - FL-CARILLON-RES-FLR1-MDF-RTR2 [10.63.255.79] | Nexus9k | NA | No | SE | 0 | NA | NA | 2018-09-19 | NA |  |  | Total footage is 5564 feet. - Levinton wallbox top left bulkhead ports 1-4 to carrilon. UPC connectors. |  |  | Nomadix requested/approved. HWC issued the Eleven OS PO. Site ready. Splash page requirements submitted to PM for customer to review and finalized.
| Delray Beach Club | Upcoming | Fed from Admirals Walk. Dale - Fiber for MDF switch connected to Gi0/0/0/7 and Gi0/1/0/7. Cross-connect complete at Boca Yatch. |  | 2018-10-26 | 77 | Fision Home | In Sales Phase | Victor Martinez |  |  |  | 2000 S Ocean Blvd, Delray Beach, FL 33483 | Conversion/OverBuild | BY&RC - FL-BOCA-Y+R-CLUB-FLR01-MDF-RTR01 [10.63.255.48] | ASR920 | Admiral Walk Condo [DISTANCE NEEDED] | Yes | ALU | 1 | G-241G-A |  |  | MFBREAK-1523 (30005379001) | [5 empty] | No pon card installed for Delray beach condos
| Metropica Towers (Phase I) (Rush) | Upcoming | move-in date: dec 2018/Jan 2019 Waiting for permition to get the fiber to the building (10.02). Training is need to enter site |  | 2018-10-30 | 263 | Fision Home | Pending | John Cleary |  |  | BROW | 1800 NW 136 Avenue Sunrise, FL 33323 | New Construction | TAO | ASR9006?? | Metropica Towers (Phase I) | Yes | ALU |  | G-241G-A |  |  | MFBREAK-1552
| Torino Lakes | Upcoming | move in end of nov/dec |  | 2018-11-01 | 148 | Fision Home | In Sales Phase | Donald Rahmer |  | Pending | WPB | 4008 NW Torino Lakes Circle Port St Lucie, Florida 34952 | New Construction | St James [3.2km] | ASR920 | Torino Lakes | No | ALU | 2 | G-240G-A | Yes | N
| The Meadows of Estero Condo | Upcoming | Start installs 12/1 ("Go Live date") |  | 2018-11-01 | 262 | Fision Home | Received | Pete Ferreira |  | Edward | SWFL | 21516 Baccarat Lane Estero, Florida, 33928 United States | Conversion/OverBuild | Genova - SWFL-GENOVA-FLR1-MDF-RTR1 [10.84.255.21] | WS-2960 | Genova. Currently 241gb- can we also install g241ga on the same OLT? Ask Jeff. Use last 3. | Yes | ALU | 3 | G-241G-A | Yes |  | MFBREAK-1535
| Windsong Villas | Upcoming |  |  | 2018-11-01 | 104 | Fision Home | In Sales Phase | Pete Ferreira |  | Edward | SWFL | 7000 Penzance Blvd Ft Myers, Florida, 33966 United States | New Construction | Mirage Bay [Synergy the Future] | WS-2960 | Windsong Villas OR Mirage Bay [check OTL for available spalce - currently 241gb ont, can use use 240g-a? ask Jeff. Use last 4. | No | ALU | 1 | G-241G-A | Yes
| Royal Reserve | Upcoming |  |  | 2018-11-01 | 14 | Fision Home | In Sales Phase | Miguel Castillo |  |  | NC | 422 Royal Reserve Dr Sunset, South Carolina, 29685 United States | Conversion/OverBuild |  |  | Royal Reserve |  | ALU | 1 | G-241G-A
346 | The Aura (Urbanea) | Upcoming | Per Joia, on 10.02, MR Cert moved to 10/15. MR Cert on-hold Pending contract and SubID. Has 2960 (10.57.74.147) going back to PDP for Lifelines. Move connection from PDP router to Urbanea - coordinate with Dale/ John. Move (1) 1G link at a time to reduce downtime/ or 30 min Maint window during day for downtime. Also has Adtran and SG350 downstream. 10/8 - Per Joia, MR Cert date moved to 11/1. Contract received - Cathy sent Launch Summary. Pending SubID from Marketing. | MR Cert | 2018-11-01 | 100 | Fision Home | In Sales Phase | Roger Bartlett | Abi | Saj/Dario | MIAMI | 21 SE 1st Avenue Miami, Florida 33131 | New Construction | PDP to Dadleland - as part of the ring - 40G, Bidi - one port needed at PDP | ASR9006 | Urbanea | No | ALU | 1 | G-240G-A | No | 2018-08-03 | MFBREAK-1298 - No contract - Pending Sub ID | OLT: 8/8/2018, RTR: 8/15/2018 | 2018-09-05 | 2018-09-20 |  |  | MR Cert moved to 10/15. MR Cert on-hold Pending contract and SubID.
1070 | Miami World Center PARAMOUNT | Upcoming | SOW to be submitted. 10/11 - Jeff confirmed still Node Insertion and BiDi. ASR and RSP440 damanged - Warehouse to send replacement. | MR Cert | 2018-11-01 | 542 | Fision Home | Pending | John Cleary | Abi | Saji | MIAMI | 900 NE 1st Avenue Miami, Florida, 33132 United States | New Construction | NI: 900 & NOTA - 10.69.255.4 & 10.63.255.32 - bi-di | ASR9006 | Miami World Center PARAMOUNT | No | ALU | 5 | G-240G-A | Yes |  | MFBREAK-1475 | [5 empty] | SOW to be submitted
| Grove House |  |  | SOW | 2018-11-01 | 98 | Fision Stay | Received | Juan Miranda | Guillermo | Saji | MIAMI | 3401 Main Highway Miami Florida 33133 | New Construction | Minerva PDP 10.50.255.14 - MR Grove at Grand Bay 10.63.255.90 | ASR920 | NA | NA | NA | NA | NA | NA | [5 empty] | 2018-11-01
| 17 West | Upcoming |  |  | 2019-01-21 | 27 | Fision Home | Pending |  |  |  | MIAMI | 1698 Alton Rd, Miami Beach, FL | New Construction | One Hotel | ASR920 | 17 West
| Belle Plaza Condo | LOST |  |  | 2018-11-01 | 226 | Fision Home | Pending |  |  |  | MIAMI | [5 empty] | Pending PCN | ALU
| Downtown Doral Project Tower 5 | Upcoming |  |  | 2018-11-01 | 238 | Fision Home | In Sales Phase | John Cleary |  |  | MIAMI | 5350 NW 84th Avenue Doral, Florida 33166 | New Construction | FL-MANORCITYPLACE-FLR02-MDF-RTR - 10.63.255.44 | ASR920 | Downtown Doral Project Tower 10 | No | ALU | 2 | G-240G-A | Pending PCN
1066 | Miami World Center Caoba [blockG/Rentals] | Upcoming | we need Paramount Bay to be ready because this feeds off of this; Per Joia on 10.02, the MR Cert moved to 11/1/18 |  | 2018-11-01 | 450 | Fision Home | Pending | John Cleary |  |  | MIAMI | 41 NE 7 St Miami, Florida 33132 | New Construction | Miami World Center PARAMOUNT | ASR920 | Miami World Center Trailer | No | ALU | 4 | G-240G-A | Yes |  | MFBREAK-1476
| Ardmore at Rice Hope | Upcoming | ready to be shipped | HW | 2018-11-01 | 300 | Fision Home | Received | Miguel Castillo | Guillermo | Lynn | GA | 108 Birch Circle Port Wentworth, GA 31407 | New Construction | 10G Circuit. ETC 10/18/2019 | ASR9006 | Ardmore at Rice Hope | No | ALU | 3 | G-241G-A | Yes | 2018-09-20 | MFBREAK-1456 | 2018-10-04 | ready to be shipped
| Harbor House - WPB | Upcoming |  |  | 2018-11-01 | 192 | Fision Home | In Sales Phase | [5 empty] | Conversion/OverBuild | 2100 Condo/Sloan Curve - Does Jeff wants another circuit?? | ASR920 | Harbor House - WPB
| Pine Ridge South 2 | LOST |  |  | 2018-11-01 | 335 | Fision Home | LOST | [5 empty] | Conversion/OverBuild | Buttonwood | ASR920 | Pine Ridge South 2
| Banyan Springs | LOST |  |  | 2018-11-02 | 658 | Fision Home | LOST | [6 empty] | Valencia Lakes | ASR9006 | Banyan Springs | Yes | ALU
| Quadro | Upcoming | Need lifelines 11/1, i.e. need switch |  | 2018-11-09 | 198 | Fision Home | Pending | Daniel Wright |  |  | MIAMI | 3900 Biscayne Blvd Miami, Florida, 33137 United States | New Construction | Onyx | ASR902 | Quadro | No | ALU | 2 | G-240G-A | Pending PCN
| Buttonwood East | Upcoming | 10/9 - Need platform assignment. Will be fed from Buttonwood West? This is an Upgrade. DISH to mediaroom |  | 2018-11-09 | 217 | Fision Home | NOT Approved to Upgrade |  |  | Saji/Dario |  | 3370 Shadow Wood Dr. Lake Worth, FL 33463 | Upgrade | FL-BUTTONWOOD-FLR01-MDF-RTR01 – 10.63.255.116 | ASR920 | Buttonwood |  | CMTS |  | F668
| The Courtyard Condos | Upcoming | 10/9 - Fiber to property by middle of Nov (follow up with PM). Then install MDF switch (but not required for MR cert). Engineering to complete config. GPON to install 1 PON card when doing MR certification. 10/11 - Per Kindley, "Stand by for SUB ID". | MR Cert | 2018-11-10 | 23 | Fision Home | Received |  | Abi | Saji/Dario | WPB | 1100 Surf Rd, Singer Island, Florida 33404 | Conversion/OverBuild | Marina Grande RTR [10.63.255.54] | ASR920 | Tiara Condominium | Yes | ALU | 1 | G-241G-B | Yes | 2018-09-28 | MFBREAK-1458 (30007363001) | ready for pick up |  |  |  |  | Engineering to complete config. Marketing to release SubID.
| Cheney Ranch | Upcoming |  |  | 2018-11-15 | 109 | Fision Home | In Sales Phase | Donald Rahmer |  |  | WPB | 155 Jog Rd West Palm Beach, Florida, United States | New Construction |  |  |  |  | ALU | 1 | G-241G-A
| The Bluffs at the River HOA | Upcoming |  |  | 2018-11-15 | 363 | Fision Home | In Sales Phase |  |  |  | WPB | 266 River Park Dr Jupiter, Florida, 33477 United States | Conversion/OverBuild |  |  | The Bluffs at the River HOA | No | ALU |  | G-240G-A
| Barrington Cove | Upcoming |  |  | 2018-11-15 | 178 | Fision Home | Pending | Eddie Miranda |  | Keith Brown | NFL | 11275 Riverstone Way, Jacksonville, Florida 32218 | Conversion/OverBuild | 2 independent paths from Herons Landing & Tier Point COLO. Part of Jacksonville Ring | ASR9006 - Router shipped/approved | Barringon Cove [Pending approval] | TBD | ALU | 2 | I-241G-B
| Pines at Glen Laurel | Upcoming |  |  | 2018-11-15 | 240 | Fision Home | Pending | Miguel Castillo |  | Lynn | NC | 1441 NC 42 East<br>Clayton, North Carolina, 27527<br>United States | New Construction | Master shown as Lost and no circuit. |  |  |  | ALU |  | G-241G-A
| Brickell West - 747 Miami Center | Upcoming | Per Joia, on 10.02, MR Cert date moved to 11/15. Per John Cleary on 10/8, MDF has working A/C. Need to install racks. need to be certify in oct; No contract |  | 2018-11-15 | 223 | Fision Home | In Sales Phase | Pending |  | Pending | MIAMI | 729 NW 2nd Street Miami, Florida 33128 | New Construction | Bonjour ASR - 10.63.255.151 | ASR920 | Riverview Tower | No | ALU | 2 | G-240G-A | Yes | 2018-10-03 | MFBREAK-1473
| Downtown Doral Project Tower 10 | Upcoming | Per Joia, on 10.02, the MRCert date moved to 11/15 |  | 2018-11-15 | 231 | Fision Home | In Sales Phase | John Cleary |  |  | MIAMI | 5250 NW 84th Ave Doral, Florida 33166 | New Construction | FL-MANORCITYPLACE-FLR02-MDF-RTR - 10.63.255.44 | ASR920 | Downtown Doral Project Tower 10 | No | ALU | 2 | G-240G-A | Pendign PCN
| Motion at Dadeland (Rush) | Upcoming | Per Joia, on 10.02, we need to rush. MR Cert on 11/30/18 |  | 2018-11-15 | 285 | Fision Home | Pending |  |  |  | MIAMI | 6900 SW 84th Steet<br>Miami, Florida, 33143<br>United States | New Construction | Downtown Dadeland – ASR9006 - 10.63.255.83 - 5km | ASR920 | Motion at Dadeland | No | ALU | 3 | G-240G-A | Yes
| Pembroke Pines City Center | Upcoming |  |  | 2018-11-15 | 450 | Fision Home | In Sales Phase | Roger Bartlett |  |  |  | 10700 City Center Blvd Pembroke Pines, Florida 33025 | New Construction | Pembroke Falls - NEW ASR9006 - MDF and fiber pending! | ASR9006 | Pembroke Pines City Center | Yes | ALU | 4 | G-241G-A | Pending PCN
| Harbour Oaks |  | Need platform assignment and where fed from. 10/10 - Replace 4x10s in Slot 1 and 2 with 8x10s to get free TenGig ports for ALU Chassis; waiting chris to let us know about buffer, AC and Power |  | 2018-11-15 | 317 |  | In Sales Phase |  |  |  |  | 2500 San Pietro Circle West Palm Beach, Florida, United States | Conversion/OverBuild | FL_LANDMARK_MDFFL001_RT001 [10.63.255.26] | ASR920 | Harbour Oaks | [8 empty] | 1-Dic-2018
| Modera Edgewater | Upcoming |  |  | 2018-11-26 | 297 | Fision Home | In Sales Phase |  |  |  |  | 455 NE 24th Street, Miami, Florida, 33137 | New Construction |  |  |  |  | ALU
| Bristol, The | Upcoming | 10/11 - MDF ASR 920 switch is online and accessible [10.57.96.35]. 10/12 - Per Ewan, Feed splicing complete.....10 fibers @Bristol PT1-10.....green 3 meter jumpers ok. MDF switch ASR-920 already patch to Fibers 5,6,7&8.. Leaving 1-4, 7&8.. @ Whitney H.E. Rack far right, very top, Old Black PP Blue Bulk head, Middle of panel, PT 1-10 3 meter jumpers ok. Total distance is 6,458’ @ 1db loss. |  | 2018-12-01 | 81 | Fision Home | Received | Donald Rahmer |  |  | WPB | 1100 S Flagler Drive, West Palm Beach, FL 33401 | New Construction | whitney [ 1.4km] Lifelines needed in Jan 2018. Getting tough getting into Whitney. Should look at adding router in area soon | ASR920 | Bristol, The | No | ALU | 1 | ALU G-241G-A | Pending PCN | N
| Delray Place | Upcoming | now starting to build |  | 2018-12-01 | 76 | Fision Home | Received | Donald Rahmer |  |  | WPB | 111 SE 1st Ave Delray Beach, FL 33483 | Conversion/OverBuild | NI: BY&RC and Casa Costa | ASR9006 | Delray Place | No | ALU | 1 | G-240G-A
| Bentley Bay | Upcoming |  |  | 2018-12-01 | 168 | Fision Home | In Sales Phase |  |  |  | MIAMI | 520 &amp; 540 West Avenue Miami Beach, Florida, 33139 United States | Conversion/OverBuild |  |  | Bentley Bay | Pending PCN | ALU | 2 | I-240G-B | Yes
| Sole Mia - Phase 1 [2 apt towers, east and west] | Upcoming | node insertion feeding from Marina Palms. On 10.22 Joia reported the MDF is ready for racks. Per Chris W. it will take 2 - 3 weeks. Joia asks for 2 weeks to certify on 11/16 |  | 2018-12-01 | 394 | Fision Home | Pending | John Cleary |  |  | MIAMI | Biscayne Landing North Miami, Florida 33181 | New Construction | N.I. from Marina Palms FL-MARINA-PALMS-FLR01-MDF-RTR01 [10.63.255.62] and ? | ASR9006 | Sole Mia | No | ALU | 4 | G-240G-A | Yes
| Nexus Doraville | Upcoming | not breaking ground until END OD Q1 2018. fw life lifes: |  | 2018-12-01 | 504 | Fision Home | Received | Miguel Castillo |  | Lynn | GA | 5597 Buford Hwy Doraville, Georgia 30340 | New Construction | Doraville MDF |  | New Construction | No | ZTE | 5 | F680 | No
| The Falls of Inverrary | Upcoming |  |  | 2018-12-01 | 750 | Fision Home | In Sales Phase |  |  |  |  | 5961 N Falls Cir Dr Fort Lauderdale, Florida, 33311 United States | Conversion/OverBuild |  |  | The Falls of Inverrary |  | ALU | 8 | I-241G-B | Yes
| Miami Beach Convention Center | Ongoing | 10/11 - Per Michael Prosser (customer), BGP is Up. Luis Contreras confirmed this on our end as well. | MR Cert | 2018-12-15 | 1 | Fision Work | Pending |  | Guillermo | LC/Thomas | MIAMI | 1900 Washington Ave, Miami Beach, FL 33139 | Hand-Off | NOTA & FB [2X10G EACH] | ASR9006 [2] | NA | No | SE | 0 | NA | No | 2018-08-24 | NA | 2018-08-31 | 2018-09-07 | 9/24/2018 - Pending north and South MDF
| Vantage | Upcoming |  |  | 2018-12-15 | 150 | Fision Home | Pending | Donald Rahmer |  |  | BROW | 3505 W Atlantic Blvd Pompano Beach, Florida | New Construction
| Westlake | LOST |  |  | 2018-12-15 | 350 | Fision Home | LOST | Donald Rahmer |  |  |  |  | Conversion/OverBuild |  |  |  |  | ALU |  | I-221E-A
| Reflection Key Condominium | Upcoming | Start installs 1/7. So need to certify 1/4 or before - 12/19. Send equipment first week in December. |  | 2018-12-19 | 174 | Fision Home | Received | Pete Ferreira |  | Edward | SWFL | 14830 Reflection Key Cir., Ft Myers, FL 33907 | Conversion/OverBuild | Venetian Pointe RTR | WS-2960 | Reflection Keys Cons | Yes | ALU | 2 | G-241G-A | Yes |  | MFBREAK-1534 (30006621001)
| Hyde Beach House CONDO |  |  |  | 2019-01-01 | 397 | Fision Home | Pending | Ralph?? Transferred to Ralph team |  |  | BROW | 4000 S Ocean Dr Hollywood, Florida, 333019 United States | New Construction | Hyde Resort - need additional 10G modules | ASR920 | Hyde Beach House CONDO |  | ALU |  | G-240G-A
| Alta Flagler Village | Upcoming |  |  | 2019-01-01 | 208 | Fision Home | In Sales Phase |  |  |  |  | 421 NE 6th Street, Fort Lauderdale, Florida | New Construction | Church - 3km | ASR920 | Alta Flagler Village | ? | ALU | 2 | G-241G-B
| Boynton Atrium | Upcoming |  |  | 2019-01-01 | 142 | Fision Home | Pending
| Cassa Grove | Upcoming |  |  | 2019-01-01 | 122 | Fision Home | In Sales Phase | TBD |  |  |  | 2900 SW 28th Lane Miami, Florida, 33131 United States | New Construction |  |  |  |  | ALU | 3 | G-240G-A
| Midtown Miami 6 | Upcoming |  |  | 2019-01-01 | 447 | Fision Home | Pending |  |  |  |  | 3100 block of Northeast First Avenue Miami, Florida
| Tributary Media Room Conversion | Upcoming | Pending Pre Budget |  | 2019-01-01 | 397 | Fision Home | In Sales Phase | Miguel Castillo |  |  |  | 3295 Darby Drive Douglasville, GA 30135 |  | Pending |  | Pending
| Grand Central | Upcoming |  |  | 2019-01-10 | 281 | Fision Home |  | Pete Ferreira |  |  |  | 4944 S Cleveland Ave Ft Myers, Florida 33907 |  | NI: Synergy and Rose Garden [temp MDF until permanent is built out] . 5 commercial units. | ASR9006 | Grand Central | No | ALU | 3 | G-241G-A | Yes
| Town Commons | Upcoming |  |  | 2019-01-10 | 132 | Fision Home | Received | [5 empty] | New Construction |  |  | Town Commons | Pending PCN | ALU | 2 | G-241G-A | Pending PCN
| Solera at Kendall West | Upcoming | Per Joia, 10.02, the MR Cert moved to 10/20/18 from Nov/15. 10/9 - Per Josh, OLT has been configured and ready to be shipped [NETENGGPON-371 ticket]. |  | 2019-01-15 | 378 | Fision Home | Received | Eddie Miranda |  | Keith Brown/ Josh [NETENGGPON-371] | NFL | 1462 Solera Terrace, Jacksonville, FL 32211 | New Construction | Jacksonville Ring -LOOK INTO! | ASR9006 | Solera at Kendall West | No | NOKIA | 4 | G-240G-A |  | 2018-10-02 | MFBREAK-1469 | OLT: 10/9/2018, RTR: ?
| Brickell Flat Iron | Upcoming |  |  | 2019-01-15 | 550 | Fision Home | In Sales Phase | John Cleary |  | Pending | MIAMI | 1001 South Miami Avenue, Miami, FL 33130 | New Construction | BCC East Tower |  | Brickell Flat Iron | No | ALU |  | G-240G-A
| Island Terrace | Upcoming |  |  | 2019-01-15 | 139 | Fision Home | In Sales Phase |  |  |  | MIAMI | 5 Island Av. Miami Beach, Florida, 33139 United States | Conversion/OverBuild |  |  |  | No | ALU | 2 | G-240G-A | Yes
| 3030 North Ocean | Upcoming |  |  | 2019-01-15 | 24 | Fision Home | In Sales Phase |  |  |  | BROW | 3030 N Ocean Boulevard, Fort Lauderdale Beach, FL 33308 | New Construction | Berkley South | ASR920 | Auberge- Fort Lauderdale | Yes | ALU | 1 | G-241G-A | Yes
| Sutton Place | Upcoming | Start installs 1/31. |  | 2019-01-15 | 76 | Fision Home | In Sales Phase | Matt Kick |  |  |  | 2778 South Ocean ave Palm Beach, Florida, 33480 United States | Conversion/OverBuild | 10/9 Tues launch call - Regency? |  | Regency of Palm Beach | No | ALU | 1 | G-241G-A
| Eastpointe HOA | Upcoming | On 10.03, Cathy V provided a launch summary |  | 2019-02-01 | 874 | Fision Home | In Sales Phase | Matthew Kick |  |  | WPB | 13560 Eastpointe Blvd Palm Beach Gardens, Florida, 33418 United States | Conversion/OverBuild | timeline needed |  | Eastpoint HOA [2] |  | ALU
| Jensen Beach Golf & Country Club | Upcoming |  |  | 2019-02-01 | 745 | Fision Home | Pending | TBD |  |  | WPB | 3735 NW Pin Oak Dr. Jensen Beach, Florida, 34957 United States | Conversion/OverBuild | Circuit? Polled Matt - waiting on feedback. | ASR9006 | Jensen Beach Golf & Country Club | Pending PCN | ALU | 7 | G-241G-A | Pending PCN
| Armani Casa Sunny Isles | Upcoming |  |  | 2019-02-01 | 308 | Fision Home | In Sales Phase | Eric Hart |  | Pending |  | 10 Northeast 39th Street, Miami, FL 33137 - or- 18325 Collins Ave, Sunny Isles Beach, FL 33160 | New Construction | Aqualina |  | Armani Casa Sunny Isles |  | ALU |  | I-241G-B | Yes
| Dune Walk by the Ocean | LOST |  |  | 2019-02-01 | 108 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 7380 S Ocean Dr Jensen Beach, Florida, 34957 United States | Conversion/OverBuild | Circuit- Pending contract signature to order circuit. | ASR9006 | Dune Walk by the Ocean | Pending PCN | ALU |  | G-241G-A | Pending PCN
| Parkside Estero Grande | Upcoming |  |  | 2019-02-01 | 198 | Fision Home | Pending
| Reflection Isles | Upcoming |  |  | 2019-02-01 | 533 | Fision Home | Pending | Pete Ferreira |  |  |  | Maybe Leg | Conversion/OverBuild
| Ritz Carlton Residences | Upcoming |  |  | 2019-02-01 | 212 | Fision Home | Pending | Roger Bartlett |  |  |  | 15701 Collins Avenue Sunny Isles, Florida 33160 | New Construction | Jade Signature | ASR920 | Ritz Carlton Residences | No | ALU
| Eviva Yards (The Assembly) | ON-HOLD | Per Joia, on 10.02, the MR Cert moved to Mar/1/2019 |  | 2019-03-01 | 390 | Fision Home | In Sales Phase | Miguel Castillo |  | Lynn | GA | Lauderdale by the Sea, FL 33308 |  | Plaza Midtown |  | Eviva Yards (The Assembly) | Yes? Joia to confirm | ALU | 4 | G-241G-A | Yes
| The Line (aka Dadeland Apartments) | Upcoming |  |  | 2019-03-19 | 416 | Fision Home | In Sales Phase |  |  |  |  | SW 70th Avenue & SW 85th St Miami, Florida 33143
| San Marco | Upcoming |  |  | 2019-04-01 | 192 | Fision Home | In Sales Phase | Victor Martinez |  |  | WPB | 7251 Lugano Drive Boynton Beach, Florida, 33437 United States | Conversion/OverBuild | CLOSE TO STARLIGHT COVE |  |  |  | ALU |  | G-241G-A
| Las Olas River House | Upcoming |  |  | 2019-04-01 | TBD | Fision Home | In Sales Phase |  |  |  |  | 333 N. New River Drive E Fort Lauderdale, FL 33301
| Tivoli Reserve | Upcoming |  |  | 2019-05-01 | 220 | Fision Home | Pending |  |  |  | WPB | 11045 Via Sorento Boynton Beach, Florida, 33437 United States | Conversion/OverBuild
| Barclay Condominium | Certified | 10/9 No PM assigned yet. Will start soon. |  | 2019-05-01 | 210 | Fision Home | In Sales Phase | Chris Smiley |  |  | WPB | 3546 South Ocean Blvd, Palm Beach, FL 33480 | Conversion/OverBuild | 3200 Inc | ASR920 | 3200 Inc | No |  | 2 | F668 | Pending PCN
| Aurora Condo | Upcoming |  |  | 2019-05-15 | 61 | Fision Home | In Sales Phase |  |  |  |  | 17550 Collins Ave, Sunny Isles Beach, FL 33160 | New Construction | Aqualina | ASR920 | Aurora Condo
| Somerby of Mt. Pleasant | Upcoming |  |  | 2019-05-31 | 226 | Fision Home | Pending |  |  |  |  | 3100 Tradition Drive, Mount Pleasant, SC 29466 | Upgrade |  |  |  |  | ALU |  | G-241G-A
| Art Plaza |  |  |  | 2019-06-01 | 667 | Fision Encore
| Pinnacle Condo | Upcoming |  |  | 2019-06-01 | 115 | Fision Home | Pending | Jorge Palaez
| Transit Village | Upcoming |  |  | 2019-07-01 | 408 | Fision Home | In Sales Phase |  |  |  |  | 150 Clearwater Drive
| 87 Park | Upcoming |  |  | 2019-08-01 | 68 | Fision Home | In Sales Phase | Pending |  | Pending |  | 8701 Collins Ave, Surfside FL 33154 | New Construction | TBD |  | TBD
| 16000 Pines Market (Post Office) | Upcoming |  |  | 2019-08-15 | 122 | Fision Home | In Sales Phase | John Cobb |  |  | BROW | 16000 Pines Blvd Pembroke Pines, FL 33082 | New Construction | Town of Pembroke Pines | ASR920 | 16000 Pines Market (Post Office) | Pending PCN | ALU | 3 | G-241G-A | Pending PCN
| Sage | Upcoming |  |  | 2019-09-01 | 166 | Fision Encore | In Sales Phase | Tony Robbins |  |  |  |  | New Construction | 10G circuit | ASR9006
| Tamarac Village Apartments | Upcoming |  |  | 2019-10-01 | 402 | Fision Home | Received | Donald Rahmer |  |  |  | 9335 W. Commercial Blvd., 33351 | New Construction | NI: Bella Vista (20km) and Crystal Riv (25km). Boca woods is too far, 40km. | ASR9006 | Tamarac Village Apartments | No | ALU |  | G-240G-A
| Tower 155 |  |  |  | 2019-11-01 | 128 | Fision Home | Pending | Donald Rahmer
| Parco Mare | Upcoming |  |  | 2019-11-15 | 237 | Fision Home | In Sales Phase | John Cleary |  |  | BROW | 700 E Dania Beach Blvd, 33004 | New Construction |  |  |  | No | ZTE |  | F680
| Vista Bay Harbor | Upcoming |  |  | 2019-12-01 | 11 | Fision Home | In Sales Phase | Roger Bartlett |  | Lik/Josh | MIAMI | 9290 West Bay Harbor Drive | New Construction | St Regis ASR [OLT] and Sereno [COA Services] | WS-2960 | Bay Harbor Island [Housed at Sereno MDF] | No | ALU | 1 | G-240G-A | No
| Turnberry Ocean Club | Upcoming |  |  | 2020-01-01 | 154 | Fision Home | In Sales Phase |  |  |  |  | 215 185th St, Sunny Isles Beach, FL 33160
| 57 Ocean |  |  |  | 2020-05-01 | 99 | Fision Home | In Sales Phase |  |  |  |  | 5775 Collins Ave, Miami Beach,Florida 33140 |  | St Regis [low on interfaces] | ASR920 | 57 Ocean
| Estates at Aqualina | Upcoming |  |  | 2020-07-01 | 252 | Fision Home | In Sales Phase |  |  |  |  | 17885 Collins Avenue Sunny Isles, Florida 33160
| Summerhill | Upcoming |  |  | 2022-01-01 | 96 | Fision Home | In Sales Phase |  |  |  |  | 2640 S Bayshore Drive, Miami, FL 33133 |  | Grove at Grand Bay?? |  |  |  | ZTE
| Oasis Park Square Doral | Upcoming |  |  | 2023-01-01 | 280 | Fision Home | Pending
| Mondrian South Beach | Upcoming |  |  | 11/1/2018??? | 350 | Fision Home | In Sales Phase |  |  |  | MIAMI | 1100 West Avenue, Miami Beach, FL 33139 | Conversion/OverBuild |  |  | Mondrian South Beach | No | ALU |  | G-240G-A
| Atlantis Reserve ALF (added 9/28/18) |  |  |  | 15/10/2019 | 220 | Fision Home | In Sales Phase | TBD |  | TBD | WPB | Dow Lane &amp; S Military Trail Atlantis, Florida, 33463 United States | New Construction
| Metropica Towers (Phase 2) (Rush) | Upcoming | Per Joia, almost ready to go. Rush. |  | 30-Oct-2018 (RM) | 400 | Fision Home | Pending |  |  |  |  | 800 NW 136th Ave sunrise, Florida, 33323 United States |  | TAO | [8 empty] | MFBREAK-1553
| NeoVita Doral South? [Terra Acon Doral Palm] | Upcoming |  |  | cea | 80 | Fision Home | Pending | Donald Rahmer |  |  |  | 6801 NW 103rd Ave Doral, FL 33178 | New Construction | ? LIVE? | ASR902
| Clarity Pointe | LOST |  |  | LOST | 215 | Fision Home | LOST | Eric Hart |  |  |  | 1010 Falkner Terrace, Palm Beach Gardens, FL, 33418 | New Construction | Martinique at Abacoa | ASR920 | Tuscany: Chassis is filled after this | No | ALU | 2 | G-241G-B | Yes
| Hidden Hallow | Upcoming |  |  | pending osp timeline | 46 | Fision Home | In Sales Phase |  |  |  | WPB | 149 Hidden Hollow Dr Palm Beach Gardens, Florida, 33418 United States | Conversion/OverBuild | OSP Pending - Not in OSP queue | Pending OSP | Hidden Hallow | Pending PCN | ALU | 1 | G-241G-A | Yes
| Water Tower Commons | On-Hold |  |  | pending osp timeline | 360 | Fision Home | In Sales Phase | Donald Rahmer |  |  | WPB | 1199 W. Lantana Road Lantana, FL 33462 | New Construction | NI |  | Water Tower Commons | No |  |  |  | Yes
| Toscano at Dadeland | Upcoming |  |  | pending osp timeline | 396 | Fision Home | In Sales Phase |  |  |  | Mimai | 7350 SW 89th Street Miami, Florida, 33156 United States | Conversion/OverBuild | Not in OSP |  | Toscano at Dadeland |  |  |  | G-241G-A
| Embassy Park | Upcoming |  |  | TBD | 84 | Fision Home | In Sales Phase |  |  |  | WPB | 1700 Embassy Dr west palm beach, Florida, 33401 United States | Conversion/OverBuild
| Edgewater Condos (added 9/28/18) |  | Per Joia 10.02, MDF is completed |  | TBD | 352 | Fision Home | In Sales Phase | TBD |  | TBD |  | 8931 Wiles Rd Coral Springs, Florida, 33067 United States | Conversion/OverBuild
| All Aboard Florida | Upcoming |  |  |  | 800 |  | In Sales Phase | Pending |  | Pending | WPB | 3800 NW 25th St Miami, Florida 33128 | New Construction | TBD |  | TBD
| Bears Club | LOST |  |  |  | 85 | Fision Home | In Sales Phase |  |  |  | WPB | 103 Bears Club Drive Jupiter, Florida, 33477 United States | Conversion/OverBuild | Frenchman's Creek |  | Bears Club |  | ALU
| Magnolia Lakes |  |  |  |  | 478 | Fision Home | In Sales Phase |  |  |  | WPB | 101 NW Magnolia Lakes BLVD, Port St. Lucike, FL 34986 | Conversion/OverBuild
| Newport Isles |  |  |  |  | 764 | Fision Home | In Sales Phase |  |  |  | WPB | 1856 Newport Isles Blvd Port Saint Lucie, Florida, 34953 United States | Conversion/OverBuild | Not in OSP
| Smith Farm |  |  |  |  | 1242 | Fision Home | In Sales Phase |  |  |  | WPB | 6595 Smith Farm Blvd Lake Worth, Florida, 33467 United States | Conversion/OverBuild | Not in OSP |  |  | No | ALU | G-240G-A
| The Isles in Palm Beach Gardens | Upcoming |  |  |  | 341 | Fision Home | In Sales Phase |  |  |  | WPB | 1500 Victoria Falls Blvd Palm Beach Gardens, Florida, 33410 United States | Conversion/OverBuild |  |  |  | Pending PCN | ALU |  | G-241G-B | Yes
| Village at Abacoa | Upcoming |  |  |  | 413 | Fision Home | In Sales Phase |  |  |  | WPB | 4798 Central Blvd Jupiter, Florida, 33458 United States | Conversion/OverBuild |  |  |  |  | ALU
| Prairie View A&M - University View |  |  |  |  | 96 | Fision U | In Sales Phase | Tony Robbins |  |  | TEXAS | 240 EM Norris St Prairie View, Texas, 77446 United States | Conversion/OverBuild
| Bordeaux Club, Inc. | Upcoming |  |  |  | 64 | Fision Home | In Sales Phase | Pete Ferreira |  |  | SWFL | 2900 Gulf Shore Blvd. N. Naples, Florida, 34103 United States | Upgrade
| Shadow Wood Preserve |  |  |  |  | 293 | Fision Home | In Sales Phase |  |  |  | SWFL | 6900 Shadow Creek Blvd. Ft. Myers, Florida, 33908 United States | Conversion/OverBuild | Not in OSP |  | Shadow Wood Preserve | Pending PCN | ALU | 4 | G-241G-A | Yes
| Wexford on the Green | Upcoming |  |  |  | 123 | Fision Home | Pending | Pete Ferreira |  |  | SWFL | 173 Braemar ave. Venice, Florida, 34293 United States | Upgrade
| Windsor Falls / Deerfoot Point (added 9/28/18) |  | (10.02 - MDF gear sent to Orlando warehouse - Keith to check) |  |  | 94 | Fision Home | In Sales Phase | Eddie Miranda |  | TBD | NFL | 7162 Deerfoot Point Circle, Jacksonville, Florida 32256 | Upgrade
| Green Gate Apartments | Upcoming |  |  |  | 172 | Fision Home | Pending |  |  |  | NFL
| Towne Club St Augustine | Upcoming | Pending Agreement. I Will reach out to |  |  | 243 | Fision Home | In Sales Phase | Eddie Miranda |  | Keith Brown | NFL | Morgan’s Treasure Rd and County Rd 214 |  | 3rd Party Circuit |  |  | Yes
| Osprey Branch |  | (10.02 - MDF gear sent to Orlando warehouse - Keith to check) |  |  | 120 | [5 empty] | NFL | 9439 Osprey Branch Trail, Jacksonville, Florida, 32257 | Upgrade |  | ASR9006 |  | No | ALU | 8
| Biltmore II | Upcoming |  |  |  | 232 | Fision Home | LOST |  |  |  | MIAMI | 600 Biltmore Way Coral Gables, Florida 33134 | Conversion/OverBuild |  |  |  | Yes | ZTE |  | F668 | [5 empty] | Carrilon MDF
| Cambria Suites Brickell FIBER BUILD | Upcoming |  |  |  | 0 | Fision Encore | Received | Elena/Chris to Buildout |  | NA | MIAMI | 165 SW 12 St Miami FL 33130 | Conversion/OverBuild | NA |  | NA | NA | NA |  | NA | NA |  |  |  |  | Back left rack middle bulkhead (Bulkhead F) top four ports 1-4.
| Fifty Six-Sixty | Upcoming |  |  |  | 90 | Fision Home | In Sales Phase |  |  |  | MIAMI | 5660 Collins Ave Miami Beach, Florida, 33140 United States | Conversion/OverBuild | Not in OSP |  |  | No | ALU | 1 | G-240G-A | Pending PCN |  |  |  |  | Both sides have been labeled with orange tape.
| Miami River Landing / River Landing | Upcoming |  |  |  | 526 | Fision Home | In Sales Phase |  |  |  | MIAMI | 1500 NW N. River Dr. Miami, Florida | New Construction | Modern Miami/Urban Club |  | Somerset Tower? | Pending PCN | ALU | 5 | G-240G-A
| South Beach Bayside II |  |  |  |  | 47 | Fision Home | In Sales Phase |  |  |  | MIAMI | 3025 Indian Creek, Miami Beach, FL | Conversion/OverBuild
| Atria at North Point (previously known as Somerby of Alpharetta) | Upcoming |  |  |  | 284 | [5 empty] | GA | "100 Somerby Dr Alpharetta, Georgia 30009" | Upgrade | Circuit will need to be upgraded! Look into. | ASR9006?? Get approval? In budget? | Atria at North Point | Yes | ALU | 3 | G-241G-A
| Avalon Medical Facility | Upcoming |  |  |  | TBD | Fision Work | Pending | Miguel Castillo |  | Lynn | GA |  | New Construction | Pending |  | Pending
| Creekside Village Parcel B | Upcoming | 200 Independent Living Units - Senior Living, dev have not gotten $ for this |  |  | 200 | Fision Encore | Received | Miguel Castillo |  | Lynn | GA | 4838 S Cobb Drive Smyrna, Georgia 30080 | New Construction | NI: Smyner & Avalon |  | Creekside Village | Yes | ZTE |  | F668
| Integral Townhomes (PH-1) | Upcoming |  |  |  | 2 | Fision Home | In Sales Phase | Miguel Castillo |  | Lynn | GA | 1) 556 Centennial Lane, NW, Atlanta, GA 30313; 2) 537 Centennial Lane NW, Atlanta, GA 30313 | New Construction | 1G Off-Net Circuit: 55M ETC: 12-May 2018 |  | NA |  | SE
| 2000 S Ocean | Upcoming |  |  |  | 64 | Fision Home | In Sales Phase | Donald Rahmer |  |  | BROW | 2000 S. Ocean Drive, Hallandale Beach, FL 33009 | New Construction | Hyde Resort/ Trump Hollywood | ASR920 | 2000 S Ocean | Yes | ALU | 1 | G-241G-A |  | N
| Rice Hope |  |  |  |  | 91 | Fision Home | In Sales Phase |  |  | Lynn | ATL |  | New Construction | Circuit 10/18/2018
| Rice Hope PHASE 2 | Upcoming |  |  |  | 40 | Fision Home | In Sales Phase |  |  | Lynn | ATL | "100 Lakeside Boulevard Port Wentworth, GA 31407" | New Construction | within rice hope - tellabs |  | Ardmore at Rice Hope???? | No |  |  |  | No
| 44 Milton | Upcoming |  |  |  |  | Fision Work | In Sales Phase | Miguel Castillo |  | Lynn
| 610 Clematis | Upcoming | Part of ButtonWood Conversion? MR ? |  |  | 246 | Fision Home | Received | TBD |  | NA |  | 610 Clematis West Palm Beach, FL 33401 | Upgrade | 610 Clematis |  | 610 Clematis?? |  | SE |  | NA
| 811 Peachtree | Upcoming |  |  |  | 400 | Fision Home | In Sales Phase | Miguel Castillo |  | Lynn/?? |  |  | New Construction | TBD |  | TBD |  |  |  | TBD
| Alhambra Cove | Upcoming |  |  |  | 240 | Fision Home | Pending | Pending |  | Pending |  | 1560 NW 119th Street Miami, FL 33167 | Upgrade | Off Net Circuit |  | TBD
| Allegro Condo |  |  |  |  | 76 | Fision Home | In Sales Phase | Pete Ferreira
| Auberge - Miami | Upcoming | Go Live 12/1/2018, Not Broken Gound |  |  | 1200 | Fision Home | In Sales Phase | John Cleary |  | Pending |  | 1440 Biscayne Blvd. Miami, FL | New Construction | Quantum or 900 ? Wilson to confirm |  | TBD | No
| Avalon [Haven] |  |  |  |  | 250 | Fision Home | Received | Miguel Castillo |  | Edward/Jose |  | 2800 Old Milton Pkwy Alpharetta, GA 30009 | [5 empty] | ZTE
| Avalon 8000 building Retail/Office | Upcoming | Networking gear shipped to facilitate life lines |  |  | TBD | Fision Work | Pending | Miguel Castillo |  | Lynn |  |  | New Construction | Avalon - ASR9006 - 10.110.255.26 |  | NA |  | SE |  | NA
| Avalon 9000 Hotel | Upcoming | Ralph |  |  | TBD | Fision Work | Pending | Miguel Castillo |  | Lynn |  |  | New Construction | Pending |  | TBD |  |  |  | TBD
| Avalon Convention Center | Upcoming |  |  |  | TBD | Fision Work | Pending | Miguel Castillo |  | Lynn |  |  | New Construction | Pending |  | Pending |  |  |  | TBD
| Babcock Ranch | Upcoming |  |  |  | 1000 | Fision Home | In Sales Phase | [6 empty] | TBD |  | TBD
| Balmoral Haines City | Upcoming |  |  |  | 240 | Fision Home | Pending |  |  |  |  | 124 Kenny Blvd. Haines City, Florida 33844 |  | TBD |  | TBD
| Boca Bath & Tennis | Upcoming |  |  |  | 243 | Fision Home | LOST |  |  |  |  | 2801 N. Military Trail, Boca Raton, FL
| Boca Glades |  |  |  |  | 385 | Fision Home
| Boca Isles South | Upcoming |  |  |  | 412 | Fision Home | Received |  |  |  |  | 19951 Ocean Key Drive Boca Raton, FL 33498 | [5 empty] | ZTE |  | F668
| Boca Towers | Upcoming |  |  |  | 272 | Fision Home | LOST |  |  |  |  | 2121 N Ocean Blvd, Boca Raton, FL 33431
| Brentwood Community Inc. | Upcoming |  |  |  | 72 | Fision Home | [5 empty] | 8750 Brentwood Blvd, 33434 |  | osp ?
| Cassa Grove | Upcoming |  |  |  | 122 | Fision Home | In Sales Phase |  |  |  |  | 2900 SW 28th Lane Miami, Florida 33131 | New Construction | Grove at Grand Bay | ASR920 | Grove at Grand Bay
| Centennial Park Apts | On-Hold | Signed |  |  | 2 | Fision Home | Pending | [6 empty] | Pending |  | Pending
| Chalfonte |  |  |  |  | 378 | Fision Home | LOST |  |  |  |  | 500 S Ocean Blvd, Boca Raton, FL 33432
| Cloister del Mar | Upcoming |  |  |  | 96 | Fision Home | In Sales Phase |  |  |  |  | 1180 South Ocean Blvd , Boca Raton, FL 33432 | Conversion/OverBuild
| Colonnade Building, The | Upcoming |  |  |  | 570 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 7240 SW 82nd Street Miami, FL 33143
| Coral Plaza | Not Approved |  |  |  | 183 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 3500 Coral Way Miami, FL 33145 | Upgrade | Not Approved
| Cortina | Upcoming | Heather to proide feedback |  |  | 450 | Fision Home | LOST | [5 empty] | New Construction | Start OSP AND Net |  | Cortina |  | ZTE
| Costa Hollywood (Hotel) | Upcoming |  |  |  | 310 | Fision Stay | LOST |  |  |  |  | 777 N Ocean Drive Hollywood, FL 33019 |  | TBD
| Courtyards at Boca | Not Approved |  |  |  | 200 | Fision Home | NOT Approved to Upgrade |  |  |  |  | Courtyard Run Boca Raton, FL 33433
| Doral Cay | Upcoming |  |  |  | 158 | Fision Home | Pending |  |  |  |  | Fort Lauderdale, FL 33304 | [5 empty] | ZTE
| Doral Commons | Upcoming |  |  |  | 35 | Fision Work | Received |  |  |  |  | Doral, FL | New Construction
| Dunham Marsh (PH-1) | Certified |  |  |  | 140 | Fision Home | Received | Miguel Castillo |  |  |  | 340 Sunbury Dr, Richmond Hill, GA 31324 | New Construction
| Dunham Marsh (PH-2) | Certified |  |  |  | 40 | Fision Home | Received | Miguel Castillo |  |  |  | 341 Sunbury Dr, Richmond Hill, GA 31324 | New Construction
| Dunham Marsh (PH-3) | Upcoming |  |  |  | 40 | Fision Home | In Sales Phase | Miguel Castillo |  | Lynn |  | 340 Sunbury Drive Richmond Hill, GA 31324 | New Construction |  |  |  | Yes
| Dunham Marsh (PH-4) | Upcoming |  |  |  | 28 | Fision Home
| Dunham Marsh (PH-7) | Upcoming |  |  |  | 53 | Fision Home
| Echo Brickell | Upcoming |  |  |  | 175 | Fision Home | In Sales Phase | [10 empty] | ALU |  | I-241G-B | Yes
| Estates at Stuart, The | Not Approved |  |  |  | 237 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 88 SE Hancock Street Stuart, FL 34994
| Flats at Mallard Creek | Upcoming |  |  |  | 131 | Fision Home | Pending | Miguel Castillo |  |  |  | 613 East Mallard Creek Church Rd. Charlotte, NC 28262 |  |  | ASR9006
| Fontainebleau Hotel 10G Handoff | Upcoming |  |  |  | 1 | Fision Stay | Pending | Juan Miranda | [5 empty] | NI: ??? |  | NA
| Gables Gate 2 | Upcoming |  |  |  | 224 | Fision Home | Pending |  |  |  |  | SW 67th Avenue/SW 19&20 Sts
| Gables Marquis | Upcoming |  |  |  | 177 | Fision Home | Received |  |  |  |  | 3232 Coral Way Miami, FL 33145
| Goldcoaster | Not Approved |  |  |  | 545 | Fision Home | Pending |  |  |  |  | 34850 SW 187th Avenue Homestead, FL 33034
| Golden Lakes Village | Not Approved |  |  |  | 1088 | Fision Home | Pending |  |  |  |  | 1700 Golde Lakes Blvd. West Palm Beach, FL 33411
| Gran Paradiso PH 1/3 |  |  |  |  | 800 | Fision Home |  | Eddie Miranda |  |  |  | 20061 Galleria Blvd Venice, Florida 34293 |  | Gran Paradiso [via 10G Offnet] |  | Gran Paradiso Chassis 1 | Yes | ZTE | 8 | F668
| Gran Paradiso PH 2/3 |  |  |  |  | 800 | Fision Home |  | Eddie Miranda |  |  |  | 20061 Galleria Blvd Venice, Florida 34293 |  | Gran Paradiso [via 10G Offnet] |  | Gran Paradiso Chassis 2 | Yes | ZTE | 8 | F668
| Gran Paradiso PH 3/3 |  |  |  |  | 399 | Fision Home |  | Eddie Miranda |  |  |  | 20061 Galleria Blvd Venice, Florida 34293 |  | Gran Paradiso [via 10G Offnet] |  | Gran Paradiso Chassis 3 | Yes | ZTE | 5 | F668
| Gran Paradiso Villas PH2 |  |  |  |  | 825 | Fision Home |  | Eddie Miranda |  |  |  | 20061 Galleria Blvd Venice, Florida 34293 |  | 10G Wavelenght to? |  |  | Yes | ZTE |  | F668
| Gran Paradiso-Townhome |  |  |  |  | 116 | Fision Home |  | Eddie Miranda |  |  |  | 20061 Galleria Blvd Venice, Florida 34293 | [5 empty] | ALU
| Gran Paradiso-Trac Home |  |  |  |  | 106 | [6 empty] | 20061 Galleria Blvd Venice, Florida 34293 | [5 empty] | ALU
| Gulls Cove Phase 2 | Upcoming | Carroll treasure is working |  |  | 107 | Fision Home | Pending | Tony Robbins |  |  |  | 201 Marin Blvd Jersey City, NJ 07302
| Hampton Inn BRICKELL | Upcoming
| Harbor House |  |  |  |  | 476
| Havana Club (formerly LeJeune Apts ) | Upcoming |  |  |  | 140 | Fision Home | In Sales Phase |  |  |  |  | 10 NW 42nd Avenue Miami, Florida 33126 | New Construction | [6 empty] | F668? | No
| Heron Isles-PH 2 |  |  |  |  | 510 | Fision Home | In Sales Phase | Eddie Miranda |  |  |  | 96059 HERON ISLE PKWY, YULEE, FL 32097
| Heron Isles-PH 3 |  |  |  |  | 166 | Fision Home | In Sales Phase | Eddie Miranda |  |  |  | 96059 HERON ISLE PKWY, YULEE, FL 32097
| High Pointe Condo 1 | Not Approved |  |  |  | 259 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 204 Manatee Lane Fort Pierce, FL 34982
| High Pointe Condo 2 | Not Approved |  |  |  | 267 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 204 Manatee Lane Fort Pierce, FL 34982
| Huntington Lakes |  |  |  |  | 2151 | Fision Home | In Sales Phase |  |  |  |  | 7355 Huntington Lane Delray Beach, FL 33446
| Hutchinson Island Club | Upcoming |  |  |  | 92 | Fision Home | Received |  |  |  |  | 10410 South Ocean Dr. Jensen Beach, Florida, 34957 United States | Conversion/OverBuild
| Indian Creek | [5 empty] | Fision Home |  | Pete Ferreira
| Integral SFH (PH-2) | On-Hold |  |  |  | 1 | Fision Work | Pending | Miguel Castillo |  | Lynn
| Island House Apartment |  |  |  |  | 132 | Fision Home | Pending |  |  |  |  | 200 Ocean Lane Dr. Key Biscayne, Florida, 33149 United States | Conversion/OverBuild |  |  | Commodore Club South |  | ALU |  | G-241G-A
| Isles of Waterway Village |  |  |  |  | 431
| Johnson Landing | Upcoming |  |  |  | 147 | Fision Home | In Sales Phase | Nieves Lopez |  |  |  | 9709 BITTER MELON DR, Angier, NC 27592 |  | 10G Circuit - check with Matt |  | Johnson Landing | Yes | ZTE | 2 | TBD
| Kellswater Bridge (PH 4) | Ongoing |  |  |  | 53 | Fision Home | In Sales Phase | Nieves Lopez |  |  |  | 3033 Keady Mill Loop, Kannapolis, NC 28081 | New Construction | Dish to home retail. |  |  | Yes | ZTE |  | F668 | Yes
| Kellswater Bridge (PH 5) | Upcoming |  |  |  | 38 | Fision Home | In Sales Phase | David Turek |  |  |  | 3033 Keady Mill Loop, Kannapolis, NC 28081 | New Construction | Dish to home retail. |  |  | Yes | ALU |  |  | Yes
| Kellswater Bridge (PH-2C) | Ongoing |  |  |  | 44 | Fision Home | In Sales Phase | Nieves Lopez |  |  |  | 3033 Keady Mill Loop, Kannapolis, NC 28081 | New Construction | Dish to home retail. |  |  | Yes | ZTE |  | F668 | Yes
| Kellswater Bridge (PH-3) | Upcoming |  |  |  | 202 | Fision Home | In Sales Phase | David Turek |  |  |  | 3033 Keady Mill Loop, Kannapolis, NC 28081 | Upgrade | Dish to home retail. |  |  | Yes | ALU |  |  | Yes
| Kings Manor | Not Approved |  |  |  | 308 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 12500 W State Rd 84 Davie, FL 33325 |  | Metropica
| L’Ambiance Beach |  |  |  |  | 124 | Fision Encore | LOST |  |  |  |  | 4240 Galt Ocean Drive Fort Lauderdale, Florida 33308
| Lakes at Savannahs, The | Not Approved |  |  |  | 243 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 1725 N. Lakefront Blvd. Ft. Pierce, FL 34982 | Upgrade
| Las Olas Beach Club | Not Approved |  |  |  | 148 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 101 S. Fort Lauderdale Beach Ft. Lauderdale, FL 33315
| Lauderdale One | Certified |  |  |  | 175 | Fision Home | Received | Bob Smith |  |  |  | 2401 E 65th Street Fort Lauderdale, FL 33308 |  | Laudedale One |  |  |  | SE
| Lausanna | Certified |  |  |  | 180 | Fision Home | Received | [8 empty] | Lausanne
| Legends Blvd |  |  |  |  | 1291 | Fision Home | Pending | Pete Ferreira | [5 empty] | Node Insertion
| Lexington Plantation - The Manors (PH 2) | Ongoing |  |  |  | 132 | Fision Home | Received | Nieves Lopez |  |  |  | 646 CENTENNIAL PKWY, Cameron, NC 28326 | [5 empty] | ALU
| Libery Cluster/Campus Project | Upcoming | Signed 9-2016 |  |  | TBD |  | In Sales Phase | [6 empty] | Pending |  | Pending
| Manor CityPlace Doral |  |  |  |  | 1200 | Fision Home | Received |  |  |  |  | 8465 NW 33rd Street Doral FL, 33122
| Mansions at Aqualina, The | On-Hold |  |  |  | 79 | Fision Home | NOT Approved to Upgrade | Roger Bartlett |  |  |  | 17749 Collins Ave, Sunny Isles Beach, FL 33160 | New Construction | Aqualina |  | Mansions at Aqualina, The | No |  |  | I-241G-B | Yes
| Miami Bay Club | Upcoming |  |  |  | 176 | Fision Home | In Sales Phase |  |  |  |  | 531/601 NE 39 St, Miami
| Midtown Miami 7 | Upcoming | [5 empty] | Pending
| Mission Bay Courtside Villas | Certified |  |  |  | 40 | Fision Home | Received |  |  |  |  | 1000 Holland Drive, Boca Raton, FL 33487
| Mizner Pointe | Upcoming |  |  |  | 372 | Fision Home | Received |  |  |  |  | 8290 Via Serena Boca Raton, Florida 33433
| Monarch in BAL Harbor | Upcoming |  |  |  | 1 | Fision Stay | LOST | Juan Miranda
| Moors, The | Upcoming |  |  |  | 1800 | Fision Home | In Sales Phase |  |  |  |  | 17321 NW 66 CT, 33015 | Conversion/OverBuild
| New River Yacht Club - Phase 1 | Certified | [10 empty] | 400 SW 1st Avenue Fort Lauderdale, FL
| New River Yacht Club - Phase 2 | Upcoming |  |  |  | 349 |  |  | John Cleary |  |  |  | 400 SW 1st Avenue Fort Lauderdale, FL
| Nirvana Condominium | LOST |  |  |  | 385 | Fision Home | LOST |  |  |  |  | 703 NE 63rd St. Miam, Fl 33138
| Notting Hill |  |  |  |  | 1 | Fision Work
| Notting Hill |  |  |  |  | 48 | Fision Home | In Sales Phase
| Oakbrook Village | Upcoming | Cathy emailed launch summary on 10.25.18 |  |  | 343 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 8200 SW 24th Street Pompano Beach, FL 33068
| Oasis Park Square at Doral | Upcoming |  |  |  |  | Fision Home | Pending |  |  |  |  | 3470 NW 82nd , Doral, FL 33122
| Oasis Tower | Certified |  |  |  | 190 | Fision Home | Received | Pete Ferreira |  |  |  | 3000 Oasis Grand Blvd., Fort Myers, FL 33916
| Oceana Key Biscayne | Upcoming |  |  |  | 154 | Fision Home | Pending |  |  |  |  | 350 Ocean Drive Key Biscayne FL, 33149 | New Construction |  |  |  |  | SE
| Old Town University Square | Upcoming |  |  |  | 143 | Fision U | Received | Tony Robbins |  |  |  | 500 Anne Preston Street, Prairie View, TX 77446
| One Brickell | Upcoming |  |  |  | 1430 | Fision Home | Pending |  |  |  |  | 444 Brickell Avenue Miami, FL 33131 | New Construction | BCC?
| One Park Grove |  |  |  |  | 72 | Fision Home | Pending |  |  |  |  | 2701 S Bayshore Dr, Miami, FL 33133
| One River Point |  |  |  |  | 350 | Fision Home | In Sales Phase |  |  |  |  | 24 SW 4th St, Miami, FL 33130
| Overlook Condo | Upcoming |  |  |  | 104 | Fision Home | LOST | [6 empty] | 90 days from Oct4th - Mid January
| Panorama Tower | Upcoming |  |  |  | 821 | Fision Home | Pending |  |  |  |  | 1101 Brickell Avenue Miami, FL 33131
| Paraiso Bay |  |  |  |  | 368 | [6 empty] | 600 NE 31st Street Miami, Florida, 33137 United States
| Paramount Bay SOW | Certified |  |  |  | 346 | Fision Home | Received | Bob Smith |  |  |  | 2020 Bayshore Drive Miami, FL 33137
| Paramount Fort Lauderdale | Upcoming |  |  |  | 95 | Fision Home | Pending |  |  |  |  | 700 S Atlantic Blvd, Fort Lauderdale, FL 33304
| Park Grove Tower 2 | Upcoming |  |  |  | 72 | Fision Home | In Sales Phase |  |  |  |  | 2701 S Bayshore Dr, Miami, FL 33133 | New Construction | Grove at Grand Bay - ASR9006 - 10.63.255. | ASR920 | Certified Under Park Grove (Tower 1, 2 & 3) | No | ZTE | 0 | F668 | No
| Park Grove Tower 3 (Club Residences ) | Certified |  |  |  | 132 | Fision Home | In Sales Phase |  |  |  |  | 2701 S Bayshore Dr, Miami, FL 33133 | New Construction | Grove at Grand Bay - ASR9006 - 10.63.255. | ASR920 | Certified Under Park Grove (Tower 1, 2 & 3) | No | ZTE | 0 | F668 | No
| Park Pointe |  |  |  |  | 488 | Fision Home | LOST |  |  |  |  | 3200 Jog Park Drive Greenacres, Florida 33467
| Park Terrace | Certified |  |  |  | 16 | Fision Home | Received | Ben Kester |  |  |  | 280 Park Terrace Boynton Beach, FL 33426 |  | Vizcaya Lakes - ASR9006 - 10.63.255.91 |  | Vizcaya Lakes |  | ZTE |  | F668
| Park Village - Add On |  |  |  |  | 145 | Fision Home | Pending | Miguel Castillo |  |  |  | 120 Park Village Dr, Canton GA 30114
| Parkway 400 | Upcoming | Pending Signed Agreement |  |  | TBD | Fision Work | Pending | [6 empty] | Pending |  | Pending
| Pembroke Pines City Center Garden Aparments |  |  |  |  | 387 | Fision Home | [18 empty] | Per Joia on 10.02, expect by the end of the year
| Plaza Midown Relocation | Certified |  |  |  | 0 | Fision Home
| Prairie View Phase 8 (Fision U) | Upcoming |  |  |  | 143 | Fision U | Pending | Tony Robbins |  |  |  | 500 Anne Preston St. Prairie View, TX 77446
| Preserve at Savannahs, The | Upcoming |  |  |  | 94 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 1725 N. Lakefront Blvd. Ft. Pierce, FL 34982
| Ranch Colony | Upcoming |  |  |  | 270 | Fision Home | Pending |  |  | Pending |  |  | New Construction
| Rancho | Upcoming |  |  |  | 1900 | Fision Home | Pending
| Related Group Atlanta/ Apogee Midtown | Upcoming |  |  |  | 390 | Fision Work | In Sales Phase | Miguel Castillo |  | Lynn |  | 22 14th St Atlanta, GA
| Residences of Riviera Palms, The | Upcoming |  |  |  | 248 | Fision Home | Pending |  |  |  |  | 3860 Lyons Road Pompano Beach, FL 33073
| Rice Hope Plantation | Upcoming |  |  |  | 494 | Fision Home | Pending | Miguel Castillo |  | Lynn |  | 100 Lakeside Boulevard Port Wentworth, GA 31407 |  |  |  | New Construction
| Richmond Park Phase 2 | Upcoming |  |  |  | 104 | Fision Home | Received | Pete Ferreira |  | Edward/Rolando |  | SE corner of Woodcrest Drive and Immokalee Rd. | New Construction | Vanderbilt |  | Richmond Park Phase 1 | Yes | ZTE |  | F668 | Yes
| Rise at Flagler Village | Upcoming |  |  |  | 348 | Fision Home | In Sales Phase |  |  |  |  | 411 NE 2nd Street Ft Lauderdale, Florida
| River Walk | Upcoming |  |  |  | 1230 | Fision Home | In Sales Phase |  |  |  |  | 1090 NW N River Drive Miami, Florida 33136 |  | TBD
| River X |  |  |  |  | 1200 |  | Pending
| San Remo | Not Approved |  |  |  | 185 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 1945 SW 60th Avenue Pompano Beach, FL 33068
| Sanctuary at Grand Oaks |  |  |  |  | 90 | Fision Home | Pending | David Turek |  |  |  | 1001 Ashley Garden Blvd Charleston, SC 29414
| Sanctuary at Grand Oaks PH 2 (The Landings) |  |  |  |  | 36 | Fision Home | Pending | Nieves Lopez |  |  |  | 1156 Bowman Rd, Charleston, SC 29464
| Sanctuary at Grand Oaks Townhomes |  |  |  |  | 110 | Fision Home | Pending | Nieves Lopez |  |  |  | 1126 Lango Avenue, Charleston, SC 29407
| Savannahs Condo, The | Not Approved |  |  |  | 211 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 1725 N. Lakefront Blvd. Ft. Pierce, FL 34982
| Sereno [Naples] |  |  |  |  | 64 | Fision Home | LOST | Pete Ferreira |  |  |  | Livingston Rd & Marsala Way Naples, Florida 34109
| Shalimar at Davie | Upcoming |  |  |  | 240 | Fision Home | Pending
| Sienna Reserve | Certified |  |  |  | 45 |  | In Sales Phase | Pete Ferreira |  |  |  | 14648 - 14750 Reserve Lane and 14682 - 14704 Reserve Place Naples, FL
| St. Andrews | Certified |  |  |  | 732 | Fision Home | Received | Wayde Webber |  | Edward/Jose |  | 17557 Claridge Oval West Boca Raton, FL 33496
| St. Tropez |  |  |  |  | 286 | Fision Home | Received |  |  |  |  | 150, 200, 250 Sunny Isles Blvd Sunny Isles, FL 33160
| Stadium Walk | Upcoming | Pending Pre Budget |  |  | 309 | Fision Work | Pending | [6 empty] | Pending |  | Pending
| Star Loft Data Upgrade | Upcoming |  |  |  | 50 | Fision Home | Received | Nerupa Imam |  |  |  | 700 NE 25th Street Miami, FL 33137 |  | Onyx -7606S - 10.63.255.15
| Stonebridge Golf and Country Club |  | On 10.03 Cathy V. ammended the summary |  |  | 398 | Fision Home | Received |  |  |  |  | 10343 Stonebridge Blvd. West Palm Beach, FL 33498
| Stratford Lakes | Upcoming |  |  |  | 448 | Fision Home | In Sales Phase | [9 empty] | Yes | ZTE |  | F680
| Summer Chase | Not Approved |  |  |  | 221 | Fision Home | Pending
| Summerwind Plantation (PH 2) | LOST |  |  |  | 46 | Fision Home | LOST | Nieves Lopez |  |  |  | Summerwind Plantation Dr, Garner, NC 27529
| Summerwind Plantation (PH 3) | LOST |  |  |  |  | Fision Encore | LOST | Nieves Lopez |  |  |  | Summerwind Plantation Dr, Garner, NC 27529
| Sun Valley | Certified |  |  |  |  | Fision Home | Received | Heather S |  |  |  | 9781 El Clair Ranch Road BOYNTON BEACH, FL 33437
| Sunshine Lakes | Upcoming |  |  |  | 208 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 10940 W 14th Avenue Miami, FL 33167
| Terra Nova | LOST
| Third Rail Studio | Upcoming |  |  |  | 1 | Fision Home | Pending |  |  |  |  | 5818 Peachtree Road, Atlanta, GA 30341 |  | Services needed?
| Towne Club | Upcoming |  |  |  | 127 | Fision Home | In Sales Phase |  |  |  |  | 6696 NW 44th Street, Lauderhill, FL 33319
| Towne Club Fort Lauderdale | LOST |  |  |  | 127 | Fision Home | LOST |  |  |  |  | 6696 NW 44th Street, Fort Lauderdale
| Trump Hollywood |  |  |  |  | 233 | Fision Home | Received | Wayde Webber |  |  |  | 2711 S Ocean Drive Hollywood, FL 33019 | Upgrade
| Turnberry Village South |  |  |  |  | 219 | Fision Home | NOT Approved to Upgrade |  |  |  |  | 20000 E Country Club Drive Miami, FL 33180
| Turnberry Yacht Club | Upcoming |  |  |  | 1 | Fision Stay | Pending | Juan Miranda | [5 empty] | Porsche |  | NA
| Twin Lakes | Upcoming | Pending Pre Budget |  |  | 279 | Fision Home | Pending | [6 empty] | Pending |  | Pending
| University Village | Upcoming |  |  |  | 187 Units/ 615 Beds | Fision U | In Sales Phase | Tony Robbins |  |  |  | 408 Campus View Dr. Townson, MD 21204
| University Village | Upcoming |  |  |  | 220 Units/ 749 Beds | Fision U | In Sales Phase | Tony Robbins |  |  |  | 1701 N 10th St. Philadelphia, PA 19122
| University Village at Prairie View | Upcoming |  |  |  | 648/2064 Beds | Fision U | Received | Tony Robbins |  |  |  | 300 East Bannon Street, Prairie View, TX 77446 | Upgrade
| Uptown ALF | Upcoming |  |  |  | 128 | Fision Home | In Sales Phase |  |  |  |  | NE 24th Ave & NE Pine Island Rd Cape Coral, Florida 33909 |  |  |  |  | Yes | ZTE |  | F668
| Villa San Remo HOA | Upcoming |  |  |  | 381 | Fision Home | Pending
| Villas of Positano | Upcoming |  |  |  | 76 | Fision Home | LOST | [6 empty] | 3rd Party Circuit
| Vizcaya Lakes | Certified |  |  |  | 1 | Demo | Not Applicable | Ben Kester |  |  |  | 280 Park Terrace Boynton Beach, FL 33426 | Upgrade | Vizcaya Lakes - ASR9006 - 10.63.255.91
| W Hotel/Viceroy | Upcoming |  |  |  | 220 | Fision Stay | Pending | Christian Galante
| Wave, The | Upcoming |  |  |  | 327 | Fision Home | In Sales Phase |  |  |  |  | 600 Alton Road Miami Beach, Florida 33139
| Whitney | Certified |  |  |  | 210 | Fision Home | Received |  |  |  |  | 410 Everia Street West Palm Beach, FL 33401
| Wind, The | Certified |  |  |  | 489 | Fision Home | Received | Diamond William |  |  |  | 350 S Miami Avenue Miami, FL 33130
World Trade Center Miami |  | Upcoming |  |  |  | 300 | Fision Home | In Sales Phase |  |  |  |  | 340 Biscayne Blvd Miami, Florida 33132
| Wycliffe Community | Upcoming |  |  |  | 1041 | Fision Home | LOST |  |  |  |  | 4550 Wycliffe Country Club Blvd
| Wynwood 26 | Upcoming |  |  |  | 176 | Fision Home | In Sales Phase |  |  |  |  | 51 NW 26th Street Miami, Florida 33131
| X Las Olas | Upcoming |  |  |  | 1200 | Fision Home | Pending |  |  |  |  | 300 SW 1st Avenue Fort Lauderdale, Florida, 33301 United States | New Construction |  | ASR9006 | X Las Olas [2] | Pending PCN | ALU | 12 | G-241G-B
| Tropic Bay Condominium |  |  |  |  | 399 | Fision Home
| WYNWOOD 25 | Upcoming |  |  |  | 289 | Fision Home | [5 empty] | 240 NW 25th Street Miami, Florida, 33127 United States
| French Village |  |  |  |  | 90 | Fision Home | [5 empty] | 775 Jeffery Street Boca Raton, FL 33487 | Conversion/OverBuild
| Valencia Isles |  |  |  |  | 793 | Fision Home | In Sales Phase |  |  |  |  | 11200 Valencia Isles Blvd Boynton Beach, FL 33437 | Conversion/OverBuild

## Geocoding (hidden)
addresskey | latitude | longitude | flag
2800 Old Milton Pkwy Alpharetta, GA 30009 | 34.06946690000001 | -84.27840909999999
601 NE 36th Street Miami, FL 33137 | 25.811021 | -80.1866783
601 NE 36th Street Miami, FL 33137 | 25.811021 | -80.1866783
10201 Collins Avenue, Bal Harbour, FL 33154 | 25.8951638 | -80.12323789999999
600 NE 31st St, Miami, FL 33137 | 25.8062284 | -80.1861552
7111, 17211, 17301 Biscayne Blvd., North Miami Beach, FL 33160 | 25.9342456 | -80.1495771
6400 Journeys End Blvd. Lake Worth, FL 33467 | 26.5810614 | -80.14761539999999
9703 Collins Avenue Miami, FL 33154 | 25.8892229 | -80.1228812
10471 Boca Woods Lane Boca Raton, FL 33428 | 26.35692 | -80.21148199999999
5150 N Federal Hwy Boca Raton, FL 33487 | 26.3960373 | -80.0755588
200 East Palmetto Park Boca Raton, FL 33432 | 26.3500276 | -80.0829131
9781 El Clair Ranch Road BOYNTON BEACH, FL 33437 | 26.5316222 | -80.1378318
2401 E 65th Street Fort Lauderdale, FL 33308 | 26.208949 | -80.10966239999999
270 Biscayne Boulevard Way, Miami, FL 33131 | 25.7705215 | -80.18933919999999
2399 Collins Ave, Miami Beach, FL 33139 | 25.799057 | -80.1273896
111 Surf Road Hallandale, FL | 25.9866784 | -80.1180505
2600 E. Hallandale Beach Blvd. Hallandale Beach, FL 33009 | 25.9859419 | -80.1227067
465, 475, 485 Brickell Ave Miami, FL 33131 | 25.7686168 | -80.1894844
2600 E. Hallandale Beach Blvd. Hallandale Beach, FL 33009 | 25.9859419 | -80.1227067
8101 Roseville Boulevard Davenport, Davenport, FL 33896 | 28.2663081 | -81.61347169999999
3003 Gulf Shore Blvd. N., Naples, FL 34 I 03 | 26.1820679 | -81.8135804
16001 Collins Avenue Miami, FL 33160 | 25.9240688 | -80.1216598
3925 N Miami Ave Miami, FL 33127 | 25.8128993 | -80.1953316
3711 SW 27th Street Miami, FL 33134 | 25.7415678 | -80.2547173
92 W 3rd Street Miami, FL 33131 | 25.769549 | -80.195165
5483 Boca Delray Blvd. Delray Beach, FL 33484 | 26.427299 | -80.1290275
8120 Logan Way Naples, Florida 34119 | 26.2708582 | -81.7026394
460 NE 28th St, Miami, Fl. 33137 | 25.8036403 | -80.1871142
16699 Collins Avenue Sunny Isles Beach, FL 33160 | 25.9302503 | -80.12113630000002
2701 NW 64 Blvd Boca Raton, FL 33496 | 26.4022346 | -80.1457586
800 S Pointe Drive Miami Beach, FL 33139 | 25.767723 | -80.13632
14401 Metro Parkway Fort Myers, FL 33912 | 26.5329385 | -81.85286579999999
10400 Kimberly Blvd. Boca Raton, FL 33498 | 26.3821937 | -80.2069087
3015 N. Ocean Blvd. Fort Lauderdale, FL | 26.166136 | -80.10141589999999
245 E. Blue Hero Blvd. West Palm Beach, FL 33404 | 26.783008 | -80.05030599999999
888 S Douglas Road Miami, FL 33134 | 25.7632524 | -80.25569809999999
17251 Newport Club Drive Boca Raton, FL 33496 | 26.421203 | -80.149182
300 S. Biscayne Blvd. Miami, FL 33131 | 25.7711417 | -80.1874545
701 S. Olive Avenue West Palm Beach, FL 33401 | 26.7065623 | -80.0524526
8130 Havasu Court Lake Worth, FL 33467 | 26.5953122 | -80.17712759999999
1100 Biscayne Blvd. Miami, FL 33131 | 25.7851774 | -80.1900783
17201 Collins Avenue Sunny Isles Beach, FL 33160 | 25.9355532 | -80.12113630000002
3201 Collins Ave, Miami Beach, FL 33140 | 25.8074337 | -80.1235138
3029 NE 188TH Street Aventura, FL 33180 | 25.9497024 | -80.14085209999999
901 Brickell Avenue Miami, FL 33131 | 25.7656106 | -80.1907464
10275 Collins Avenue Bal Harbour, FL 33154 | 25.897903 | -80.12344829999999

## Cisco Forecast Q3-Q4 2017
# | Projects | Unit # | Fed From | CAP YEAR | ASR9006-DC | ASR9010-DC | MOD-80 | 2X10G | 4X10G | 20X1GE
2017 Q3-Q4 - Forecasted to be Deployed
1 | 1000 Museum | 83 | 900 [Router] Marquis [Chassis] | 2017 | 1 |  | 2 | 0 | 2 | 2
2 | 2000 S Ocean | 64 | Beachclub | 2017 |  |  |  | 0 |  | 2
3 | 2500 Biscayne | 156 | Paraiso Bay ASR9006 | 2017 |  |  | 1 | 0 | 1 | 2
4 | 26 Edgewater | 86 | Parasio Bay | 2017 |  |  | 1 | 0 | 1 | 2
5 | 32 Royal Palm Condo | 24 | Via Mizner | 2017 |  |  | 1 | 0 |  | 1
6 | 747 Miami Center | 223 | Wind | 2017 |  |  | 1 | 0 | 1 | 2
7 | Aqualina Estates | 264 | Trump Hollywood | 2017 |  | 1 | 2 | 0 | 2 | 2
8 | Aria on the Bay | 660 | Quantum on the Bay | 2017 | 1 |  | 2 | 0 | 2 | 2
9 | Armani Casa Sunny Isles | 308 | Aqualina | 2017 |  |  | 1 | 0 | 1 | 2
10 | Auberge - Miami | 338 | Quantum or 900 ? Wilson to confirm [Aria] | 2017 |  |  | 1 | 0 | 1 | 2
11 | Aurora | 61 | TBD | 2017 | [5 empty] | 2 | Added 6/8/2017
12 | Avalon 9000 Hotel | 1 | Avalon ASR | 2017 | [5 empty] | 2 | Added 6/8/2017
13 | Aventura Park Square | 275 | TBD | 2017 |  |  | 1 |  | 1 | 2 | Added 6/8/2017
14 | Avida Senior Living | 460 | Node Insertion | 2018 | 1 |  | 2 |  | 2 | 2 | Added 6/8/2017
15 | Balmoral Haines City | 240 | 3rd Party Circuit | 2017 | 1 |  | 2 |  | 2 | 2 | Added 6/8/2017
16 | Bella Vista Phase 2 | 124 | Bella Vista | 2017 | [5 empty] | 2 | Added 6/8/2017
17 | Belle Isle | 144 | One Hotel | 2017 |  |  | 1 | 0 | 1 | 2
18 | Biltmore 2 | 232 | PDP | 2017 |  |  | 1 | 0 | 1 | 2
19 | Boca Lakes | 95 | Pelican Harbor/ BY&RC MDF | 2017 |  |  | 1 | 0 | 1 | 2
20 | Cascade Lakes | 600 | Valencia Lakes and Vizcaye | 2017 | 1 |  | 2 | 0 | 2 | 2
21 | Cloister Beach Tower | 124 | Stratford Arms | 2017 |  |  | 1 | 0 | 1 | 2
22 | Cypress Key at Park Central | 147 | 3rd Party [AT&T] - NAP | 2017 | 1 |  | 2 | 0 | 2 | 2
23 | Downtown Doral - Tower 10 | 225 | Modern Doral? | 2017 |  |  | 1 | 0 | 1 | 2
24 | Eagle Creek | 458 | NI: Bellasara and Deauville | 2017 | 1 |  | 2 | 0 | 2 | 2
25 | Emilia Edgewater Condos | 30 |  | 2017 |  |  | 1 |  | 1 | 2 | Added 6/8/2017
26 | Enclave at Boca Dunes (aka Whispering Lakes aka ) | 211 | Sinai Res | 2017 |  |  | 1 | 0 | 1 | 2
27 | Everglades Club | 44 | Auberge | 2017 |  |  |  | 0 |  | 0
28 | Eviva Yards (The Assembly) | 390 | Terminus [atl] | 2017 |  |  | 1 | 0 | 1 | 2
29 | Gale Residences, The | 129 |  | 2017 |  |  | 1 |  | 1 | 2 | Added 6/8/2017
30 | Genova | 205 | Pelican Landing | 2017 |  |  | 1 | 0 | 1 | 2
31 | Golfview Golf & Racquet Club | 400 | Venetian Pointe [Same MDF] | 2017 |  |  | 1 | 0 |  | 2
32 | Gran Parasio | 315 | Paraiso Bay _2 Chassis | 2017 |  |  | 1 | 0 | 1 | 2
33 | High Pointe Condo 1 | 259 |  | 2017 | 1 |  | 2 |  | 2 | 2 | Added 6/8/2017
34 | Icon Las Olas | 272 | The Church | 2017 |  |  | 1 | 0 | 1 | 2
35 | Jade Signature | 192 | Aqualina | 2017 |  |  | 1 | 0 | 1 | 2
36 | Magnolia Falls | 144 | Deauville | 2017 |  |  | 1 | 0 |  | 2
37 | Martinique at Abacoa | 480 | Frenchmans Creek | 2017 | 1 |  | 2 | 0 | 2 | 2
38 | Miami World Center Trailer | 1 | 900 and NAP | 2017 | 2 |  | 4 | 0 | 4 | 4
39 | Midtown Apartments [Naples] | 90 | 3rd Party Circuit - Cypress Office | 2017 | 1 |  | 2 | 0 | 2 | 2
40 | Mosaic at the Forum | 252 | NI: Oasis and Ole Cypress | 2017 | 1 |  | 2 | 0 | 2 | 2
41 | Mystic Pointe Tower 1 | 289 | UML | 2017 |  |  | 1 | 0 | 1 | 2
42 | One Brickell | 1430 | BCC East Tower | 2017 | 1 |  | 2 | 0 | 2 | 2
43 | Park Square Doral | 280 |  | 2017 |  |  | 1 |  | 2 | 2 | Added 6/8/2017
44 | Prima Luce on the Waterfront | 220 | Oasis Ft Myers? | 2017 |  |  | 1 | 0 | 1 | 2
45 | Prive at Island Estates | 178 | PEN2 | 2017 | 1 |  | 2 | 0 | 2 | 2
46 | Richmond Park [Phase 1 and 2] | 124 | Vanderbilt | 2017 |  |  | 1 | 0 | 1 | 2
47 | Ritz Carlton Residences | 212 | NEW ASR NEEDED! Fed from Trump? | 2017 | 1 |  | 2 | 0 | 2 | 2
48 | Santorini at Renaissance Commons | 226 | Vizcaya Lakes | 2017 |  |  | 1 | 0 | 1 | 2
49 | Torino Lakes | 148 | St James? OR Harbor Ridge? | 2017 |  |  | 1 | 0 | 1 | 2
50 | TRYP Hotel | 150 | 3rd Party Circuit to Cypress | 2017 |  | 1 | 4 | 0 | 2 | 6
51 | Tuscany at Abacoa | 446 | ASR Needed - fed from F.Creek | 2017 | 1 |  | 2 | 0 | 2 | 2
52 | Uptown ALF | 128 | North Star Yacht Club | 2017 |  |  | 1 | 0 | 1 | 2
53 | Uptown Residential | 320 | North Star Yacht Club | 2017 |  |  | 1 | 0 | 1 | 2
54 | URBANEA | 100 | PDP | 2017 | 1 |  | 2 | 0 | 2 | 2
55 | Venetian Pointe | 180 | NI: Mbay & Synery | 2017 | 1 |  | 2 | 0 | 2 | 2
56 | Versailles at Wellington | 450 | Isle of Wellington | 2017 |  |  | 1 | 0 | 2 | 2
57 | Villa Borghese | 582 | Valencia Lakes?? | 2017 | 1 |  | 2 | 0 | 2 | 2
58 | Villas of Positano | 76 |  | 2017 |  |  |  | 0 |  | 0
59 | VistaBlue Singer Island | 58 | Marina Grande | 2017 |  |  |  | 0 |  | 0
60 | Wellington Shores | 181 | Isle of Wellington | 2017 |  |  |  | 0 |  | 0
61 | Pop Up |  |  | 2017 |  | 5 | 10 |  | 10 | 10
| TOTAL | 14584 |  |  | 20 | 7 | 87 |  | 84 | 127
2017 Q3-Q4 - Pending Info to Forecast
62 | 6080 Collins | 1 | TBD | 2017
63 | 811 Peachtree | 400 | TBD | 2017 | [6 empty] | Added 6/8/2017
64 | Alhambra Cove | 240 | TBD | 2017
65 | All Aboard Florida | 800 | TBD | 2017
66 | Avalon Convention Center |  | Avalon ASR? | 2017
67 | Avalon Medical Facility |  | Avalon ASR? | 2017
68 | Botaniko - Weston Estates Sales Center | 120 | OSP Pending | 2017 | [6 empty] | Nexus
69 | Babcock Ranch | 1000 | TBD | 2017
70 | Centennial Park Apts | 2 | TBD | 2017
71 | Colonnade Building, The | 570 | TBD | 2017
72 | Creekside Village Parcel B | 200 | NI? | 2017 | [6 empty] | Nexus
73 | Delray Place | 76 | TBD | 2017 | [6 empty] | Added 6/8/2017
74 | Coral Plaza | 183 |  | 2017
75 | Costa Hollywood (Hotel) | 310 |  | 2017
76 | Courtyards at Boca | 200 |  | 2017
77 | Doral Landings West | 242 |  | 2017
78 | Estates at Stuart, The | 237 |  | 2017
79 | Flats at Mallard Creek | 131 |  | 2017
80 | Gables Gate 2 | 224 |  | 2017
81 | Goldcoaster | 545 |  | 2017
82 | Golden Lakes Village | 1088 |  | 2017
83 | High Pointe Condo 2 | 267 |  | 2017
84 | Huntcrest | 299 |  | 2017
85 | Lakes at Savannahs, The | 243 |  | 2017
86 | Las Olas Beach Club | 148 |  | 2017
87 | Libery Cluster/Campus Project |  |  | 2017
88 | Muse | 68 | Acqualina | 2017 | [6 empty] | Added 6/8/2017
89 | Miami Bay Club | 176 |  | 2017 | [6 empty] | Added 6/8/2017
90 | Monarch in BAL Harbor | 1 |  | 2017
91 | Oakbrook Village | 343 |  | 2017
92 | Park Grove | 298 |  | 2017 | [6 empty] | Added 6/8/2017
93 | Parkway 400 |  |  | 2017 | [6 empty] | Added 6/8/2017
94 | Porco Mare | 237 | OSP Needed | 2017 | [6 empty] | Added 6/8/2017
95 | Panorama Tower | 821 |  | 2017
96 | Preserve at Savannahs, The | 94 |  | 2017
97 | Promenade Shores at Doral | 240 |  | 2017
98 | Rancho | 1900 |  | 2017
99 | Residences of Riviera Palms, The | 248 |  | 2017
100 | River Walk | 1230 |  | 2017
101 | Solemia | 4390 |  | 2017 | [6 empty] | Added 6/8/2017
102 | Spoke | 224 |  | 2017 | [6 empty] | Added 6/8/2017
103 | Summerhill | 96 |  | 2017 | [6 empty] | Added 6/8/2017
104 | Savannahs Condo, The | 211 |  | 2017
105 | Sereno Assisted Living | 64 |  | 2017
106 | Shalimar at Davie | 240 |  | 2017
107 | Somerset Tower | 115 |  | 2017
108 | Stadium Walk | 309 |  | 2017
109 | Summer Chase | 221 |  | 2017
110 | Sunshine Lakes | 208 |  | 2017
111 | Third Rail Studio | 1 |  | 2017 | [6 empty] | Added 6/8/2017
112 | Towne Club Fort Lauderdale | 127 |  | 2017 | [6 empty] | Added 6/8/2017
113 | Tributary Media Room Conversion | 325 |  | 2017 | [6 empty] | Added 6/8/2017
114 | Turnberry Yacht Club | 1 |  | 2017 | [6 empty] | Added 6/8/2017
115 | Twin Lakes | 279 |  | 2017
116 | Villa San Remo HOA | 381 |  | 2017
20374

## Cisco Forecast Q1-Q2 2018
2018 NEW FORECAST! | [9 empty] | hide these columns before providing to LOU
Projects | Unit # | Fed From | CAP YEAR | ASR9006-DC (Bundle) | ASR9010-DC | Nexus 9K | MOD-200 | 4X10G | 20X1GE | ASR920 | ? | PRIOR NOTES:
115 Sunrise Condominium | 14 | Oceana Key Biscayne | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
16000 Pines Market | 122 | Pem Falls | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
3200 INC | 80 | CIRCUIT | 2018 | 1 |  |  | 2 | 2 | 2 |  |  | utilized not forecasted
6080 Collins | 140 | Carillon | 2018 |  |  | 1 | 1 | 1 |  |  | P | 2017 not forecasted
811 Peachtree | 400 | TBD | 2018 | 1 |  |  | 2 | 2 | 2 |  | P | 2017 not forecasted
Akoya Boca West | 139 | Boca West | 2018 | [6 empty] | 1 | N | 2018 FORECAST
Aloft Hotel - Aventura Park Square | 207 |  | 2018 | 1 |  |  | 2 | 2 | 2 |  |  | utilized not forecasted
Aqua at Pelican Isle Condominium | 80 | Naples MDF [Office] | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2018 FORECAST
Armani Casa Sunny Isles | 308 | Aqualina | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
Auberge- Fort Lauderdale | 171 | Berkley South | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2018 FORECAST
Auberge- Miami | 338 | Quantum | 2018 |  |  |  | 1 | 1 | 1 | 1 | p
Aurora Condo | 61 | Acqualina | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
Avalon Convention Center | 1 | Avalon ASR? | 2018 | 1 |  |  | 2 | 2 | 2 |  | Y | 2017 not forecasted
Avalon Medical Facility | 1 | Avalon ASR? | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2017 not forecasted
Aventura Park Square | 131 | NI: Trump Holly and Beachwalk | 2018 | 2 |  |  | 4 | 4 | 4 |  | Y | 2018 FORECAST
Barclay Condo | 210 | 3200 Inc | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
Bay Harbor One | 36 | Sereno | 2018 | [6 empty] | 1 | N | 2018 FORECAST
Biscayne Cove | 592 | UML | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
Boca Yacht & Racquet Club | 3000+ | ROUTER 2 | 2018 | 1 |  |  | 4 | 4 | 4 |  |  | utilized not forecasted
Bonita Bay | 3507 | Pelican Landing | 2018 |  | 1 |  | 6 | 5 | 6 |  |  | utilized not forecasted
Botaniko | 125 | 2G Off-Net Circuit: 2100 | 2018 | 1 |  |  | 2 | 2 | 2 |  | Y | 2018 FORECAST
Brickell West - 747 Miami Center | 223 | 819 | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
Canvas Condo | 513 | Quantum & 900B [ASR9010] | 2018 |  | 1 |  | 2 | 2 | 2 |  | N | 2018 FORECAST
Cassa Grove | 122 | Pending | 2018 | [7 empty] | N | 2018 FORECAST
Clarity Pointe | 215 | Martinique at Abacoa | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
CYPRESS - COLO | 1 | COLO | 2018 |  | 1 |  | 4 | 4 | 4 |  |  | utilized not forecasted
Delray Place | 76 | TBD | 2018 | 1 |  |  | 2 | 2 | 2 |  | P | 2017 not forecasted
Diamondhead Beach Resort | 124 | 5G Offnet Circuit | 2018 |  |  | 1 |  |  |  |  | Y | 2018 FORECAST
Flats at Mallard Creek | 131 | CIRCUIT | 2018 | 1 |  |  | 2 | 2 | 2 | 1 | Y | 2017 not forecasted
Frenchmans Creek- UPGRADE | 3000+ | To feed: Abacoas, Sonoma Bay, Marlwood, Tiara, Jup. CC | 2018 |  | 1 |  | 6 | 10 | 2 |  |  | utilized not forecasted
Gables Gate 2 | 224 |  | 2018 | 1 |  |  | 2 | 2 | 2 |  | P | 2017 not forecasted
Giralda Place | 33 | PDP | 2018 | [5 empty] | 1 | 1 | N | 2018 FORECAST
Heritage Bay Golf and Country Club | 1250 | Vanderbuilt and Old Cypress | 2018 |  | 1 |  | 4 | 4 | 4 |  | N | 2018 FORECAST
Hollywood Circle | 386 | MR Ring | 2018 | 1 |  |  | 2 | 2 | 2 |  |  | utilized not forecasted
Hollywood Circle -HANDOFF | 104 | NI: New River & Beachwalk | 2018 | 1 |  |  | 2 | 2 | 2 |  | Y | 2018 FORECAST
Hunters Run | 1649 | St Andrews and Valencia Lakes | 2018 |  | 1 |  | 4 | 4 | 4 |  | N | 2018 FORECAST
Jade Signature | 192 |  | 2018 | 1 |  |  | 1 | 1 | 1 |  |  | utilized not forecasted
Jupiter Country Club | 545 | Frenchmans Creek | 2018 | 1 |  |  | 2 | 2 | 2 |  |  | utilized not forecasted
Lake Washington | 288 | CIRCUIT | 2018 | 1 |  |  | 2 | 2 | 2 |  |  | utilized not forecasted
Mallory Creek | 595 | Martinique | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2018 FORECAST
Meadows at Martin Downs | 832 | Harbor Ridge | 2018 | 1 |  |  | 2 | 2 | 2 |  | N | 2018 FORECAST
Miami River Landing | 526 | Pending | 2018 | [7 empty] | N | 2018 FORECAST
Midtown Miami 3 Hotel | 60 | Midtown 2 | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2018 FORECAST
Muse | 68 | Acqualina | 2018 | 1 |  |  | 2 | 2 | 2 |  | Y | 2018 FORECAST
Oceantree | 146 | Marina Grande | 2018 | [5 empty] | 1 | 1 | N | 2018 FORECAST
Park Grove | 298 | PASSIVE | 2018 | [6 empty] | 1 | Y | 2017 not forecasted
Park Square Assisted Living | 141 | Aventura MR | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2018 FORECAST
Pembroke Pines City Center | 350 | Pembroke Falls | 2018 | 1 |  |  | 2 | 2 | 2 |  | N | 2018 FORECAST
Point Orlando Resort | 144 | CIRCUIT | 2018 | 1 |  |  | 2 | 2 | 2 |  |  | utilized not forecasted
Promenade Shores at Doral | 240 | Modern Doral | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2017 not forecasted
Portofino Tower | 228 | Apogee South Beach | 2018 |  |  |  | 1 | 1 | 1 | 1 | P | 2018
Sereno Assisted Living | 64 |  | 2018 |  |  | 1 | 1 | 1 | 1 | 1 | Y | 2017 not forecasted
Silverleaf | 141 | Journey End | 2018 | [6 empty] | 1 | N | 2018 FORECAST
Skylink | 1 | COLO | 2018 |  | 2 |  | 8 | 8 | 6 |  |  | utilized not forecasted
Sole Mia | 500 |  | 2018 | 1 |  |  | 2 | 2 | 2 |  | P | 2017 not forecasted
Somerset Tower (Jenny Tower) | 115 | Modern Miami | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
Spoke | 224 |  | 2018 | 1 |  |  | 2 | 2 | 2 |  | Y | 2017 not forecasted
Square Station | 710 | Quantum, 900 Biscayne | 2018 | 1 |  |  | 2 | 2 | 2 |  | Y | 2018 FORECAST
St Andrews | 3000+ | To feed: 20G ring upgrade; Broken Sound, Woodfield, Orchid, Newport, | 2018 |  | 1 |  | 6 | 10 | 2 |  |  | utilized not forecasted
Strata at Plantation | 147 | Bella Vista | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2018 FORECAST
Summit Garden | 102 | Summit Garden | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2018 FORECAST
Synergy - Naples COLO | 1 | COLO | 2018 | 1 |  |  | 4 | 4 | 2 |  |  | utilized not forecasted
The Circ Hotel, Hollywood | 115 | hand off | 2018 | 1 |  |  | 2 | 2 | 2 |  |  | utilized not forecasted
The Reserve at Lake Keowee | 854 | 10G Off-Net Circuit: 55M | 2018 | 1 |  |  | 2 | 2 | 2 |  | Y | 2018 FORECAST
Tributary Media Room Conversion | 325 |  | 2018 | 1 |  |  | 2 | 2 | 2 |  | P | 2017 not forecasted
Uptown at Liberty Park | 320 | NI: Synergy and North Star | 2018 | 1 |  |  | 2 | 2 | 2 |  | Y | 2018 FORECAST
Valencia Shores-UPGRADE | 3000+ | To feed: 20G ring upgrade; Whitney, IoW, Boyntn Office, Cobblestone, Journeys End, Valencia Pointe, HBS locations | 2018 |  | 1 |  | 4 | 6 | 2 |  |  | utilized not forecasted
Vice Miami | 464 | Vizcayne | 2018 |  |  |  | 1 | 1 | 1 | 1 | N | 2018 FORECAST
Woodmere | 246 | Summit Garden | 2018 |  |  |  | 1 | 1 | 1 | 1 | Y | 2018 FORECAST
Zattoo | 1 | COLO | 2018 |  | 1 |  | 4 | 4 | 4 |  |  | utilized not forecasted
| Unit # |  |  | ASR9006-DC (Bundle) | ASR9010-DC | Nexus 9K | MOD-200 | 4X10G | 20X1GE | ASR920
TOTAL: | 20697 |  |  | 28 | 11 | 3 | 131 | 140 | 118 | 30

## TOTAL Market Critical Spare
Hotwire Market Critical Spares - Total
Description | Model | QTY | Unit Cost | Total Cost
Routers - ASR9K
Cisco ASR9010 | ASR9010-DC Chassis | 3 | 4114 | 12342
Cisco ASR9006 | ASR9006-DC Chassis | 5 | 3060 | 15300
ASR-9006 Fan Tray Version 2 | ASR-9006-FAN-V2 | 20 | 1309 | 26180
Cisco RSP Module | A9K-RSP880-TR | 10 | 25500 | 255000
2KW DC Power Module Version 2 | PWR-2KW-DC-V2 | 20 | 952 | 19040
ASR9000 MOD200-TR | A9K-MOD200RL-TR | 8 | 34000 | 272000
ASR 9000 24-port 10GE & 1GE dual rate | A9K-24X10GE-1G-TR | 7 | 32340 | 226380
ASR 9000 4-port 10GE Modular Port Adapter | A9K-MPA-4X10GE | 10 | 8820 | 88200
ASR 9000 20-port 1GE Modular Port Adapter | A9K-MPA-20X1GE | 10 | 3200 | 32000
Routers - 7606
Cisco C7606-S | C7606-S | 2 | 3500 | 7000
Supervisor Engine 720 | WS-SUP720-3B | 4 | 4495 | 17980
CEF720 4 port 10-Gigabit Ethernet | WS-X6704-10GE | 2 | 6599 | 13198
CEF720 8 port 10-Gigabit Ethernet | WS-X6708-10GE | 2 | 9949 | 19898
CEF720 24 port 1000mb SFP | WS-X6724-SFP | 2 | 3895 | 7790
Switches/Routers
Nexus 93180YC-EX - AC | N9K-C93180YC-EX | 3 | 22137.5 | 66412.5
Nexus 93180YC-EX - DC | N9K-C93180YC-EX | 1 | 22137.5 | 22137.5
MikroTik NAT Router | CCR1072-1G-8S+ | 10 | 3000 | 30000
Cisco ASR920 Series - 12GE and 2-10GE - AC model | ASR-920-12CZ-A | 5 | 1600 | 8000
Catalyst 2960-X 24 GigE PoE 370W, 2 x 10G SFP+, LAN Base | WS-C2960X-24PD-L | 20 | 905.22 | 18104.4
GPON
ZTE OLT | ZXA10-C300 | 2 | 22153 | 44306
ZTE 8-PORT PON Card | GTGO-G | 3 | 6482.92 | 19448.76
ALU/Nokia OLT Bundle | ISAM 7360 FX-8 | 5 | 19800 | 99000
ALU/Nokia 8 Port PON Card | NGLT-C | 4 | 8000 | 32000
ALU/Nokia 16 Port PON Card | FGLT-A | 4 | 13500 | 54000
ALU/Nokia 7360 Controller Card | FANT-F | 8 | 8000 | 64000
ALU/Nokia XGS 8 Port PON Card | FWLT-B | 2 | 9265 | 18530
ALU/Nokia SFP B+ Optics | SFP B+ | 32 | 175 | 5600
XGS Optics | XGS Dual Rate XFP N1 (C-temp) OLT | 16 | 420 | 6720
Optics
ASR Ten Gig Optic -LR | XFP-10GLR-OC192SR | 10 | 180 | 1800
ASR Ten Gig Optic 10G-ER | XFP-10GER-OC192IR | 10 | 3700 | 37000
ASR Ten Gig Optic 10G-ZR | XFP-10GZR-OC192LR | 8 | 3700 | 29600
Cisco Ten Gig Optic - LR | XENPAK-10GB-LR | 10 | 670 | 6700
Cisco Ten Gig Optic - ER | XENPAK-10GB-ER | 10 | 3495 | 34950
Cisco Ten Gig Optic - ZR | XENPAK-10GB-ZR | 8 | 3495 | 27960
Cisco Ten Gig Optic - LR | X2-10GB-LR | 10 | 675 | 6750
Cisco Ten Gig Optic - ER | X2-10GB-ER | 10 | 3495 | 34950
Cisco Ten Gig Optic - ZR | X2-10GB-ZR | 8 | 3495 | 27960
Cisco Ten Gig Optic - LR | SFP-10G-LR | 10 | 675 | 6750
1G SFP SM | GLC-LH-SM | 10 | 75 | 750
1G Copper SFP | GLC-T | 10 | 40 | 400
1G-SFP Bidirectional Optic | GLC-BX-D | 7 | 120 | 840
1G-SFP Bidirectional Optic | GLC-BX-U | 7 | 120 | 840
10G-XFP Bidirectional for 10km | XFP-10G-BX10U-I | 5 | 675 | 3375
10G-XFP Bidirectional for 10km | XFP-10G-BX10D-I | 5 | 675 | 3375
10G-XFP Bidirectional for 40km | XFP-10G-BX40U-I | 5 | 1660 | 8300
10G-XFP Bidirectional for 40km | XFP-10G-BX40D-I | 5 | 1660 | 8300
10G-XFP Bidirectional for 60km | XFP-10G-BX60U-I | 5 | 2295 | 11475
10G-XFP Bidirectional for 60km | XFP-10G-BX60D-I | 5 | 2295 | 11475
10G-XFP Bidirectional for 80km (ZR) | XFP-10G-BX80U-I | 5 | 2295 | 11475
10G-XFP Bidirectional for 80km (ZR) | XFP-10G-BX80D-I | 5 | 2295 | 11475
WiFi
Access Points | R610 | 8 | 405 | 3240
Access Points | R700 | 8 | 415 | 3320
Access Points | T300 | 8 | 550 | 4400
Access Points | T310C | 8 | 485 | 3880
Access Points | T310S | 4 | 685 | 2740
Access Points | T310N | 4 | 685 | 2740
Access Points | H510 | 8 | 170 | 1360
Encoder |  | 0
Encoder | Encoder | 6 | 15600 | 93600
Encoder GBE Card | Encoder GBE Card | 6 | 895 | 5370
Encoder 8VSB Card | Encoder 8VSB Card | 6 | 2419 | 14514
Miscellaneous
Racks [42U Rack Enclosure - with access control by HWC] | 42U Rack Eclosure | 10 | 724.99 | 7249.9
Total |  |  |  | 1929481.06